Shake Shack – Oak Lawn, IL - Commissioning Kick-Off Meeting

Collaboration & Communication

- Kick off meeting

- Team identification and roles

- Support [OEM’S & AEC team]

- Reporting Methods

Field Installation Verification:  Specified Materials, Routing, Size, Supports

- CxA will perform field verification of details for underground, in-wall, and above ceiling inspections

- Review will consist of division specified materials, routing, size, supports, installation details

- Issues or RFI’s will be sent if omissions, errors, or change request are identified

- GC/Trade should respond no later than 5 business days with resolution or clarification response

- Engineer/Owner may review for acceptance any requested change

Pre-Commissioning Checklist of specified equipment:

Division specific checklist have been sent to each responsible trade for review of required checklist.  Each trade is to review and accept or revise as necessary the checklist to ensure it accurately reflects their scope, installation details, and local AHJ code requirements.  CxA will setup a quick review meeting with each of the following contractors to review the mark-ups and resubmit.  At that time, we can register you onto the FaciliBuild-HUB platform if you would like to complete the online checklist rather than complete a hard copy version.

Each Checklist will be organized in a similar manner:

- Identification:  Matches accepted submittal data

- Installation details:  Installed per MFG requirements, design details, and local code

- Operation:  Normal and abnormal interlocks and operation

  - Startup reports to be collected

  - City inspection reports to be collected

  - Specialized testing

  - GC – Owner authorized installation certificate of installation

Completed checklist are due prior to final commissioning is to be scheduled.

Functional Performance testing:

To be completed by the commissioning agent.

- Review all completed checklist

- Ensure all open issues / RFI’s created during the processes have been resolved

- TAB has been completed

Overview:  Each divisional contractor to be available / present on site during their scheduled test period.  Anticipate 4 hours, but in some cases, this may be reduced based on previous inspections, city test, startups and functional verifications.  CxA may require test be repeated outside of city or other specialized testing periods or even as validated by the contractors pre-commissioning checklist.  When possible the CxA will be present or other consent during time of city/specialized testing to prevent duplication of these test.

Electrical

- Ensure all circuit power is connected to correct appliances

- Demonstrate panel A,B,C phase Loads

- Test all GFCI outlets

- Validate timers are set correctly and are functional

- Validate starter/overloads

- Validate emergency back-up systems/power

- Review SOO of normal and abnormal operation and validate interlocks

Sprinkler

- Tamper Valves

- Test Drain

- Flow switch

- Dry Valve – Compressor settings and operation

Plumbing

- Test all gas line pressures at appliances (100% load)

- Validate all external regulator pressure settings

- Test all water heater safety devices and settings

- Validate sequence of operation of the recirculated hot water/hot water heater system

- Test mixing Valve – sink hot water heater temperatures and time

HVAC

- TAB report completed

- RTU settings, thermostat programming, sensor calibration

- RTU coil performance EAT/LAT conditions (1st stage, 2nd stage)

- Sub-cool and super heat setpoints & control

- Free cooling enthalpy sensors and SOO

- Dehumidification performance

- Fire suppression interlocks – RTU shutdown

- Space performance manual & automatic control

- Hood capture test

- Building pressure unoccupied, occupied, free cooling

Lighting

- Startup

- Programming

- Validate sensors &  SOO

- Measure Space lighting manual and automatic operation