## AHU- (115)
National TAB
Project: GSA DC0021ZZ Central office Headquarters (Washington, DC)
System:
Supply Air CFM Measured: | 258 CFM
Confirm DCV is Disabled (Demand Controlled Ventilation) | DCV IS CONFIRMED TO BE DISABLED.
Outside Air Measurement Method (Direct PT or SA-RA PT) | THIS UNIT IS RUNNING 100% OUTSIDE AIR.
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units) | 258 CFM
Outside Air CFM Measured: (with fan at maximum allowable speed) | THIS IS A CONSTANT VOLUME UNIT.
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM: | THIS UNIT IS RUNNING 100% OUTSIDE AIR.
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside AIr Damper Setpoint BAS shows. | THIS IS A CONSTANT VOLUME UNIT.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive. | THIS IS A CONSTANT VOLUME UNIT.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.] | THIS UNIT IS RUNNING 100% OUTSIDE AIR.
Does AHU have full air side economizer? | THIS UNIT IS RUNNING 100% OUTSIDE AIR.
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate. | SEE SITE PICTURES.
Pre-Filter MERV Rating (or NA) | THIS UNIT HAD NO PRE FILTERS IN USE.
Pre-Filter Size | N/A
Final Filter MERV Rating | THE FINAL FILTERS WERE MARKED AS MERV 8.
Final Filter Size | THE FINAL FILTERS WERE 20X22X1
Belts - Visual Assessment of condition | THERE WAS NO ACCESS TO THE BELT DRIVE.
Belts - Size and quantity | THERE WAS NO ACCESS TO THE BELT DRIVE.
Note any modifications made to AHU set points to operate in full capacity. | THIS IS A CONSTANT VOLUME UNIT.
Note if the AHU has full air side economizing ability & Damper Type. | THIS UNIT RUNS 100% OUTSIDE AIR.
Electrical connections - Visual assessment. Document motor Voltage and Amperage. | THERE WAS NO ACCESS TO THE ELECTRICAL CONNECTIONS
Heating Coil(s) - Visual assessment and photo documentation. | THERE WAS NO HEATING OR COOLING COIL.
Cooling Coil(s) - Visual assessment and photo documentation. | THERE WAS NO HEATING OR COOLING COIL.
Condensate Pan(s) - Visual assessment and photo documentation. | THERE WAS NO HEATING OR COOLING COIL.
Any unusual operation observed? (including vibration, over-pressure, etc.) | NO UNUSUAL OPERATION WAS OBSERVED AT THE UNIT.
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A" | NO EXHAUST SYSTEM WAS INSTALLED.
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity. | AS FAR AS IT COULD BE ACCESSED AND SEEN, THE OUTSIDE AIR INTAKE LOUVER WAS CLEAR AND IN GOOD CONDTION.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry. | AS FAR AS IT COULD BE ACCESSED AND SEEN, THE OUTSIDE AIR INTAKE LOUVER WAS CLEAR AND IN GOOD CONDTION.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings. | NO DEFICIENCIES WERE IDENTIFIED AT THE UNIT.