NT-SS Field Commissioning Activities

Shake Shack – McKinney, TX Commissioning Activities

Activity 1: (Just before break-ground)

Kick-Off Video Presentation:

- What is commissioning

- Communication plan and resource HUB

  - Team

  - Checklist (FIV, Readiness, FPT)

  - Issues & RFI’s

  - Files

- FIV inspection

- Pre-Commissioning Readiness

- FPT inspections

- Close-out

Activity 2 (Below Slab Inspection):  2 weeks prior to scheduled inspection

- Send out/Share FIV inspection checklist

  - Underground

    - SS, GC, Plumber, Electrician

    - NTAB communication Team will contact trades to ensure they reviewed and understood checklist and requirements

- During inspection Issues will be developed and shared while on site.

- Trade will be required to acknowledge issue

- Issue must be documented and resolved prior to pouring back the slab

- Send Inspection report

Activity 3 (In-Wall Inspection):  2 weeks prior to scheduled inspection

- Send out/Share FIV inspection checklist

  - In-Wall

    - SS, GC, Plumber, Electrician

    - NTAB communication Team will contact trades to ensure they reviewed and understood checklist and requirements

- During inspection Issues will be developed and shared while on site.

- Trade will be required to acknowledge issue

- Issue must be documented and resolved prior to closing walls

- Send Inspection report

Activity 4 (Above Ceiling/Roof):  2 weeks prior to scheduled inspection

- Send out/Share FIV inspection checklist

  - Above Ceiling / Roof

    - SS, GC, Plumber, Electrician, Mechanical, Sprinkler

    - NTAB communication Team will contact trades to ensure they reviewed and understood checklist and requirements

- During inspection Issues will be developed and shared while on site.

- Trade will be required to acknowledge issue

- Issue must be documented and resolved prior to closing walls

- Send Inspection report

Activity 5 (Pre-Commissioning Readiness):  2 weeks prior to scheduled inspection

- Send out/Share Pre-Commissioning Readiness Checklist

  - Final Equipment Installation Validation

    - SS, GC, Plumber, Electrician, Mechanical, Sprinkler, Fire Suppression

    - NTAB communication Team will contact trades to ensure they reviewed and understood checklist and requirements

- Readiness checklist must be completed prior to Scheduling on-site CxA activities

- Startups must be completed by HVAC & Plumbing Trades

- Successful finals must be completed by sprinkler and suppression trades

- TAB must be completed

Activity 6 (FPT Test):  1 weeks prior to scheduled inspection

Send out / Share FPT test Checklist

- Day 1:  Schedule 2 hours on site with each trade to go over final installation details, Setup, Startup details, interlocks & SOO.

- Day 2-4: Upon validating each section NT will commence the Cx functions

- Trade must return prior to end of day 4 if any resolutions are required for full functional performance of the equipment/systems

- Lighting controls provider must be scheduled to be on site to validate lighting startup during the FPT test dates

Activity 7 (Close-Out): 1 week after commissioning activities

Validate all final warranty documents have been uploaded and are enforceable

Validate operational team has scheduled required training

Validate O/M manuals are available to operations team and stored in appropriate place

Send final report