## CRAC-1-1
National TAB
Project:
Address:
Asset: CRAC-1-1 |  | Area: IDF 01D01
Unit Data |  |  |  |  | Test Data
MFG | [5 empty] | Design | Actual
Model Num |  |  |  |  | SA CFM | 500
Serial Num |  |  |  |  | Fan Speed
OA CFM
RA CFM
Motor Data |  |  |  |  | RL Voltage | 265
Motor MFG |  |  |  |  | RL Amperage | 7.5
Horsepower | 0.33 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 265 |  |  |  | Brake HP
Amperage (rated) | 7.5
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
C11-1 | 01D01 | F | 22X10 | 500 |  |  | 0
SGRD TOTAL |  |  |  | 500 |  | 0 | 0
RC11-1 | 01D01 | E | (2) 24X12 | 500 |  |  | 0
EGRD TOTAL |  |  |  | 500 |  | 0 | 0
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FPVAV's
National TAB
Project: CW 2999 - Langan
Address: 2999 OLYMPUS BLVD, DALLAS, TX
Asset: Series Fan Powered Boxes
Asset | Area Served | Address | Type | Size | Design Pri Max CFM | Actual Pri Max CFM | Design Pri Min CFM | Actual Pri Min CFM | Design Fan CFM | Actual Fan CFM | Ak (max)
FPB-1-1 | 01B02 |  | REHEAT | 10 | 650 |  | 162.5 |  | 455
FPB-1-2 | OPEN OFFICE |  | REHEAT | 10 | 1000 |  | 250 |  | 700
FPB-1-3 | OPEN OFFICE |  | REHEAT | 16 | 2240 |  | 560 |  | 1568
FPB-1-4 | OPEN OFFICE |  | REHEAT |  | 1750 |  | 437.5 |  | 1225
FPB-1-5 | 01K01 |  | REHEAT |  | 1000 |  | 250 |  | 700
NOTES: | FPB DESIGN MAX IS DIFFUSER TOTAL, DESIGN MIN IS 25% OF MAX, FAN IS 70% OF MAX.
Note on C7: NTAB: BILLINGSLEY ONLY

## FPVAV SGRD's
National TAB
Project: CW 2999 - Langan
Address: 2999 OLYMPUS BLVD, DALLAS, TX
Asset: FPVAV SGRD's
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F11-1 | 01B02 | B | 16X4 | 130 |  |  | 0
F11-2 | 01B02 | B | 16X4 | 130 |  |  | 0
F11-3 | 01B02 | B | 16X4 | 130 |  |  | 0
F11-4 | 01B02 | B | 16X4 | 130 |  |  | 0
F11-5 | 01B02 | B | 16X4 | 130 |  |  | 0
FPB-1-1 |  |  |  | 650 |  | 0 | 0
F12-1 | OPEN OFFICE | A | 10 | 250 |  |  | 0
F12-2 | OPEN OFFICE | A | 10 | 250 |  |  | 0
F12-3 | OPEN OFFICE | A | 10 | 250 |  |  | 0
F12-4 | OPEN OFFICE | A | 10 | 250 |  |  | 0
FPB-1-2 |  |  |  | 1000 |  | 0 | 0
F13-1 | OPEN OFFICE | A | 10 | 320 |  |  | 0
F13-2 | OPEN OFFICE | A | 10 | 320 |  |  | 0
F13-3 | OPEN OFFICE | A | 10 | 320 |  |  | 0
F13-4 | OPEN OFFICE | A | 10 | 320 |  |  | 0
F13-5 | OPEN OFFICE | A | 10 | 320 |  |  | 0
F13-6 | OPEN OFFICE | A | 10 | 320 |  |  | 0
F13-7 | OPEN OFFICE | A | 10 | 320 |  |  | 0
FPB-1-3 |  |  |  | 2240 |  | 0 | 0
F14-1 | OPEN OFFICE | A | 10 | 350 |  |  | 0
F14-2 | OPEN OFFICE | A | 10 | 350 |  |  | 0
F14-3 | OPEN OFFICE | A | 10 | 350 |  |  | 0
F14-4 | OPEN OFFICE | A | 10 | 350 |  |  | 0
F14-5 | OPEN OFFICE | A | 10 | 350 |  |  | 0
FPB-1-4 |  |  |  | 1750 |  | 0 | 0
F15-1 | 01K01 | C |  | 200 |  |  | 0
F15-2 | 01K01 | C |  | 200 |  |  | 0
F15-3 | 01K01 | C |  | 200 |  |  | 0
F15-4 | 01K01 | C |  | 200 |  |  | 0
F15-5 | 01K01 | C |  | 200 |  |  | 0
FPB-1-5 |  |  |  | 1000 |  | 0 | 0
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!

## VAV's
National TAB
Project: CW 2999 - Langan
Address: 2999 OLYMPUS BLVD, DALLAS, TX
Asset: Single Duct VAV's
Asset | Area Served | Address | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max)
VAV-1-1 | OO HALL |  |  |  | 360 |  | 72
VAV-1-2 | 01C02 |  |  |  | 220 |  | 44
VAV-1-3 | OO HALL |  |  |  | 910 |  | 182
VAV-1-4 | 01D03 |  |  |  | 360 |  | 72
VAV-1-5 | 01D01 |  |  |  | 300 |  | 60
VAV-1-6 | 01F02 |  |  |  | 140 |  | 28
VAV-1-7 | 01G03 |  |  |  | 240 |  | 48
VAV-1-8 | 01F00 |  |  |  | 160 |  | 32
VAV-1-9 | HALL |  |  |  | 420 |  | 84
VAV-1-10 | 01G02 |  |  |  | 150 |  | 30
NOTES: | NO VAV TYPE (INLET SIZE) ON DRAWING. DESIGN MAX IS DIFFUSER TOTAL, DESIGN MIN IS 20% OF MAX.
Note on C7: NTAB: BILLINGSLEY ONLY

## VAV SGRD's (1)
National TAB
Project: CW 2999 - Langan
Address: 2999 OLYMPUS BLVD, DALLAS, TX
Asset: SGRD's
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V11-1 | OO HALL | B | 10X4 | 120 |  |  | 0
V11-2 | OO HALL | B | 10X4 | 120 |  |  | 0
V11-3 | OO HALL | B | 10X4 | 120 |  |  | 0
VAV-1-1 |  |  |  | 360 |  | 0 | 0
V12-1 | 01B01 | A | 6 | 60 |  |  | 0
V12-2 | 01C02 | A | 6 | 100 |  |  | 0
V12-3 | 01B02 | A | 6 | 60 |  |  | 0
VAV-1-2 |  |  |  | 220 |  | 0 | 0
V13-1 | OPEN OFFICE | A | 6 | 130 |  |  | 0
V13-2 | OPEN OFFICE | A | 6 | 130 |  |  | 0
V13-3 | OPEN OFFICE | A | 6 | 130 |  |  | 0
V13-4 | OPEN OFFICE | A | 6 | 130 |  |  | 0
V13-5 | OPEN OFFICE | A | 6 | 130 |  |  | 0
V13-6 | OPEN OFFICE | A | 6 | 130 |  |  | 0
V13-7 | OPEN OFFICE | A | 6 | 130 |  |  | 0
VAV-1-3 |  |  |  | 910 |  | 0 | 0
V14-1 | 01C03 | A | 6 | 100 |  |  | 0
V14-2 | 01D03 | A | 6 | 100 |  |  | 0
V14-3 | 01E01 | A | 6 | 60 |  |  | 0
V14-4 | 01E03 | A | 6 | 100 |  |  | 0
VAV-1-4 |  |  |  | 360 |  | 0 | 0
V15-1 | 01D01 | F | 22X10 | 300 |  |  | 0
VAV-1-5 |  |  |  | 300 |  | 0 | 0
V16-1 | 01F02 | A | 6 | 140 |  |  | 0
VAV-1-6 |  |  |  | 140 |  | 0 | 0
V17-1 | 01F03 | A | 6 | 120 |  |  | 0
V17-2 | 01G03 | A | 6 | 120 |  |  | 0
VAV-1-7 |  |  |  | 240 |  | 0 | 0
V18-1 | 01F00 | A | 6 | 80 |  |  | 0
V18-2 | 01F01 | A | 6 | 80 |  |  | 0
VAV-1-18 |  |  |  | 160 |  | 0 | 0

## VAV SGRD's (2)
National TAB
Project: CW 2999 - Langan
Address: 2999 OLYMPUS BLVD, DALLAS, TX
Asset: SGRD's
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V19-1 |  | B | 6 | 70 |  |  | 0
V19-2 |  | B | 6 | 70 |  |  | 0
V19-3 | HALL | B | 6 | 70 |  |  | 0
V19-4 | HALL | B | 6 | 70 |  |  | 0
V19-5 | HALL | B | 6 | 70 |  |  | 0
V19-6 | HALL | B | 6 | 70 |  |  | 0
VAV-1-19 |  |  |  | 420 |  | 0 | 0
V110-1 | 01G02 | A | 8 | 150 |  |  | 0
VAV-1-10 |  |  |  | 150 |  | 0 | 0

## TF-1-1
National TAB
Project: CW 2999 - Langan
Address: 2999 OLYMPUS BLVD, DALLAS, TX
Asset: TF-1-1 |  |  | Area: IDF 01D01
Unit Data |  |  |  |  | Test Data
MFG | [5 empty] | Design | Actual
Model Num |  |  |  |  | CFM | 600
Serial Num |  |  |  |  | Fan RPM | 1357
Type |  |  |  |  | RL Voltage | 120
RL Amperage
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP | 0.4
Frame
Horsepower |  | 236W
Motor Rpm
Phase |  | 1
Voltage (rated) |  | 120
Amperage (rated)
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
TF11-1 | 01D01 | E | (2) 24X12 | 600 |  |  | 0
|  |  |  | 600 |  | 0 | 0
-