## DOAS-01
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: DOAS-01 |  | Area: OA FOR BOTH FLOORS
Unit Data |  |  | Test Data
Manufacurer | YORK |  |  | Design | Actual
Model Number | XTI-36x42 |  | SF CFM | 2600
Serial Number |  |  | SF RPM | 3553
Configuration | VERTICAL
No. Pre Filters / Size | 4 / 20X16X4 |  | OA CFM | 2600
|  |  | RL VOLTAGE | 460
|  |  | RL AMPERAGE | 5.90
|  |  | Motor B.H.P. | 2.52
Motor Data |  |  | Performance Data
Motor MFG | BALDOR |  |  | Design | Actual
Frame | 182 |  | Suction S.P.
HP | 5.0 |  | Discharge S.P.
RPM | 3600 |  | Total SP | 3.41
Phase | 3 |  | CW Coil P.D.
Volts | 460 |  | HW Coil P.D.
Amps | 5.90 |  | Final Filters P.D.
Heat Wheel P.D.
Pre Filters P.D.
|  |  | Total ESP | 1.00

## DOAS-01 OAT's
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: DOAS-01 OAT's (OUTSIDE AIR TERMINALS)
Asset | Area Served | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max)
OAT-01 | FCU-01 | COOL | 5 | 120 |  | 50
OAT-02 | FCU-02 | COOL | 5 | 150 |  | 50
OAT-03 | FCU-03 | COOL | 5 | 125 |  | 50
OAT-04 | FCU-04 | COOL | 5 | 150 |  | 50
OAT-05 | FCU-05 | COOL | 5 | 150 |  | 50
OAT-06 | FCU-06 | COOL | 6 | 220 |  | 50
OAT-07 | FCU-07 | COOL | 5 | 150 |  | 50
OAT-08 | FCU-08 | COOL | 5 | 135 |  | 50
OAT-09 | FCU-09 | COOL | 14 | 1400 |  | 400
|  |  |  | 2600 | 0
Note on C7: NTAB: BILLINGSLEY ONLY

## AH-01
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 |  | Area: A&B ON BOTH FLOORS
Unit Data |  |  | Test Data
Manufacurer | YORK |  |  | Design | Actual
Model Number | XTI-78x126 |  | SF CFM | 24000
Serial Number |  |  | SF RPM | 1852
Configuration | VERTICAL |  | RA CFM | 15975
No. Pre Filters / Size | 36 / 16X20X4 |  | OA CFM | 8025
|  |  | RL VOLTAGE | 460
|  |  | RL AMPERAGE | 48.0
|  |  | Motor B.H.P. | 15.78
Motor Data |  |  | Performance Data
Motor MFG | BALDOR |  |  | Design | Actual
Frame | 256 |  | Suction S.P.
HP | 20.0 |  | Discharge S.P.
RPM | 1800 |  | Total SP | 5.49
Phase | 3 |  | CW Coil P.D.
Volts | 460 |  | HW Coil P.D.
Amps | 48.0 |  | Final Filters P.D.
Heat Wheel P.D.
Pre Filters P.D.
|  |  | Total ESP | 3.50

## AH-01 VAV's (1)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 VAV's
Asset | NOTE | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL
1-01-T |  | REHEAT | 8 | 515 |  | 200 |  | 200 |  |  | 515
1-02-T |  | REHEAT | 8 | 395 |  | 145 |  | 145 |  |  | 395
1-03-T |  | REHEAT | 6 | 155 |  | 80 |  | 80 |  |  | 155
1-04-T |  | REHEAT | 8 | 440 |  | 145 |  | 145 |  |  | 440
1-05-T |  | REHEAT | 8 | 525 |  | 155 |  | 155 |  |  | 525
1-06-T |  | REHEAT | 6 | 350 |  | 105 |  | 105 |  |  | 350
1-07-T |  | REHEAT | 12 | 1300 |  | 390 |  | 390 |  |  | 1200
1-08-T |  | REHEAT | 8 | 400 |  | 200 |  | 200 |  |  | 400
1-09-T |  | REHEAT | 6 | 160 |  | 80 |  | 80 |  |  | 160
1-10-T |  | REHEAT | 6 | 200 |  | 80 |  | 80 |  |  | 200
1-11-T |  | REHEAT | 12 | 1100 |  | 330 |  | 330 |  |  | 1100
1-12-T |  | REHEAT | 8 | 600 |  | 200 |  | 200 |  |  | 600
1-13-T |  | REHEAT | 5 | 105 |  | 65 |  | 65 |  |  | 105
1-14-T |  | REHEAT | 6 | 160 |  | 80 |  | 80 |  |  | 160
1-15-T |  | REHEAT | 6 | 240 |  | 80 |  | 80 |  |  | 240
1-16-T |  | REHEAT | 12 | 1500 |  | 450 |  | 450 |  |  | 1500
1-17-T |  | REHEAT | 5 | 90 |  | 65 |  | 65 |  |  | 90
1-18-T | [1] | REHEAT | 12 | 1325 |  | 395 |  | 395 |  |  | 1550
1-19-T |  | REHEAT | 14 | 2475 |  | 740 |  | 740 |  |  | 2475
1-20-T |  | REHEAT | 6 | 250 |  | 100 |  | 100 |  |  | 250
1-21-T |  | REHEAT | 8 | 400 |  | 155 |  | 155 |  |  | 400
1-22-T |  | REHEAT | 10 | 1225 |  | 365 |  | 365 |  |  | 1225
1-23-T |  | REHEAT | 6 | 290 |  | 85 |  | 85 |  |  | 290
1-24-T |  | REHEAT | 6 | 240 |  | 80 |  | 80 |  |  | 240
1-25-T |  | REHEAT | 6 | 260 |  | 80 |  | 80 |  |  | 260
1-26-T |  | REHEAT | 8 | 510 |  | 150 |  | 150 |  |  | 510
1-27-T |  | REHEAT | 10 | 1050 |  | 315 |  | 315 |  |  | 1050
1-28-T |  | REHEAT | 12 | 1500 |  | 500 |  | 500 |  |  | 1500
1-29-T |  | REHEAT | 12 | 1500 |  | 500 |  | 500 |  |  | 1500
1-30-T |  | REHEAT | 10 | 900 |  | 270 |  | 270 |  |  | 900
1-31-T |  | REHEAT | 8 | 400 |  | 145 |  | 145 |  |  | 400
1-32-T |  | REHEAT | 8 | 555 |  | 165 |  | 165 |  |  | 555
1-33-T | [2] | REHEAT | 8 | 555 |  | 165 |  | 165 |  |  | 615
1-34-T |  | REHEAT | 6 | 200 |  | 80 |  | 80 |  |  | 200
|  |  |  | 21870 | 0 | [5 empty] | 22055
[1] VAV DESIGN IS 1325 CFM, DIFFUSER TOTAL IS 1550 CFM
[2] VAV DESIGN IS 555 CFM, DIFFUSER TOTAL IS 615 CFM

## AH-01 VAV's (2)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 VAV's
Asset | NOTE | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL
1-35-T |  | REHEAT | 10 | 800 |  | 240 |  | 240 |  |  | 800
1-36-T |  | REHEAT | 8 | 520 |  | 155 |  | 155 |  |  | 520
1-37-T |  | REHEAT | 8 | 330 |  | 145 |  | 145 |  |  | 330
1-38-T |  | REHEAT | 10 | 1050 |  | 315 |  | 315 |  |  | 1050
1-39-T |  | REHEAT | 6 | 255 |  | 80 |  | 80 |  |  | 255
1-40-T |  | REHEAT | 6 | 175 |  | 80 |  | 80 |  |  | 175
1-41-T |  | REHEAT | 8 | 525 |  | 225 |  | 225 |  |  | 525
1-42-T |  | REHEAT | 10 | 800 |  | 240 |  | 240 |  |  | 800
1-43-T |  | REHEAT | 6 | 175 |  | 80 |  | 80 |  |  | 175
1-61-T | [1] | REHEAT | 8 | 400 |  | 175 |  | 175 |  |  | 200
|  |  |  | 5030 | 0 | [5 empty] | 4830
PAGE 1 TOTAL |  |  |  | 21870 | 0
AH-01 TOTAL |  |  |  | 26900 | 0
[1] VAV DESIGN IS 400 CFM, DIFFUSER TOTAL IS 200 CFM

## AH-01 SGRD (1)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V11-1 | S120C | EX | 8 | 140 |  |  | 0
V11-2 | S120D | EX | 8 | 115 |  |  | 0
V11-3 | S120D | EX | 8 | 115 |  |  | 0
V11-4 | S120E | EX | 8 | 145 |  |  | 0
1-1-T |  |  |  | 515 |  | 0 | 0
V12-1 | S120G | EX | 8 | 135 |  |  | 0
V12-2 | S120H | EX | 8 | 130 |  |  | 0
V12-3 | S120I | EX | 8 | 130 |  |  | 0
1-2-T |  |  |  | 395 |  | 0 | 0
V13-1 | S120B | EX | 6 | 80 |  |  | 0
V13-2 | S120A | EX | 6 | 75 |  |  | 0
1-3-T |  |  |  | 155 |  | 0 | 0
V14-1 | S113 | EX | 8 | 220 |  |  | 0
V14-2 | S113 | EX | 8 | 220 |  |  | 0
1-4-T |  |  |  | 440 |  | 0 | 0
V15-1 | S109 | EX | 6 | 100 |  |  | 0
V15-2 | S111 | EX | 6 | 100 |  |  | 0
V15-3 | S107 | EX | 6 | 125 |  |  | 0
V15-4 | S107A | EX | 6 | 75 |  |  | 0
V15-5 | S107 | EX | 6 | 125 |  |  | 0
1-5-T |  |  |  | 525 |  | 0 | 0
V16-1 | S114 | EX | 8 | 175 |  |  | 0
V16-2 | S114 | EX | 8 | 175 |  |  | 0
1-6-T |  |  |  | 350 |  | 0 | 0

## AH-01 SGRD (2)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V17-1 | S116 | EX | 10 | 225 |  |  | 0
V17-2 | S116 | EX | 10 | 225 |  |  | 0
V17-3 | S116A | EX | 10 | 150 |  |  | 0
V17-4 | S116 | EX | 10 | 225 |  |  | 0
V17-5 | S116 | EX | 10 | 225 |  |  | 0
V17-6 | S116A | EX | 10 | 150 |  |  | 0
1-7-T |  |  |  | 1200 |  | 0 | 0
V18-1 | 160 | EX | 6 | 75 |  |  | 0
V18-2 | S118 | EX | 6 | 100 |  |  | 0
V18-3 | 158 | EX | 8 | 100 |  |  | 0
V18-4 | 158 | EX | 8 | 75 |  |  | 0
V18-5 | S122 | EX | 6X6 | 50 |  |  | 0
1-8-T |  |  |  | 400 |  | 0 | 0
V19-1 | S106D | EX | 6 | 80 |  |  | 0
V19-2 | S106C | EX | 6 | 80 |  |  | 0
1-9-T |  |  |  | 160 |  | 0 | 0
V110-1 | S106B | EX | 10 | 200 |  |  | 0
1-10-T |  |  |  | 200 |  | 0 | 0
V111-1 | S106 | EX | 10 | 275 |  |  | 0
V111-2 | S106 | EX | 10 | 275 |  |  | 0
V111-3 | S106 | EX | 10 | 275 |  |  | 0
V111-4 | S106 | EX | 10 | 275 |  |  | 0
1-11-T |  |  |  | 1100 |  | 0 | 0

## AH-01 SGRD (3)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V112-1 | S106A | EX | 10 | 200 |  |  | 0
V112-2 | S102 | EX | 10 | 200 |  |  | 0
V112-3 | S102 | EX | 10 | 200 |  |  | 0
1-12-T |  |  |  | 600 |  | 0 | 0
V113-1 | 201D | EX | 6 | 105 |  |  | 0
1-13-T |  |  |  | 105 |  | 0 | 0
V114-1 | 201E | EX | 8 | 160 |  |  | 0
1-14-T |  |  |  | 160 |  | 0 | 0
V115-1 | 201A | EX | 6 | 80 |  |  | 0
V115-2 | 201B | EX | 6 | 80 |  |  | 0
V115-3 | 201C | EX | 6 | 80 |  |  | 0
1-15-T |  |  |  | 240 |  | 0 | 0
V116-1 | 201 | EX | 10 | 250 |  |  | 0
V116-2 | 201 | EX | 10 | 250 |  |  | 0
V116-3 | 201 | EX | 10 | 250 |  |  | 0
V116-4 | 201 | EX | 10 | 250 |  |  | 0
V116-5 | 201 | EX | 10 | 250 |  |  | 0
V116-6 | 201 | EX | 10 | 250 |  |  | 0
1-16-T |  |  |  | 1500 |  | 0 | 0
V117-1 | 202A | EX | 6 | 90 |  |  | 0
1-17-T |  |  |  | 90 |  | 0 | 0

## AH-01 SGRD (4)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V118-1 | 202 | EX | 8 | 150 |  |  | 0
V118-2 | 202 | EX | 8 | 150 |  |  | 0
V118-3 | 202 | EX | 8 | 150 |  |  | 0
V118-4 | 202 | EX | 8 | 150 |  |  | 0
V118-5 | 202 | EX | 8 | 150 |  |  | 0
V118-6 | 202 | EX | 8 | 150 |  |  | 0
V118-7 | CORR | EX | 6 | 50 |  |  | 0
V118-8 | 202 | EX | 8 | 150 |  |  | 0
V118-9 | CORR | EX | 6 | 75 |  |  | 0
V118-10 | 202 | EX | 8 | 150 |  |  | 0
V118-11 | 202 | EX | 8 | 150 |  |  | 0
V118-12 | CORR | EX | 6 | 75 |  |  | 0
1-18-T |  |  |  | 1550 |  | 0 | 0
V118-1 | 202 | EX | 8 | 225 |  |  | 0
V118-2 | 202 | EX | 8 | 225 |  |  | 0
V118-3 | 202 | EX | 8 | 225 |  |  | 0
V118-4 | 202 | EX | 8 | 225 |  |  | 0
V118-5 | 202 | EX | 8 | 225 |  |  | 0
V118-6 | 202 | EX | 8 | 225 |  |  | 0
V118-7 | 202 | EX | 8 | 225 |  |  | 0
V118-8 | 202 | EX | 8 | 225 |  |  | 0
V118-9 | 202 | EX | 8 | 225 |  |  | 0
V118-10 | 202 | EX | 8 | 225 |  |  | 0
V118-11 | 202 | EX | 8 | 225 |  |  | 0
1-19-T |  |  |  | 2475 |  | 0 | 0
V120-1 | 204E | EX | 10 | 250 |  |  | 0
1-20-T |  |  |  | 250 |  | 0 | 0

## AH-01 SGRD (5)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V121-1 | 204D | EX | 10 | 200 |  |  | 0
V121-2 | 204C | EX | 10 | 200 |  |  | 0
1-21-T |  |  |  | 400 |  | 0 | 0
V122-1 | 203 | EX | 8 | 175 |  |  | 0
V122-2 | 203 | EX | 8 | 175 |  |  | 0
V122-3 | 203 | EX | 8 | 175 |  |  | 0
V122-4 | 203 | EX | 8 | 175 |  |  | 0
V122-5 | 203 | EX | 8 | 175 |  |  | 0
V122-6 | 203 | EX | 8 | 175 |  |  | 0
V122-7 | 203 | EX | 8 | 175 |  |  | 0
1-22-T |  |  |  | 1225 |  | 0 | 0
V123-1 | 203F |  |  | 80 |  |  | 0
V123-2 | 207 |  |  | 80 |  |  | 0
V123-3 | 203G |  |  | 80 |  |  | 0
V123-4 | CORR | EX | 6 | 50 |  |  | 0
1-23-T |  |  |  | 290 |  |  | 0
V124-1 | 203C | EX | 6 | 80 |  |  | 0
V124-2 | 203D | EX | 6 | 80 |  |  | 0
V124-3 | 203E | EX | 6 | 80 |  |  | 0
1-24-T |  |  |  | 240 |  | 0 | 0
V125-1 | 203B | EX | 6 | 90 |  |  | 0
V125-2 | 203A | EX | 6 | 80 |  |  | 0
V125-3 | 205C | EX | 6 | 90 |  |  | 0
1-25-T |  |  |  | 260 |  | 0 | 0

## AH-01 SGRD (6)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V126-1 | 204A | EX | 6 | 80 |  |  | 0
V126-2 | 204B | EX | 6 | 80 |  |  | 0
V126-3 | 238 | EX | 8 | 75 |  |  | 0
V126-4 | 206A | EX | 6 | 25 |  |  | 0
V126-5 | 206 | EX | 10 | 200 |  |  | 0
V126-6 | 208 | EX | 6 | 50 |  |  | 0
1-26-T |  |  |  | 510 |  | 0 | 0
V127-1 | 212 | EX | 10 | 150 |  |  | 0
V127-2 | 212 | EX | 10 | 150 |  |  | 0
V127-3 | 238 | EX | 6 | 75 |  |  | 0
V127-4 | 238 | EX | 6 | 75 |  |  | 0
V127-5 | 212 | EX | 10 | 150 |  |  | 0
V127-6 | 212 | EX | 10 | 150 |  |  | 0
V127-7 | 212 | EX | 10 | 150 |  |  | 0
V127-8 | 212 | EX | 10 | 150 |  |  | 0
1-27-T |  |  |  | 1050 |  | 0 | 0
V128-1 | 212 | EX | 10 | 300 |  |  | 0
V128-2 | 212 | EX | 10 | 300 |  |  | 0
V128-3 | 212 | EX | 10 | 300 |  |  | 0
V128-4 | 212 | EX | 10 | 300 |  |  | 0
V128-5 | 212 | EX | 10 | 300 |  |  | 0
1-28-T |  |  |  | 1500 |  | 0 | 0
V129-1 | 212 | EX | 10 | 300 |  |  | 0
V129-2 | 212 | EX | 10 | 300 |  |  | 0
V129-3 | 212 | EX | 10 | 300 |  |  | 0
V129-4 | 212 | EX | 10 | 300 |  |  | 0
V129-5 | 212 | EX | 10 | 300 |  |  | 0
1-29-T |  |  |  | 1500 |  | 0 | 0

## AH-01 SGRD (7)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V130-1 | 212 | EX | 10 | 150 |  |  | 0
V130-2 | 212 | EX | 10 | 150 |  |  | 0
V130-3 | 212 | EX | 10 | 150 |  |  | 0
V130-4 | 212 | EX | 10 | 150 |  |  | 0
V130-5 | 212 | EX | 10 | 150 |  |  | 0
V130-6 | CORR | EX | 10 | 150 |  |  | 0
1-30-T |  |  |  | 900 |  | 0 | 0
V131-1 | 216 | EX | 6 | 80 |  |  | 0
V131-2 | 212C | EX | 6 | 80 |  |  | 0
V131-3 | 212B | EX | 6 | 80 |  |  | 0
V131-4 | 214 | EX | 6 | 80 |  |  | 0
V131-5 | 212A | EX | 6 | 80 |  |  | 0
1-31-T |  |  |  | 400 |  | 0 | 0
V132-1 | 222 | EX | 6 | 80 |  |  | 0
V132-2 | 238 | EX | 6 | 75 |  |  | 0
V132-3 | 220 | EX | 6 | 80 |  |  | 0
V132-4 | 212E | EX | 6 | 80 |  |  | 0
V132-5 | 212D | EX | 6 | 80 |  |  | 0
V132-6 | 218 | EX | 6 | 80 |  |  | 0
V132-7 | 212F | EX | 6 | 80 |  |  | 0
1-32-T |  |  |  | 555 |  | 0 | 0
V133-1 | 224 | EX | 6 | 90 |  |  | 0
V133-2 | 238 | EX | 6 | 75 |  |  | 0
V133-3 | 226 | EX | 6 | 90 |  |  | 0
V133-4 | 212H | EX | 6 | 90 |  |  | 0
V133-5 | 228 | EX | 6 | 90 |  |  | 0
V133-6 | 212J | EX | 6 | 90 |  |  | 0
V133-7 | 212G | EX | 6 | 90 |  |  | 0
1-33-T |  |  |  | 615 |  | 0 | 0

## AH-01 SGRD (8)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V134-1 | 230E | EX | 10 | 200 |  |  | 0
1-34-T |  |  |  | 200 |  | 0 | 0
V135-1 | 230A | EX | 10 | 200 |  |  | 0
V135-2 | 230B | EX | 10 | 200 |  |  | 0
V135-3 | 230C | EX | 10 | 200 |  |  | 0
V135-4 | 230D | EX | 10 | 200 |  |  | 0
1-35-T |  |  |  | 800 |  | 0 | 0
V136-1 | 215 | EX | 10 | 260 |  |  | 0
V136-2 | 215 | EX | 10 | 260 |  |  | 0
1-36-T |  |  |  | 520 |  | 0 | 0
V137-1 | 217 | EX | 8 | 150 |  |  | 0
V137-2 | 213F | EX | 6 | 90 |  |  | 0
V137-3 | 213G | EX | 6 | 90 |  |  | 0
1-37-T |  |  |  | 330 |  | 0 | 0
V138-1 | 213 | EX | 8 | 175 |  |  | 0
V138-2 | 213 | EX | 8 | 175 |  |  | 0
V138-3 | 213 | EX | 8 | 175 |  |  | 0
V138-4 | 213 | EX | 8 | 175 |  |  | 0
V138-5 | 213 | EX | 8 | 175 |  |  | 0
V138-6 | 213 | EX | 8 | 175 |  |  | 0
1-38-T |  |  |  | 1050 |  | 0 | 0
V139-1 | 213H | EX | 6 | 85 |  |  | 0
V139-2 | 213J | EX | 6 | 85 |  |  | 0
V139-3 | 213K | EX | 6 | 85 |  |  | 0
1-39-T |  |  |  | 255 |  | 0 | 0

## AH-01 SGRD (9)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V140-1 | 213L | EX | 8 | 175 |  |  | 0
1-40-T |  |  |  | 175 |  | 0 | 0
V141-1 | 213 | EX | 8 | 175 |  |  | 0
V141-2 | 213 | EX | 8 | 175 |  |  | 0
V141-3 | 213 | EX | 8 | 175 |  |  | 0
1-41-T |  |  |  | 525 |  | 0 | 0
V142-1 | 213A | EX | 10 | 200 |  |  | 0
V142-2 | 213B | EX | 10 | 200 |  |  | 0
V142-3 | 213C | EX | 10 | 200 |  |  | 0
V142-4 | 213D | EX | 10 | 200 |  |  | 0
1-42-T |  |  |  | 800 |  | 0 | 0
V143-1 | 213E | EX | 10 | 175 |  |  | 0
1-43-T |  |  |  | 175 |  | 0 | 0
V161-1 | 102 | EX | 8 | 75 |  |  | 0
V161-2 | 102 | EX | 8 | 75 |  |  | 0
V161-3 | 102 | EX | 6 | 50 |  |  | 0
1-61-T |  |  |  | 200 |  | 0 | 0

## AH-03
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-03 |  | Area: C ON FIRST FLOOR
Unit Data |  |  | Test Data
Manufacurer | YORK |  |  | Design | Actual
Model Number | XTI-45x72 |  | SF CFM | 7300
Serial Number |  |  | SF RPM | 1832
Configuration | VERTICAL |  | RA CFM | 5012
No. Pre Filters / Size | 4 / 24X24X4 |  | OA CFM | 2288
No. Pre Filters / Size | 2 / 24X12X4 |  | RL VOLTAGE | 460
|  |  | RL AMPERAGE | 12.5
|  |  | Motor B.H.P. | 7.77
Motor Data |  |  | Performance Data
Motor MFG | BALDOR |  |  | Design | Actual
Frame | 215 |  | Suction S.P.
HP | 10.0 |  | Discharge S.P.
RPM | 1800 |  | Total SP | 4.69
Phase | 3 |  | CW Coil P.D.
Volts | 460 |  | HW Coil P.D.
Amps | 12.5 |  | Final Filters P.D.
Heat Wheel P.D.
Pre Filters P.D.
|  |  | Total ESP | 2.50

## AH-03 VAV's
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-03 VAV's
Asset | NOTE | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL
3-65-T |  | REHEAT | 5 | 250 |  | 75 |  | 75 |  |  | 250
3-66-T |  | REHEAT | 8 | 450 |  | 145 |  | 145 |  |  | 450
3-67-T |  | REHEAT | 10 | 800 |  | 240 |  | 240 |  |  | 800
3-68-T |  | REHEAT | 8 | 510 |  | 150 |  | 150 |  |  | 510
3-69-T |  | REHEAT | 5 | 100 |  | 65 |  | 65 |  |  | 100
3-70-T |  | REHEAT | 8 | 630 |  | 185 |  | 185 |  |  | 630
3-71-T |  | REHEAT | 6 | 250 |  | 75 |  | 75 |  |  | 250
3-72-T |  | REHEAT | 5 | 110 |  | 65 |  | 65 |  |  | 110
3-73-T |  | REHEAT | 14 | 1625 |  | 485 |  | 485 |  |  | 1625
3-74-T |  | REHEAT | 8 | 330 |  | 120 |  | 120 |  |  | 330
3-75-T |  | REHEAT | 8 | 300 |  | 145 |  | 145 |  |  | 300
3-76-T |  | REHEAT | 6 | 160 |  | 80 |  | 80 |  |  | 160
3-77A-T |  | REHEAT | 10 | 820 |  | 290 |  | 290 |  |  | 820
3-77B-T |  | REHEAT | 8 | 575 |  | 150 |  | 150 |  |  | 575
|  |  |  | 6910 | 0 | [5 empty] | 6910

## AH-03 SGRD (1)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-03 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V365-1 | N105 | EX | 8 | 150 |  |  | 0
V365-2 | N105 | EX | 6 | 100 |  |  | 0
3-65-T |  |  |  | 250 |  | 0 | 0
V366-1 | N101 | EX | 8 | 225 |  |  | 0
V366-2 | N101 | EX | 8 | 225 |  |  | 0
3-66-T |  |  |  | 450 |  | 0 | 0
V367-1 | N107 | EX | 8 | 170 |  |  | 0
V367-2 | N107 | EX | 8 | 170 |  |  | 0
V367-3 | N107B | EX | 8 | 120 |  |  | 0
V367-4 | N107 | EX | 8 | 170 |  |  | 0
V367-5 | N107 | EX | 8 | 170 |  |  | 0
3-67-T |  |  |  | 800 |  | 0 | 0
V368-1 | N107A | EX | 8 | 255 |  |  | 0
V368-2 | N107A | EX | 8 | 255 |  |  | 0
3-68-T |  |  |  | 510 |  | 0 | 0
V369-1 | N100A | EX | 6 | 100 |  |  | 0
3-69-T |  |  |  | 100 |  | 0 | 0
V370-1 | N102 | EX | 8 | 315 |  |  | 0
V370-2 | N102 | EX | 8 | 315 |  |  | 0
3-70-T |  |  |  | 630 |  | 0 | 0
V371-1 | N104 | EX | 6 | 50 |  |  | 0
V371-2 | 170 | EX | 6 | 100 |  |  | 0
V371-3 | 170 | EX | 6 | 100 |  |  | 0
3-71-T |  |  |  | 250 |  | 0 | 0

## AH-03 SGRD (2)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-03 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V372-1 | N110A | EX | 6 | 110 |  |  | 0
3-72-T |  |  |  | 110 |  | 0 | 0
V373-1 | N109 | EX | 10 | 325 |  |  | 0
V373-2 | N109 | EX | 12 | 325 |  |  | 0
V373-3 | N109 | EX | 12 | 325 |  |  | 0
V373-4 | N109 | EX | 12 | 325 |  |  | 0
V373-5 | N109 | EX | 12 | 325 |  |  | 0
3-73-T |  |  |  | 1625 |  | 0 | 0
V374-1 | N109C | EX | 6 | 110 |  |  | 0
V374-2 | N109B | EX | 6 | 110 |  |  | 0
V374-3 | N109A | EX | 6 | 110 |  |  | 0
3-74-T |  |  |  | 330 |  | 0 | 0
V375-1 | N109E | EX | 8 | 150 |  |  | 0
V375-2 | N109E | EX | 8 | 150 |  |  | 0
3-75-T |  |  |  | 300 |  | 0 | 0
V376-1 | N109D | EX | 6 | 160 |  |  | 0
3-76-T |  |  |  | 160 |  | 0 | 0
V377A-1 | 180 | EX | 6 | 100 |  |  | 0
V377A-2 | 180 | EX | 6 | 100 |  |  | 0
V377A-3 | N111 | EX | 8 | 150 |  |  | 0
V377A-4 | N111 | EX | 8 | 150 |  |  | 0
V377A-5 | N111 | EX | 8 | 160 |  |  | 0
V377A-6 | N111 | EX | 8 | 160 |  |  | 0
3-77A-T |  |  |  | 820 |  | 0 | 0

## AH-03 SGRD (3)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-03 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V377B-1 | 180 | EX | 6 | 75 |  |  | 0
V377B-2 | N111 | EX | 8 | 125 |  |  | 0
V377B-3 | N111 | EX | 8 | 125 |  |  | 0
V377B-4 | N111 | EX | 8 | 125 |  |  | 0
V377B-5 | N111 | EX | 8 | 125 |  |  | 0
3-77B-T |  |  |  | 575 |  | 0 | 0

## AH-02
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AH-02 |  | Area: 210A RCAS
Unit Data |  |  |  |  | Test Data
MFG | LG |  |  |  |  | Design | Actual
Model Num | LVN361HV4 |  |  |  | SA CFM | 875
Serial Num |  |  |  |  | Fan Speed
OA CFM
[5 empty] | RA CFM | 875
Motor Data |  |  |  |  | RL Voltage | 208
Motor MFG |  |  |  |  | RL Amperage
Horsepower |  |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP
Voltage (rated) | 208 |  |  |  | Brake HP
Amperage (rated)
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
AH2-1 | 210A | A | 10 | 300 |  |  | 0
AH2-2 | 210 | A | 10 | 275 |  |  | 0
AH2-3 | 210A | A | 10 | 300 |  |  | 0
|  |  |  | 875 |  | 0 | 0
RETURN
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
RAH2-1 | 210A | B | 22X22 | 600 |  |  | 0
RAH2-2 | 210 | B | 22X10 | 275 |  |  | 0
|  |  |  | 875 |  | 0 | 0
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## AH-04
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: AHU-04 |  | Area: N106 TELE/RCAS
Unit Data |  |  |  |  | Test Data
MFG | LG |  |  |  |  | Design | Actual
Model Num | LVN361HV4 |  |  |  | SA CFM | 875
Serial Num |  |  |  |  | Fan Speed
OA CFM
[5 empty] | RA CFM | 875
Motor Data |  |  |  |  | RL Voltage | 208
Motor MFG |  |  |  |  | RL Amperage
Horsepower |  |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP
Voltage (rated) | 208 |  |  |  | Brake HP
Amperage (rated)
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
AH4-1 | N108 | A | 8 | 175 |  |  | 0
AH4-2 | N106 | A | 10 | 350 |  |  | 0
AH4-3 | N106 | A | 10 | 350 |  |  | 0
|  |  |  | 875 |  | 0 | 0
RETURN
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
RAH4-1 | N106 | B | 12X10 | 700 |  |  | 0
RAH4-2 | N108 | B | 22X10 | 175 |  |  | 0
|  |  |  | 875 |  | 0 | 0
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-01
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-01 |  | Area: S112 CLASSROOM
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 1000
Serial Num |  |  |  |  | Fan Speed | 1206
[5 empty] | OA CFM | 120
[5 empty] | RA CFM | 880
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 7.7
Horsepower | 0.5 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 7.7
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F01-1 | S112 | EX | 12 | 500 |  |  | 0
F01-1 | S112 | EX | 12 | 500 |  |  | 0
|  |  |  | 1000 |  | 0 | 0
OAT-01 | 120 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-02
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-02 |  | Area: S110B CLASSROOM
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 800
Serial Num |  |  |  |  | Fan Speed | 1095
[5 empty] | OA CFM | 150
[5 empty] | RA CFM | 650
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 7.7
Horsepower | 0.5 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 7.7
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F02-1 | S110A | EX | 10 | 350 |  |  | 0
F02-2 | 118 | EX | 6 | 100 |  |  | 0
F02-3 | S110A | EX | 10 | 350 |  |  | 0
|  |  |  | 800 |  | 0 | 0
OAT-02 | 150 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-03
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-03 |  | Area: S110A CLASSROOM
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 700
Serial Num |  |  |  |  | Fan Speed | 1278
[5 empty] | OA CFM | 125
[5 empty] | RA CFM | 575
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 5
Horsepower | 0.33 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 5
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F03-1 | S110A | EX | 10 | 350 |  |  | 0
F03-2 | S110A | EX | 10 | 350 |  |  | 0
|  |  |  | 700 |  | 0 | 0
OAT-03 | 125 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-04
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-04 |  | Area: S108A CLASSROOM
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 800
Serial Num |  |  |  |  | Fan Speed | 1095
[5 empty] | OA CFM | 150
[5 empty] | RA CFM | 650
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 7.7
Horsepower | 0.5 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 7.7
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F04-1 | S108A | EX | 10 | 350 |  |  | 0
F04-2 | 118 | EX | 6 | 100 |  |  | 0
F04-3 | S108A | EX | 10 | 350 |  |  | 0
|  |  |  | 800 |  | 0 | 0
OAT-04 | 150 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-05
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-05 |  | Area: S108B CLASSROOM
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 800
Serial Num |  |  |  |  | Fan Speed | 1095
[5 empty] | OA CFM | 150
[5 empty] | RA CFM | 650
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 7.7
Horsepower | 0.5 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 7.7
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F05-1 | S108B | EX | 10 | 350 |  |  | 0
F05-2 | 118 | EX | 6 | 100 |  |  | 0
F05-3 | S108B | EX | 10 | 350 |  |  | 0
|  |  |  | 800 |  | 0 | 0
OAT-05 | 150 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-06
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-06 |  | Area: S115A CLASSROOM
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 960
Serial Num |  |  |  |  | Fan Speed | 1187
[5 empty] | OA CFM | 220
[5 empty] | RA CFM | 740
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 7.7
Horsepower | 0.5 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 7.7
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F06-1 | S115A | EX | 8 | 215 |  |  | 0
F06-2 | S115A | EX | 8 | 215 |  |  | 0
F06-3 | S115A | EX | 8 | 215 |  |  | 0
F06-4 | S115A | EX | 8 | 215 |  |  | 0
F06-5 | S106 | EX | 6 | 100 |  |  | 0
|  |  |  | 960 |  | 0 | 0
OAT-06 | 220 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-07
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-07 |  | Area: S115B CLASSROOM
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 660
Serial Num |  |  |  |  | Fan Speed | 1236
[5 empty] | OA CFM | 150
[5 empty] | RA CFM | 510
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 5
Horsepower | 0.33 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 5
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F07-1 | S115B | EX | 8 | 165 |  |  | 0
F07-2 | S115B | EX | 8 | 165 |  |  | 0
F07-3 | S115B | EX | 8 | 165 |  |  | 0
F07-4 | S115B | EX | 8 | 165 |  |  | 0
|  |  |  | 660 |  | 0 | 0
OAT-07 | 150 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-08
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-08 |  | Area: S117 CLASSROOM
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 580
Serial Num |  |  |  |  | Fan Speed
[5 empty] | OA CFM | 135
[5 empty] | RA CFM | 445
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 5
Horsepower | 0.33 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 5
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F08-1 | S117 | EX | 10 | 290 |  |  | 0
F08-2 | S117 | EX | 10 | 290 |  |  | 0
|  |  |  | 580 |  | 0 | 0
OAT-08 | 135 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-09
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-09 |  | Area: 100 ASSEMBLY
Unit Data |  |  |  |  | Test Data
MFG | YORK |  |  |  |  | Design | Actual
Model Num | XTI-42x57 |  |  |  | SA CFM | 4800
Serial Num |  |  |  |  | Fan Speed | 1885
[5 empty] | OA CFM | 1400
[5 empty] | RA CFM | 4800
Motor Data |  |  |  |  | RL Voltage | 460
Motor MFG | TECO |  |  |  | RL Amperage | 6.2
Horsepower | 5 |  |  |  | Suction ESP
Motor Rpm | 1800 |  |  |  | Discharge ESP
Phase | 3 |  |  |  | Total ESP | 0.75
Voltage (rated) | 460 |  |  |  | Brake HP | 2.92
Amperage (rated) | 6.2
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F09-1 | 100 | EX | 10 | 320 |  |  | 0
F09-2 | 100 | EX | 10 | 320 |  |  | 0
F09-3 | 100 | EX | 10 | 320 |  |  | 0
F09-4 | 100 | EX | 10 | 320 |  |  | 0
F09-5 | 100 | EX | 10 | 320 |  |  | 0
F09-6 | 100 | EX | 10 | 320 |  |  | 0
F09-7 | 100 | EX | 10 | 320 |  |  | 0
F09-8 | 100 | EX | 10 | 320 |  |  | 0
F09-9 | 100 | EX | 10 | 320 |  |  | 0
F09-10 | 100 | EX | 10 | 320 |  |  | 0
F09-11 | 100 | EX | 10 | 320 |  |  | 0
F09-12 | 100 | EX | 10 | 320 |  |  | 0
F09-13 | 100 | EX | 10 | 320 |  |  | 0
F09-14 | 100 | EX | 10 | 320 |  |  | 0
F09-15 | 100 | EX | 10 | 320 |  |  | 0
|  |  |  | 4800 |  | 0 | 0
RETURN
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
RF09-1 | 100 | B | 46X22 | 1600 |  |  | 0
RF09-2 | 100 | B | 46X22 | 1600 |  |  | 0
RF09-3 | 100 | B | 46X22 | 1600 |  |  | 0
|  |  |  | 4800 |  | 0 | 0
OAT-09 | 1400 CFM
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## FCU-10
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: FCU-10 |  | Area: 115 KITCHEN
Unit Data |  |  |  |  | Test Data
MFG | JOHNSON CONTROLS |  |  |  |  | Design | Actual
Model Num | FNP |  |  |  | SA CFM | 1200
Serial Num |  |  |  |  | Fan Speed | 1303
OA CFM
RA CFM
Motor Data |  |  |  |  | RL Voltage | 115
Motor MFG |  |  |  |  | RL Amperage | 7.7
Horsepower | 0.5 |  |  |  | Suction ESP
Motor Rpm |  |  |  |  | Discharge ESP
Phase | 1 |  |  |  | Total ESP | 0.5
Voltage (rated) | 115 |  |  |  | Brake HP
Amperage (rated) | 7.7
SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F10-1 | 116 | E | 8 | 120 |  |  | 0
F10-2 | 116 | E | 8 | 120 |  |  | 0
F10-3 | 115 | E | 8 | 225 |  |  | 0
F10-4 | 115 | E | 8 | 225 |  |  | 0
F10-5 | 115 | E | 8 | 225 |  |  | 0
F10-6 | 113 | A | 6 | 85 |  |  | 0
F10-7 | 114 | E | 8 | 200 |  |  | 0
|  |  |  | 1200 |  | 0 | 0
Note on A5: USE FOR: FAN COIL UNIT SPLIT SYSTEM FURNACE HEAT PUMP

## ERV-01
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: ERV-01 |  | Area: MEN'S LOCKER
Supply Side |  |  | Exhaust Side
Unit Data |  |  | Unit Data
Manufacturer | GREENHECK |  | Manufacturer | GREENHECK
Model Number | ECV-30-P-L |  | Model Number | ECV-30-P-L
Serial Number |  |  | Serial Number
Configuration |  |  | Configuration
No. Pre Filters / Size | 3 / 30X30X2 |  | No. Pre Filters / Size | 3 / 30X30X2
Motor Data |  |  | Motor Data
Motor MFG / Frame |  |  | Motor MFG / Frame
Horsepower / RPM | 1.0 / 1750 |  | Horsepower / RPM | 0.75 / 1750
Rated Volts / Phase | 208/ 3 |  | Rated Volts / Phase | 208/ 3
Rated Amperage / SF |  |  | Rated Amperage / SF
Test Data |  |  | Test Data
| Design | Actual |  | Design | Actual
Total CFM | 1800 |  | Total CFM | 2000
Fan RPM | 1789 |  | Fan RPM | 1656
VFD Speed |  |  | VFD Speed
RL Voltage | 208 |  | RL Voltage | 208
RL Amperage |  |  | RL Amperage
Motor B.H.P. |  |  | Motor B.H.P.
Performance Data |  |  | Performance Data
| Design | Actual |  | Design | Actual
System Set Point
Suction S.P. |  |  | Suction S.P.
Discharge S.P. |  |  | Discharge S.P.
Total SP | 1.984 |  | Total SP | 1.567
CW Coil P.D.
HW Coil P.D. |  |  | HW Coil P.D.
Final Filters P.D.
Heat Wheel P.D. |  |  | Heat Wheel P.D.
Pre Filters P.D. |  |  | Pre Filters P.D.
Total ESP | 1.0 |  | Total ESP | 0.5

## ERV-01 GRD
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: ERV-01 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
ERV1-1 | 182C | A | 12 | 450 |  |  | 0
ERV1-2 | 182C | A | 12 | 450 |  |  | 0
ERV1-3 | 182C | A | 12 | 450 |  |  | 0
ERV1-4 | 182C | A | 12 | 450 |  |  | 0
|  |  |  | 1800 |  | 0 | 0
Asset: ERV-01 EXHAUST
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
EERV1-1 | 182C | D | 14X14 | 450 |  |  | 0
EERV1-2 | 182C | D | 14X14 | 450 |  |  | 0
EERV1-3 | 182B | D | 8X8 | 200 |  |  | 0
EERV1-4 | 182A | D | 8X8 | 200 |  |  | 0
EERV1-5 | 182 | D | 10X10 | 250 |  |  | 0
EERV1-6 | 182 | D | 14X14 | 450 |  |  | 0
|  |  |  | 2000 |  | 0 | 0

## ERV-02
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: ERV-02 |  | Area: WOMEN'S LOCKER
Supply Side |  |  | Exhaust Side
Unit Data |  |  | Unit Data
Manufacturer | GREENHECK |  | Manufacturer | GREENHECK
Model Number | ECV-20-P-L |  | Model Number | ECV-20-P-L
Serial Number |  |  | Serial Number
Configuration |  |  | Configuration
No. Pre Filters / Size | 2 / 20X20X2 |  | No. Pre Filters / Size | 2 / 20X20X2
Motor Data |  |  | Motor Data
Motor MFG / Frame |  |  | Motor MFG / Frame
Horsepower / RPM | 0.75 / 1750 |  | Horsepower / RPM | 0.75 / 1750
Rated Volts / Phase | 208 / 3 |  | Rated Volts / Phase | 208 / 3
Rated Amperage / SF |  |  | Rated Amperage / SF
Test Data |  |  | Test Data
| Design | Actual |  | Design | Actual
Total CFM | 1100 |  | Total CFM | 1345
Fan RPM | 1654 |  | Fan RPM | 1732
VFD Speed |  |  | VFD Speed
RL Voltage | 208 |  | RL Voltage | 208
RL Amperage |  |  | RL Amperage
Motor B.H.P. |  |  | Motor B.H.P.
Performance Data |  |  | Performance Data
| Design | Actual |  | Design | Actual
System Set Point
Suction S.P. |  |  | Suction S.P.
Discharge S.P. |  |  | Discharge S.P.
Total SP | 1.714 |  | Total SP | 1.354
CW Coil P.D.
HW Coil P.D. |  |  | HW Coil P.D.
Final Filters P.D.
Heat Wheel P.D. |  |  | Heat Wheel P.D.
Pre Filters P.D. |  |  | Pre Filters P.D.
Total ESP | 1.0 |  | Total ESP | 0.5

## ERV-02 GRD
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: ERV-02SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
ERV2-1 | 177B | A | 10 | 275 |  |  | 0
ERV2-2 | 177B | A | 10 | 275 |  |  | 0
ERV2-3 | 177B | A | 10 | 275 |  |  | 0
ERV2-4 | 177B | A | 10 | 275 |  |  | 0
|  |  |  | 1100 |  | 0 | 0
Asset: ERV-02 EXHAUST
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
EERV2-1 | 177B | B | 14X14 | 450 |  |  | 0
EERV2-2 | 177A | B | 10X12 | 325 |  |  | 0
EERV2-3 | 177 | B | 14X14 | 450 |  |  | 0
EERV2-4 | N104 | EX | 22X22 | 120 |  |  | 0
|  |  |  | 1345 |  | 0 | 0

## EF-01-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-01-T |  |  | Area: N110 SUPPLY
Unit Data |  |  |  |  | Test Data
MFG |  | GREENHECK |  |  |  | Design | Actual
Model Num |  | SQ-99-VG |  |  | CFM | 800
Serial Num |  |  |  |  | Fan RPM | 1835
Type |  | INLINE |  |  | RL Voltage | 115
[5 empty] | RL Amperage | 10.5
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP | 0.5
Frame
Horsepower |  | 0.75
Motor Rpm |  | 2200
Phase |  | 1
Voltage (rated) |  | 115
Amperage (rated) |  | 10.5
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
EF1-1 | N110 | D | 18X18 | 800 |  |  | 0
-

## EF-02-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-02-T |  | Area: N110B VAULT
Unit Data |  |  | Test Data
MFG | GREENHECK |  |  | Design | Actual
Model Num | SQ-80-VG |  | CFM | 296
Serial Num |  |  | Fan RPM | 1725
Type | INLINE |  | RL Voltage | 115
|  |  | RL Amperage | 1.38
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP | 0.488
Frame
Horsepower | 0.1
Motor Rpm | 1725
Phase | 1
Voltage (rated) | 115
Amperage (rated) | 1.38
Service Factor
-

## EF-03-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-03-T |  | Area: S120K VAULT
Unit Data |  |  | Test Data
MFG | GREENHECK |  |  | Design | Actual
Model Num | SQ-80-VG |  | CFM | 296
Serial Num |  |  | Fan RPM | 1725
Type | INLINE |  | RL Voltage | 115
|  |  | RL Amperage | 1.38
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP | 0.488
Frame
Horsepower | 0.1
Motor Rpm | 1725
Phase | 1
Voltage (rated) | 115
Amperage (rated) | 1.38
Service Factor
-

## EF-04-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-04-T |  |  | Area: RESERVE GENERAL EXHAUST
Unit Data |  |  |  |  | Test Data
MFG |  | GREENHECK |  |  |  | Design | Actual
Model Num |  | SQ-130-VG |  |  | CFM | 1625
Serial Num |  |  |  |  | Fan RPM | 1526
Type |  | INLINE |  |  | RL Voltage | 115
[5 empty] | RL Amperage | 8.8
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP | 0.75
Frame
Horsepower |  | 0.75
Motor Rpm |  | 1725
Phase |  | 1
Voltage (rated) |  | 115
Amperage (rated) |  | 8.8
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
EF4-1 | 277 | D | 8X10 | 125 |  |  | 0
EF4-2 | 277 | D | 8X10 | 125 |  |  | 0
EF4-3 | 276 | D | 8X10 | 225 |  |  | 0
EF4-4 | 276 | D | 8X10 | 225 |  |  | 0
EF4-5 | 208 | EX | 8X8 | 175 |  |  | 0
EF4-6 | 163 | D | 6X10 | 175 |  |  | 0
EF4-7 | 163 | D | 6X10 | 175 |  |  | 0
EF4-8 | 164 | D | 6X10 | 100 |  |  | 0
EF4-9 | 164 | D | 6X10 | 100 |  |  | 0
EF4-10 | S118 | EX | 12X12 | 200 |  |  | 0
|  |  |  | 1625 |  | 0 | 0
-

## EF-05-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-05-T |  | Area: KH-01 HOOD
Unit Data |  |  | Drive Data
MFG | GREENHECK |  | Motor Sheave Size |  |  | KEF-01 HOOD SUBMITTAL PAGE 6
Model Num | CUBE-180-10 |  | Motor Bore Size |  |  | EF SUBMITTAL PAGE 30
Serial Num |  |  | Fan Sheave Size
Type | CRE UPBLAST |  | Fan Bore Size
Belt CL Distance
Motor Data |  |  | No of Belts
Motor MFG |  |  | Belt Size
Frame | 184
Horsepower | 1 |  | Test Data
Motor Rpm | 1725 |  |  | Design | Actual
Phase | 3 |  | CFM | 3053
Voltage (rated) | 460 |  | Fan RPM | 1109
Amperage (rated) | 2.1 |  | RL Voltage | 460
Service Factor |  |  | RL Amperage | 2.1
Suction ESP
|  |  | Total ESP | 0.9
Brake Horse Power
-

## EF-06-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-06-T |  | Area: S104 ELEVATOR EQUIP
Unit Data |  |  | Test Data
MFG | GREENHECK |  |  | Design | Actual
Model Num | SQ-80-VG |  | CFM | 296
Serial Num |  |  | Fan RPM | 1725
Type | INLINE |  | RL Voltage | 115
|  |  | RL Amperage | 1.38
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP | 0.488
Frame
Horsepower | 0.1
Motor Rpm | 1725
Phase | 1
Voltage (rated) | 115
Amperage (rated) | 1.38
Service Factor
-

## EF-07-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-06-T |  | Area: EXISTING DISHWASH HOOD
Unit Data |  |  | Test Data
MFG | GREENHECK |  |  | Design | Actual
Model Num | CUE-95-VG |  | CFM | 450
Serial Num |  |  | Fan RPM | 1184
Type | CRE UPBLAST |  | RL Voltage | 115
|  |  | RL Amperage | 2.3
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP | 0.3
Frame
Horsepower | 0.167
Motor Rpm | 1725
Phase | 1
Voltage (rated) | 115
Amperage (rated) | 2.3
Service Factor
-

## EF-08-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-08-T |  | Area: 194 MECHANICAL
Unit Data |  |  | Drive Data
MFG | GREENHECK |  | Motor Sheave Size
Model Num | SBE-1H24-5 |  | Motor Bore Size
Serial Num |  |  | Fan Sheave Size
Type | WALL PROPELLER |  | Fan Bore Size
Belt CL Distance
Motor Data |  |  | No of Belts
Motor MFG |  |  | Belt Size
Frame
Horsepower | 0.5 |  | Test Data
Motor Rpm | 1725 |  |  | Design | Actual
Phase | 3 |  | CFM | 1600
Voltage (rated) | 460 |  | Fan RPM | 841
Amperage (rated) | 1.1 |  | RL Voltage | 460
Service Factor |  |  | RL Amperage | 1.1
Suction ESP
|  |  | Total ESP | 0.361
Brake Horse Power
-

## EF-09-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-09-T |  | Area: S124 MECHANICAL
Unit Data |  |  | Drive Data
MFG | GREENHECK |  | Motor Sheave Size
Model Num | BSQ-160 |  | Motor Bore Size
Serial Num |  |  | Fan Sheave Size
Type | INLINE |  | Fan Bore Size
Belt CL Distance
Motor Data |  |  | No of Belts
Motor MFG |  |  | Belt Size
Frame
Horsepower | 1 |  | Test Data
Motor Rpm | 1725 |  |  | Design | Actual
Phase | 3 |  | CFM | 3200
Voltage (rated) | 460 |  | Fan RPM | 1334
Amperage (rated) | 2.1 |  | RL Voltage | 460
Service Factor |  |  | RL Amperage | 2.1
Suction ESP
|  |  | Total ESP | 0.75
Brake Horse Power
-

## EF-10-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-10-T |  |  | Area: S120 UNIT STORAGE
Unit Data |  |  |  |  | Drive Data
MFG |  | GREENHECK |  |  | Motor Sheave Size
Model Num |  | SBE-2H24-7 |  |  | Motor Bore Size
Serial Num |  |  |  |  | Fan Sheave Size
Type |  | WALL PROPELLER |  |  | Fan Bore Size
Belt CL Distance
Motor Data |  |  |  |  | No of Belts
Motor MFG |  |  |  |  | Belt Size
Frame
Horsepower |  | 0.75 |  |  | Test Data
Motor Rpm |  | 1725 |  |  |  | Design | Actual
Phase |  | 3 |  |  | CFM | 2200
Voltage (rated) |  | 460 |  |  | Fan RPM | 1093
Amperage (rated) |  | 1.6 |  |  | RL Voltage | 460
Service Factor |  |  |  |  | RL Amperage | 1.6
Suction ESP
[5 empty] | Total ESP | 0.591
Brake Horse Power
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
-

## EF-11-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-11-T |  | Area: S120J ELECTRIC
Unit Data |  |  | Test Data
MFG | GREENHECK |  |  | Design | Actual
Model Num | SE1-14-440-VG |  | CFM | 500
Serial Num |  |  | Fan RPM | 839
Type | WALL PROPELLER |  | RL Voltage | 115
|  |  | RL Amperage | 6.4
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP | 0.2
Frame
Horsepower | 0.5
Motor Rpm | 1725
Phase | 1
Voltage (rated) | 115
Amperage (rated) | 6.4
Service Factor
-

## EF-12-T
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: EF-12-T |  | Area: N105 MAIL ROOMS
Unit Data |  |  | Test Data
MFG | GREENHECK |  |  | Design | Actual
Model Num | SQ-98-VG |  | CFM | 325
Serial Num |  |  | Fan RPM | 1340
Type | INLINE |  | RL Voltage | 115
|  |  | RL Amperage | 3.5
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP | 0.5
Frame
Horsepower | 0.25
Motor Rpm | 1725
Phase | 1
Voltage (rated) | 115
Amperage (rated) | 3.5
Service Factor
-

## RF-01
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: RF-01 |  | Area: AH-01 RELIEF
Unit Data |  |  | Drive Data
MFG | GREENHECK |  | Motor Sheave Size
Model Num | BSQ-180 |  | Motor Bore Size
Serial Num |  |  | Fan Sheave Size
Type | INLINE |  | Fan Bore Size
Belt CL Distance
Motor Data |  |  | No of Belts
Motor MFG |  |  | Belt Size
Frame
Horsepower | 2 |  | Test Data
Motor Rpm | 1725 |  |  | Design | Actual
Phase | 3 |  | CFM | 4750
Voltage (rated) | 460 |  | Fan RPM | 1399
Amperage (rated) | 3.4 |  | RL Voltage | 460
Service Factor |  |  | RL Amperage | 3.4
Suction ESP
|  |  | Total ESP | 1
Brake Horse Power
-

## RF-03
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: RF-03 |  | Area: AH-03 RELIEF
.
Unit Data |  |  | Drive Data
MFG | GREENHECK |  | Motor Sheave Size
Model Num | BSQ-100 |  | Motor Bore Size
Serial Num |  |  | Fan Sheave Size
Type | INLINE |  | Fan Bore Size
Belt CL Distance
Motor Data |  |  | No of Belts
Motor MFG |  |  | Belt Size
Frame
Horsepower | 0.5 |  | Test Data
Motor Rpm | 1725 |  |  | Design | Actual
Phase | 3 |  | CFM | 1000
Voltage (rated) | 460 |  | Fan RPM | 1822
Amperage (rated) | 1.1 |  | RL Voltage | 460
Service Factor |  |  | RL Amperage | 1.1
Suction ESP
|  |  | Total ESP | 1
Brake Horse Power
-

## MAU-01
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: MAU-01 |  | Area: MAKEUP AIR FOR KITCHEN
Unit Data |  |  | Test Data
MFG | ECON-AIR |  |  | Design | Actual | MAU-01 HOOD SUBMITTAL PAGE 6
Model Num | A1-D.250-16Z |  | CFM | 2231
Serial Num | 5996145 |  | SF RPM | 2391
Type | GAS FIRED |  | RL Voltage | 460
Configuration |  |  | RL Amperage | 3.3
No. Filters / Size |  |  | Suction ESP
No. Filters / Size |  |  | Discharge ESP
|  |  | Total ESP | 0.5
Motor Data |  |  | Brake Horse Power | 1.679
Motor MFG
Frame
Horsepower | 3.4
Motor Rpm
Phase | 3
Voltage (rated) | 460
Amperage (rated) | 3.3
Service Factor

## KH-01 Hood
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: KH-01 |  | Area: 115 KITCHEN
Unit Data |  |  | Test Data Supply
MFG | ECON-AIR |  |  | PRELIM | FINAL
Model Num | 4824 EX-2-PSP-F |  | AK factor |  |  | HOOD SUBMITTAL PAGE 3
Job / Serial Num |  |  | Total AK Area | 15.94
Type | TYPE I CANOPY |  | Kv factor (Vel) | 0.9
Hood length | 163 |  | Reading1 FPM
Hood Width | 48 |  | Reading2 FPM
Supply Plenum Type | PSP |  | Reading3 FPM
Supply Plenum Width | 14 |  | Reading4 FPM
Supply Plenum Length | 164 |  | Reading5 FPM
Reading6 FPM
Test Data Exhaust |  |  | Reading7 FPM
| PRELIM | FINAL | Reading8 FPM
Filter Type | CAPTRATE SOLO |  | Reading9 FPM
Filter Size 1 | 20X16 |  | Reading10 FPM
Filter Qty 1 | 10 |  | Reading11 FPM
Filter AK factor size 1 | 2.08 |  | Reading12 FPM
Filter Total AK Area | 20.8 |  | Reading13 FPM
Filter1 FPM |  |  | Reading14 FPM
Filter2 FPM |  |  | Ave FPM(corr)
Filter3 FPM |  |  | CFM | 2231
Filter4 FPM
Filter5 FPM |  |  | Performance Data
Filter6 FPM |  |  |  | Design | Actual
Filter7 FPM |  |  | Exh-Supply Net CFM | 784
Filter8 FPM |  |  | Smoke Generation Type
Filter9 FPM |  |  | Cooking Equip Heat On
Filter Ave FPM |  |  | Hood Capture %
CFM | 3015 |  | Ambient Room Temp
100% override functional
Cooking Equipment |  |  | General
Item 1 |  |  | Third Party Witness
Item 2 |  |  | Third Party Company
Item 3 |  |  | Tech Witness
Item 4 |  |  | Tech Company
Item 5 |  |  | Code Official Witness

## CH-01 Chiller
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: CH-01 (AIR COOLED)
UNIT DATA
Unit Description
Manufacturer | JCI-YORK
Model Number | YLAA0200HE46XFBBCTX
Serial Number
EVAPORATOR DATA | Design | Actual
Flow GPM | 380.7
Pressure Drop | 12.8

## Boilers
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: BOILERS |  | Service: HOT WATER
Unit Data | B-01 |  | B-02
Manufacturer | LAARS HEATING SYSTEMS |  | LAARS HEATING SYSTEMS |  | SUBMITTAL PAGE 23
Model Number | 1500 |  | 1500
Serial Number
Test Data | Design | Actual | Design | Actual
Water Flow GPM | 92.0 |  | 92.0
Water Press. Drop | < 9.0 |  | < 9.0

## CP-01
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: CP-01 |  | Service: CHILLED WATER
Unit Data |  |  | Test Data
| Actual |  |  | Design | Actual | SUBMITTAL PAGE 10 (OPTION 1)
MFG | ARMSTRONG |  | Pump Off Pressure (psi)
Model Num | 4030-4X3X10-4P-15HP |  | Pump Dead Head (ft)
Serial Num |  |  | Act. Impellar Dia (in) | 10.19
Service |  |  | Valve Open GPM
Pump RPM | 1633 |  | Valve Open Diff (ft)
GPM/Head | 348 / 80 |  | Discharge Pressure (ft)
Impellar Diameter | 10.19 |  | Suction Pressure (ft)
|  |  | Total Head Pressure (ft) | 80
Motor Data |  |  | Final GPM | 348
| Actual |  | Motor Frequency (HZ)
Motor MFG |  |  | System Set Point
Frame | 254TC |  | RL Voltage | 460
Horsepower | 15 |  | RL Amperage
Motor RPM |  |  | BHP | 9.39
Phase | 3
Voltage | 460
Amperage
Service Factor
Efficiency
Power Factor

## CP-02
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: CP-02 |  | Service: CHILLED WATER
Unit Data |  |  | Test Data
| Actual |  |  | Design | Actual
MFG | ARMSTRONG |  | Pump Off Pressure (psi) |  |  | SUBMITTAL PAGE 10 (OPTION 1)
Model Num | 4030-4X3X10-4P-15HP |  | Pump Dead Head (ft)
Serial Num |  |  | Act. Impellar Dia (in) | 10.19
Service |  |  | Valve Open GPM
Pump RPM | 1633 |  | Valve Open Diff (ft)
GPM/Head | 348 / 80 |  | Discharge Pressure (ft)
Impellar Diameter | 10.19 |  | Suction Pressure (ft)
|  |  | Total Head Pressure (ft) | 80
Motor Data |  |  | Final GPM | 348
| Actual |  | Motor Frequency (HZ)
Motor MFG |  |  | System Set Point
Frame | 254TC |  | RL Voltage | 460
Horsepower | 15 |  | RL Amperage
Motor RPM |  |  | BHP | 9.39
Phase | 3
Voltage | 460
Amperage
Service Factor
Efficiency
Power Factor

## CP-03
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: CP-03 |  | Service: HEATING WATER
Unit Data |  |  | Test Data
| Actual |  |  | Design | Actual
MFG | ARMSTRONG |  | Pump Off Pressure (psi) |  |  | SUBMITTAL 2 PAGE 44 (OPTION)
Model Num | 4030-3X1.5X6-2P-7.5HP |  | Pump Dead Head (ft)
Serial Num |  |  | Act. Impellar Dia (in) | 5.42
Service |  |  | Valve Open GPM
Pump RPM | 3116 |  | Valve Open Diff (ft)
GPM/Head | 120 / 85 |  | Discharge Pressure (ft)
Impellar Diameter | 5.42 |  | Suction Pressure (ft)
|  |  | Total Head Pressure (ft) | 85
Motor Data |  |  | Final GPM | 120
| Actual |  | Motor Frequency (HZ)
Motor MFG |  |  | System Set Point
Frame | 184TC |  | RL Voltage
Horsepower | 7.5 |  | RL Amperage
Motor RPM |  |  | BHP | 3.9
Phase | 3
Voltage | 460
Amperage
Service Factor
Efficiency
Power Factor

## CP-04
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: CP-04 |  | Service: HEATING WATER
Unit Data |  |  | Test Data
| Actual |  |  | Design | Actual
MFG | ARMSTRONG |  | Pump Off Pressure (psi) |  |  | SUBMITTAL 2 PAGE 44 (OPTION)
Model Num | 4030-3X1.5X6-2P-7.5HP |  | Pump Dead Head (ft)
Serial Num |  |  | Act. Impellar Dia (in) | 5.42
Service |  |  | Valve Open GPM
Pump RPM | 3116 |  | Valve Open Diff (ft)
GPM/Head | 120 / 85 |  | Discharge Pressure (ft)
Impellar Diameter | 5.42 |  | Suction Pressure (ft)
|  |  | Total Head Pressure (ft) | 85
Motor Data |  |  | Final GPM | 120
| Actual |  | Motor Frequency (HZ)
Motor MFG |  |  | System Set Point
Frame | 184TC |  | RL Voltage
Horsepower | 7.5 |  | RL Amperage
Motor RPM |  |  | BHP | 3.9
Phase | 3
Voltage | 460
Amperage
Service Factor
Efficiency
Power Factor

## CP-05
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: CP-05 |  | Service: B-01 BOILER
Unit Data |  |  | Test Data
| Actual |  |  | Design | Actual
MFG | ARMSTRONG |  | Pump Off Pressure (psi) |  |  | SUBMITTAL 2 PAGE 50 (OPTION)
Model Num | 4380-2X2X8-6P-1.5HP |  | Pump Dead Head (ft)
Serial Num |  |  | Act. Impellar Dia (in) | 7.92
Service |  |  | Valve Open GPM
Pump RPM | 1170 |  | Valve Open Diff (ft)
GPM/Head | 92 / 25 |  | Discharge Pressure (ft)
Impellar Diameter | 7.92 |  | Suction Pressure (ft)
|  |  | Total Head Pressure (ft) | 25
Motor Data |  |  | Final GPM | 92
| Actual |  | Motor Frequency (HZ)
Motor MFG |  |  | System Set Point
Frame | 182JM |  | RL Voltage
Horsepower | 1.5 |  | RL Amperage
Motor RPM |  |  | BHP | 0.89
Phase | 3
Voltage | 460
Amperage
Service Factor
Efficiency
Power Factor

## CP-06
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: CP-06 |  | Service: B-02 BOILER
Unit Data |  |  | Test Data
| Actual |  |  | Design | Actual
MFG | ARMSTRONG |  | Pump Off Pressure (psi) |  |  | SUBMITTAL 2 PAGE 50 (OPTION)
Model Num | 4380-2X2X8-6P-1.5HP |  | Pump Dead Head (ft)
Serial Num |  |  | Act. Impellar Dia (in) | 7.92
Service |  |  | Valve Open GPM
Pump RPM | 1170 |  | Valve Open Diff (ft)
GPM/Head | 92 / 25 |  | Discharge Pressure (ft)
Impellar Diameter | 7.92 |  | Suction Pressure (ft)
|  |  | Total Head Pressure (ft) | 25
Motor Data |  |  | Final GPM | 92
| Actual |  | Motor Frequency (HZ)
Motor MFG |  |  | System Set Point
Frame | 182JM |  | RL Voltage
Horsepower | 1.5 |  | RL Amperage
Motor RPM |  |  | BHP | 0.89
Phase | 3
Voltage | 460
Amperage
Service Factor
Efficiency
Power Factor

## CHW Bal Valve (1)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: CHW CIRCUIT SETTERS |  |  |  | Service: CHILLED WATER
Asset | Location | MFG | Type | Size | Range (PSID) | Design GPM | Actual DP (PSID) | Final GPM | % to Design
CC-AH01 | 209 | PRO HYDRONIC | Auto-flow | 4 | 2-60 | 208 |  |  | 0
CC-AH03 | 194 | PRO HYDRONIC | Auto-flow | 2.5 | 2-60 | 62.1 |  |  | 0
CC-DOAS01 | S124 | PRO HYDRONIC | Auto-flow | 2 | 2-60 | 30.3 |  |  | 0
HC-ERV01 | 182C | PRO HYDRONIC | Auto-flow | 1.25 | 2-60 | 10.7 |  |  | 0
HC-ERV02 | 177B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 4.2 |  |  | 0
FCU-01 | S112 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 3.07 |  |  | 0
FCU-02 | S110B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2.39 |  |  | 0
FCU-03 | S110A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2.08 |  |  | 0
FCU-04 | S108A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2.39 |  |  | 0
FCU-05 | S108B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2.39 |  |  | 0
FCU-06 | S115A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2.92 |  |  | 0
FCU-07 | S115B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2.02 |  |  | 0
FCU-08 | S117 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.74 |  |  | 0
FCU-09 | 209 | PRO HYDRONIC | Auto-flow | 2 | 2-60 | 30.34 |  |  | 0
FCU-10 | 117 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 4.32 |  |  | 0
[6 empty] | 368.96 |  | 0 | 0

## HW Bal Valve (1)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: HW CIRCUIT SETTERS |  |  |  | Service: HOT WATER
Asset | Location | MFG | Type | Size | Range (PSID) | Design GPM | Actual DP (PSID) | Final GPM | % to Design
HC-AH01 | 209 | PRO HYDRONIC | Auto-flow | 1.5 | 2-60 | 22.36 |  |  | 0
HC-AH03 | 194 | PRO HYDRONIC | Auto-flow | 1 | 2-60 | 5.93 |  |  | 0
HC-DOAS01A | S124 | PRO HYDRONIC | Auto-flow | 1 | 2-60 | 5 |  |  | 0
HC-DOAS01B | S124 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2.83 |  |  | 0
HC-ERV01 | 182C | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 3.8 |  |  | 0
HC-ERV02 | 177B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2.3 |  |  | 0
CUH-03 | 180 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.25 |  |  | 0
CUH-04 | 101 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.25 |  |  | 0
CUH-05 | 117 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.25 |  |  | 0
CUH-06 | 119 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.25 |  |  | 0
CUH-07 | 150 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.25 |  |  | 0
UH-03 | 194 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-04 | N110 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-05 | N110 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-06 | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-07 | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-08 | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-09 | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-10 | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-11 | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-12 | 209 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
UH-13 | S124 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
1-1-T | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
1-2-T | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.5 |  |  | 0
1-3-T | S120B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.25 |  |  | 0
1-4-T | S113 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
1-5-T | S109 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-6-T | S107 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-7-T | S111 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
1-8-T | 160 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
1-9-T | S106D | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.25 |  |  | 0
1-10-T | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.5 |  |  | 0
[6 empty] | 70.63 |  | 0 | 0

## HW Bal Valve (2)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: HW CIRCUIT SETTERS |  |  |  | Service: HOT WATER
Asset | Location | MFG | Type | Size | Range (PSID) | Design GPM | Actual DP (PSID) | Final GPM | % to Design
1-11-T | S120 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
1-12-T | S106 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
1-13-T | 201D | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-14-T | 201E | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-15-T | 201A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-16-T | 201 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2 |  |  | 0
1-17-T | 202A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-18-T | 202 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
1-19-T | 202 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 3 |  |  | 0
1-20-T | 202 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.5 |  |  | 0
1-21-T | 204C | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.5 |  |  | 0
1-22-T | 203E | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
1-23-T | 203F | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.5 |  |  | 0
1-24-T | 203C | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-25-T | 203B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-26-T | 204A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
1-27-T | 212 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
1-28-T | 212 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2 |  |  | 0
1-29-T | 212 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2 |  |  | 0
1-30-T | 212 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
1-31-T | 212C | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-32-T | 222 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
1-33-T | 224 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
1-34-T | 212 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-35-T | 230B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.25 |  |  | 0
1-36-T | 215 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.25 |  |  | 0
1-37-T | 213F | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-38-T | 213 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
1-39-T | 213 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-40-T | 213 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-41-T | 213 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
1-42-T | 213 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
[6 empty] | 27.88 |  | 0 | 0

## HW Bal Valve (3)
National TAB
Project: NC026 HVAC-Elec-Plumb Reset
Address: USACE Winterville, NC
Asset: HW CIRCUIT SETTERS |  |  |  | Service: HOT WATER
Asset | Location | MFG | Type | Size | Range (PSID) | Design GPM | Actual DP (PSID) | Final GPM | % to Design
1-43-T | 213 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
1-61-T | S106 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1 |  |  | 0
3-65-T | N105 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
3-66-T | N101 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.5 |  |  | 0
3-67-T | N107 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
3-68-T | N107B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
3-69-T | 100A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
3-70-T | N102 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.5 |  |  | 0
3-71-T | 170 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
3-72-T | N110A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.25 |  |  | 0
3-73-T | 180 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 1.5 |  |  | 0
3-74-T | N109 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
3-75-T | N109 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
3-76-T | N109 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.33 |  |  | 0
3-77A-T | 180 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 2 |  |  | 0
3-77B-T | 180 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
FCU-01 | S112 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.97 |  |  | 0
FCU-02 | S110B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
FCU-03 | S110A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.65 |  |  | 0
FCU-04 | S108A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
FCU-05 | S108B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.75 |  |  | 0
FCU-06 | S115A | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.93 |  |  | 0
FCU-07 | S115B | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.84 |  |  | 0
FCU-08 | S117 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.73 |  |  | 0
FCU-09 | 209 | PRO HYDRONIC | Auto-flow | 1 | 2-60 | 5.79 |  |  | 0
FCU-10 | 117 | PRO HYDRONIC | Auto-flow | 0.75 | 2-60 | 0.88 |  |  | 0
[6 empty] | 23.77 |  | 0 | 0
|  | HW (1) |  |  |  | 70.63 |  | 0
|  | HW (2) |  |  |  | 27.88 |  | 0
|  | HW TOTAL |  |  |  | 122.28 |  | 0 | 0