## RTU-3
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-3 (EXISTING) |  | Building A
Unit Data |  | Test Data
Manufacturer | McQuay |  | Design | Actual
Model Num | OAH021FDAC | SF CFM | 10500 |  | 10825 | VAV TOTAL
Serial Num |  | SF RPM
Configuration |  | RA CFM | 9075
Num OA Filters |  | OA CFM | 1425
OA Filter Size |  | RL VOLTAGE
Num Final Filter |  | RL AMPERAGE
Final Filter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-3 VAV's
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-3 VAV's
Asset | Area Served | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL | UNIT SIZE | NOTES
VAV-1.1 | 1105 | REHEAT | 16 | 2900 |  | 725 |  | 1160 |  |  | 2900 | 16 | SUBMITTAL IS 1160 CFM
VAV-1.2 | 1116 | REHEAT | 10 | 750 |  | 190 |  | 300 |  |  | 750 | 10 | SUBMITTAL IS 300 CFM
VAV-1.3 | 1113 | REHEAT | 8 | 500 |  | 125 |  | 200 |  |  | 500 | 8 | SUBMITTAL IS 200 CFM
VAV-1.4 | 1107 | REHEAT | 6 | 300 |  | 75 |  | 120 |  |  | 300 | 6 | SUBMITTAL IS 120 CFM
CAV-1.28 | 1101 | REHEAT | 12 | 1300 |  | 1300 |  | 1300 |  |  | 1300 | 12
CAV-1.29 | 1101 | REHEAT | 10 | 1000 |  | 1000 |  | 1000 |  |  | 1000 | 10
VAV-1.30 | 1102 | REHEAT | 6 | 350 |  | 90 |  | 140 |  |  | 350 | 6 | SUBMITTAL IS 140 CFM
VAV-1.31 | 1103 | REHEAT | 8 | 500 |  | 125 |  | 200 |  |  | 500 | 8 | SUBMITTAL IS 200 CFM
VAV-1.32 | 1104 | REHEAT | 14 | 2000 |  | 500 |  | 800 |  |  | 2000 | 14 | SUBMITTAL IS 800 CFM
VAV-1.33 | 1111 | REHEAT | 8 | 400 |  | 100 |  | 160 |  |  | 400 | 8 | SUBMITTAL IS 160 CFM
VAV-1.34 | 1110 | REHEAT | 6 | 250 |  | 65 |  | 100 |  |  | 250 | 6 | SUBMITTAL IS 100 CFM
VAV-1.35 | 1108 | REHEAT | 8 | 575 |  | 145 |  | 230 |  |  | 575 | 8 | SUBMITTAL IS 230 CFM
RTU-3 |  |  |  | 10825 | 0
Note on C7: NTAB: BILLINGSLEY ONLY

## RTU-3 SGRD (1)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-3 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
1-1 | 1105 | C | 10 | 250 |  |  | 0
1-2 | 1105 | C | 10 | 250 |  |  | 0
1-3 | 1105 | C | 10 | 350 |  |  | 0
1-4 | 1105 | C | 10 | 350 |  |  | 0
1-5 | 1105 | C | 10 | 350 |  |  | 0
1-6 | 1105 | C | 10 | 350 |  |  | 0
1-7 | 1105 | C | 10 | 350 |  |  | 0
1-8 | 1105 | C | 10 | 350 |  |  | 0
1-9 | 1200 | C | 8 | 150 |  |  | 0
1-10 | 1200 | C | 8 | 150 |  |  | 0
VAV-1.1 |  |  |  | 2900 |  | 0 | 0
2-1 | 1118 | B | 6 | 100 |  |  | 0
2-2 | 1117 | B | 6 | 100 |  |  | 0
2-3 | 1116 | B | 6 | 100 |  |  | 0
2-4 | 1100 | B | 8 | 225 |  |  | 0
2-5 | 1100 | B | 8 | 225 |  |  | 0
VAV-1.2 |  |  |  | 750 |  | 0 | 0
3-1 | 1113 | B | 6 | 100 |  |  | 0
3-2 | 1115 | B | 8X8 | 200 |  |  | 0
3-3 | 1114 | B | 6 | 100 |  |  | 0
3-4 | 1114 | B | 6 | 100 |  |  | 0
VAV-1.3 |  |  |  | 500 |  | 0 | 0
4-1 | 1107 | B | 8 | 150 |  |  | 0
4-2 | 1106 | B | 8 | 150 |  |  | 0
VAV-1.4 |  |  |  | 300 |  | 0 | 0
#DIV/0!
#DIV/0!

## RTU-3 SGRD (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-3 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
28-1 | 1101 | C | 8 | 200 |  |  | 0
28-2 | 1101 | C | 8 | 200 |  |  | 0
28-3 | 1101 | C | 8 | 200 |  |  | 0
28-4 | 1101 | C | 8 | 200 |  |  | 0
28-5 | 1101 | C | 8 | 200 |  |  | 0
28-6 | 1101A | C | 8 | 150 |  |  | 0
28-7 | 1101A | C | 8 | 150 |  |  | 0
CAV-1.28 |  |  |  | 1300 |  | 0 | 0
29-1 | 1101 | C | 8 | 200 |  |  | 0
29-2 | 1101 | C | 8 | 200 |  |  | 0
29-3 | 1101 | C | 8 | 200 |  |  | 0
29-4 | 1101 | C | 8 | 200 |  |  | 0
29-5 | 1101 | C | 8 | 200 |  |  | 0
CAV-1.29 |  |  |  | 1000 |  | 0 | 0
30-1 | 1102 | B | 8 | 175 |  |  | 0
30-2 | 1102 | B | 8 | 175 |  |  | 0
VAV-1.30 |  |  |  | 350 |  | 0 | 0
31-1 | 1103 | B | 8 | 125 |  |  | 0
31-2 | 1103 | B | 8 | 125 |  |  | 0
31-3 | 1103 | B | 8 | 125 |  |  | 0
31-4 | 1103 | B | 8 | 125 |  |  | 0
VAV-1.31 |  |  |  | 500 |  | 0 | 0

## RTU-3 SGRD (3)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-3 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
32-1 | 1104 | B | 8 | 200 |  |  | 0
32-2 | 1104 | B | 8 | 200 |  |  | 0
32-3 | 1104 | C | 8 | 200 |  |  | 0
32-4 | 1104 | B | 8 | 200 |  |  | 0
32-5 | 1104 | B | 8 | 200 |  |  | 0
32-6 | 1104 | C | 8 | 200 |  |  | 0
32-7 | 1104 | C | 8 | 200 |  |  | 0
32-8 | 1104 | B | 8 | 200 |  |  | 0
32-9 | 1104 | C | 8 | 200 |  |  | 0
32-10 | 1104 | C | 8 | 200 |  |  | 0
VAV-1.32 |  |  |  | 2000 |  | 0 | 0
133-1 | 1112 | B | 8X6 | 175 |  |  | 0
133-2 | 1111 | B | 8X8 | 225 |  |  | 0
VAV-1.33 |  |  |  | 400 |  | 0 | 0
134-1 | 1110 | B | 8X8 | 250 |  |  | 0
VAV-1.34 |  |  |  | 250 |  | 0 | 0
135-1 | 1109 | B | 8X8 | 200 |  |  | 0
135-2 | 1108 | B | 8 | 175 |  |  | 0
135-3 | 1108 | B | 8 | 200 |  |  | 0
VAV-1.35 |  |  |  | 575 |  | 0 | 0

## RTU-5
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-5 (EXISTING) |  | Building A
Unit Data |  | Test Data
Manufacturer | McQuay |  | Design | Actual
Model Num | OAH021FDAC | SF CFM | 10500 |  | 7975 | VAV TOTAL
Serial Num |  | SF RPM
Configuration |  | RA CFM | 8700
Num OA Filters |  | OA CFM | 1800
OA Filter Size |  | RL VOLTAGE
Num Final Filter |  | RL AMPERAGE
Final Filter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-5 VAV's
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-5 VAV's
Asset | Area Served | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL | UNIT SIZE | NOTES
VAV-1.5 | 1214 | REHEAT | 6 | 250 |  | 65 |  | 100 |  |  | 250 | 6 | SUBMITTAL IS 100 CFM
VAV-1.6 | 1215 | REHEAT | 8 | 400 |  | 100 |  | 160 |  |  | 400 | 8 | SUBMITTAL IS 160 CFM
VAV-1.7 | 1213 | REHEAT | 8 | 550 |  | 90 |  | 220 |  |  | 550 | 8 | SUBMITTAL IS 220 CFM
VAV-1.8 | 1206 | REHEAT | 8 | 400 |  | 100 |  | 160 |  |  | 400 | 8 | SUBMITTAL IS 160 CFM
VAV-1.9 | 1205 | REHEAT | 8 | 425 |  | 110 |  | 170 |  |  | 425 | 8 | SUBMITTAL IS 170 CFM
VAV-1.10 | 1202 | REHEAT | 5 | 175 |  | 45 |  | 70 |  |  | 175 | 5 | SUBMITTAL IS 70 CFM
VAV-1.39 | 1211 | REHEAT | 6 | 275 |  | 70 |  | 110 |  |  | 275 | 6 | SUBMITTAL IS 110 CFM
VAV-1.40 | 1216 | REHEAT | 10 | 950 |  | 240 |  | 380 |  |  | 950 | 10 | SUBMITTAL IS 380 CFM
VAV-1.41 | 1218 | REHEAT | 10 | 950 |  | 240 |  | 380 |  |  | 950 | 10 | SUBMITTAL IS 380 CFM
VAV-1.42 | 1219 | REHEAT | 10 | 850 |  | 215 |  | 340 |  |  | 850 | 10 | SUBMITTAL IS 340 CFM
VAV-1.44 | 1217 | REHEAT | 10 | 950 |  | 240 |  | 380 |  |  | 950 | 10 | SUBMITTAL IS 380 CFM
VAV-1.45 | 1210 | REHEAT | 10 | 850 |  | 215 |  | 340 |  |  | 850 | 10 | SUBMITTAL IS 340 CFM
VAV-1.46 | 1204 | REHEAT | 10 | 950 |  | 240 |  | 380 |  |  | 950 | 10 | SUBMITTAL IS 380 CFM
RTU-5 |  |  |  | 7975 | 0
Note on C7: NTAB: BILLINGSLEY ONLY

## RTU-5 SGRD (1)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-5 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
5-1 | 1214 | B | 8X8 | 250 |  |  | 0
VAV-1.5 |  |  |  | 250 |  | 0 | 0
6-1 | 1215 | B | 8 | 200 |  |  | 0
6-2 | 1215 | B | 8 | 200 |  |  | 0
VAV-1.6 |  |  |  | 400 |  | 0 | 0
7-1 | 1213 | B | 8 | 150 |  |  | 0
7-2 | 1213 | B | 8 | 125 |  |  | 0
7-3 | 1213 | B | 8 | 125 |  |  | 0
7-4 | 1213 | B | 8 | 150 |  |  | 0
VAV-1.7 |  |  |  | 550 |  | 0 | 0
8-1 | 1208 | B | 6 | 100 |  |  | 0
8-2 | 1206 | B | 8 | 175 |  |  | 0
8-3 | 1207 | B | 8 | 125 |  |  | 0
VAV-1.8 |  |  |  | 400 |  | 0 | 0
9-1 | 1200 | B | 8 | 175 |  |  | 0
9-2 | 1200 | B | 8 | 175 |  |  | 0
9-3 | 1205 | B | 6X6 | 75 |  |  | 0
VAV-1.9 |  |  |  | 425 |  | 0 | 0
10-1 | 1202 | B | 8X6 | 175 |  |  | 0
VAV-1.10 |  |  |  | 175 |  | 0 | 0
39-1 | 1211 | B | 8X6 | 125 |  |  | 0
39-2 | 1212 | B | 8X6 | 150 |  |  | 0
VAV-1.39 |  |  |  | 275 |  | 0 | 0

## RTU-5 SGRD (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-5 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
40-1 | 1216 | B | 8 | 225 |  |  | 0
40-2 | 1216 | B | 8 | 250 |  |  | 0
40-3 | 1216 | B | 8 | 225 |  |  | 0
40-4 | 1216 | B | 8 | 250 |  |  | 0
VAV-1.40 |  |  |  | 950 |  | 0 | 0
41-1 | 1218 | B | 8 | 225 |  |  | 0
41-2 | 1218 | B | 8 | 250 |  |  | 0
41-3 | 1218 | B | 8 | 225 |  |  | 0
41-4 | 1218 | B | 8 | 250 |  |  | 0
VAV-1.41 |  |  |  | 950 |  | 0 | 0
42-1 | 1219 | B | 8 | 200 |  |  | 0
42-2 | 1219 | B | 8 | 225 |  |  | 0
42-3 | 1219 | B | 8 | 200 |  |  | 0
42-4 | 1219 | B | 8 | 225 |  |  | 0
VAV-1.42 |  |  |  | 850 |  | 0 | 0
44-1 | 1217 | B | 8 | 225 |  |  | 0
44-2 | 1217 | B | 8 | 250 |  |  | 0
44-3 | 1217 | B | 8 | 225 |  |  | 0
44-4 | 1217 | B | 8 | 250 |  |  | 0
VAV-1.44 |  |  |  | 950 |  | 0 | 0
45-1 | 1210 | B | 8 | 175 |  |  | 0
45-2 | 1210 | B | 8 | 175 |  |  | 0
45-3 | 1210 | B | 8 | 175 |  |  | 0
45-4 | 1210 | B | 8 | 175 |  |  | 0
45-5 | 1210 | B | 8X8 | 150 |  |  | 0
VAV-1.45 |  |  |  | 850 |  | 0 | 0

## RTU-5 SGRD (3)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-5 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
146-1 | 1204 | B | 8 | 150 |  |  | 0
146-2 | 1204 | B | 8 | 175 |  |  | 0
146-3 | 1204 | B | 8 | 150 |  |  | 0
146-4 | 1204 | B | 8 | 150 |  |  | 0
146-5 | 1204 | B | 8 | 175 |  |  | 0
146-6 | 1204 | B | 8 | 150 |  |  | 0
VAV-1.46 |  |  |  | 950 |  |  | 0

## RTU-6
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-6 (EXISTING) |  | Building A
Unit Data |  | Test Data
Manufacturer | McQuay |  | Design | Actual
Model Num | OAH025FDAC | SF CFM | 13500 |  | 9750 | VAV TOTAL
Serial Num |  | SF RPM
Configuration |  | RA CFM | 12475
Num OA Filters |  | OA CFM | 1025
OA Filter Size |  | RL VOLTAGE
Num Final Filter |  | RL AMPERAGE
Final Filter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-6 VAV's
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-6 VAV's
Asset | Area Served | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL | UNIT SIZE | NOTES
VAV-1.11 | 1513 | REHEAT |  | 320 |  | 200 |  | 320 |  |  | 800 | 10 | SUBMITTAL IS 320 CFM, SCHEDULE IS 800 CFM, LOAD IS 800 CFM
VAV-1.12 | 1518 | REHEAT |  | 130 |  | 85 |  | 130 |  |  | 325 | 6 | SUBMITTAL IS 130 CFM, SCHEDULE IS 325 CFM, LOAD IS 325 CFM
VAV-1.13 | CORRIDOR | REHEAT |  | 370 |  | 235 |  | 370 |  |  | 875 | 10 | SUBMITTAL IS 370 CFM, SCHEDULE IS 925 CFM, LOAD IS 875 CFM
VAV-1.14 | 1511 | REHEAT |  | 140 |  | 90 |  | 140 |  |  | 350 | 6 | SUBMITTAL IS 140 CFM, SCHEDULE IS 350 CFM, LOAD IS 350 CFM
VAV-1.15 | 1404 | REHEAT |  | 100 |  | 65 |  | 100 |  |  | 250 | 6 | SUBMITTAL IS 100 CFM, SCHEDULE IS 250 CFM, LOAD IS 250 CFM
VAV-1.16 | 1401 | REHEAT |  | 170 |  | 110 |  | 170 |  |  | 425 | 8 | SUBMITTAL IS 170 CFM, SCHEDULE IS 425 CFM, LOAD IS 425 CFM
VAV-1.17 | 1406 | REHEAT | 6 | 250 |  | 65 |  | 100 |  |  | 250 | 6 | SUBMITTAL IS 100 CFM
VAV-1.18 | 1411 | REHEAT | 6 | 400 |  | 95 |  | 150 |  |  | 400 | 6 | SUBMITTAL IS 150 CFM
VAV-1.19 | 1408 | REHEAT | 6 | 550 |  | 75 |  | 120 |  |  | 550 | 6 | SUBMITTAL IS 120 CFM
VAV-1.20 | 1412 | REHEAT | 5 | 400 |  | 25 |  | 40 |  |  | 400 | 5 | SUBMITTAL IS 40 CFM
VAV-1.21 | 1417 | REHEAT | 6 | 425 |  | 75 |  | 120 |  |  | 425 | 6 | SUBMITTAL IS 120 CFM
VAV-1.22 | 1414 | REHEAT | 6 | 175 |  | 115 |  | 180 |  |  | 175 | 6 | SUBMITTAL IS 180 CFM
VAV-1.23 | 1418 | REHEAT | 6 | 275 |  | 75 |  | 120 |  |  | 275 | 6 | SUBMITTAL IS 120 CFM
VAV-1.24 | 1424 | REHEAT | 8 | 950 |  | 150 |  | 240 |  |  | 950 | 8 | SUBMITTAL IS 240 CFM
VAV-1.25 | 1425 | REHEAT | 10 | 950 |  | 175 |  | 280 |  |  | 950 | 10 | SUBMITTAL IS 280 CFM
VAV-1.26 | 1423 | REHEAT | 8 | 850 |  | 100 |  | 160 |  |  | 850 | 8 | SUBMITTAL IS 160 CFM
VAV-1.27 | 1501 | REHEAT | 12 | 950 |  | 365 |  | 580 |  |  | 950 | 12 | SUBMITTAL IS 580 CFM
VAV-1.36 | 1501 | REHEAT | 10 | 850 |  | 250 |  | 400 |  |  | 850 | 10 | SUBMITTAL IS 400 CFM
VAV-1.37 | 1403 | REHEAT | 5 | 950 |  | 40 |  | 60 |  |  | 950 | 5 | SUBMITTAL IS 60 CFM
VAV-1.38 | 1402 | REHEAT | 6 | 300 |  | 75 |  | 120 |  |  | 300 | 6 | SUBMITTAL IS 120 CFM
RTU-6 |  |  |  | 9505 | 0
Note on C7: NTAB: BILLINGSLEY ONLY

## RTU-6 SGRD (1)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-6 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
11-1 | 1514 | B | 8X8 | 250 |  |  | 0
11-2 | 1507 | B | 6 | 100 |  |  | 0
11-3 | 1506 | B | 8 | 150 |  |  | 0
11-4 | 1506 | B | 8 | 150 |  |  | 0
11-5 | 1513 | B | 6 | 150 |  |  | 0
VAV-1.11 |  |  |  | 800 |  | 0 | 0
12-1 | 1519 | B | 8 | 175 |  |  | 0
12-2 | 1518 | B | 8 | 150 |  |  | 0
VAV-1.12 |  |  |  | 325 |  | 0 | 0
13-1 | 1517 | B | 8 | 125 |  |  | 0
13-2 | CORRIDOR | B | 8 | 150 |  |  | 0
13-3 | CORRIDOR | B | 8 | 150 |  |  | 0
13-4 | CORRIDOR | B | 8 | 150 |  |  | 0
13-5 | CORRIDOR | B | 8 | 150 |  |  | 0
13-6 | CORRIDOR | B | 8 | 150 |  |  | 0
VAV-1.13 |  |  |  | 875 |  |  | 0
14-1 | 1510 | B | 6 | 100 |  |  | 0
14-2 | 1511 | B | 6 | 125 |  |  | 0
14-3 | 1512 | B | 6 | 125 |  |  | 0
VAV-1.14 |  |  |  | 350 |  | 0 | 0
15-1 | 1404 | B | 6 | 125 |  |  | 0
15-2 | 1405 | B | 6 | 125 |  |  | 0
VAV-1.15 |  |  |  | 250 |  |  | 0

## RTU-6 SGRD (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-6 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
16-1 | 1401 | B | 6X6 | 125 |  |  | 0
16-2 | HALL | B | 6X6 | 150 |  |  | 0 | 2 DANGLING DIFFUSERS TOTAL THE MISSING 300 CFM AND IS IN THE VACINITY
16-3 | HALL | B | 6X6 | 150 |  |  | 0 | 2 DANGLING DIFFUSERS TOTAL THE MISSING 300 CFM AND IS IN THE VACINITY
VAV-1.16 |  |  |  | 425 |  | 0 | 0
17-1 | 1407 | B | 6 | 125 |  |  | 0
17-2 | 1406 | B | 6X6 | 125 |  |  | 0
VAV-1.17 |  |  |  | 250 |  | 0 | 0
18-1 | 1411 | B | 6X6 | 125 |  |  | 0
18-2 | 1409 | B | 6 | 125 |  |  | 0
18-3 | 1410 | B | 6X6 | 125 |  |  | 0
VAV-1.18 |  |  |  | 375 |  | 0 | 0
19-1 | 1408 | B | 8 | 200 |  |  | 0
19-2 | 1408 | B | 8 | 125 |  |  | 0
VAV-1.19 |  |  |  | 325 |  | 0 | 0
20-1 | 1412 | B | 6 | 100 |  |  | 0
VAV-1.20 |  |  |  | 100 |  | 0 | 0
21-1 | 1417 | B | 8 | 125 |  |  | 0
21-2 | 1416 | B | 8 | 125 |  |  | 0
VAV-1.21 |  |  |  | 250 |  | 0 | 0
22-1 | 1420 | B | 6 | 50 |  |  | 0
22-2 | LOBBY | B | 8 | 150 |  |  | 0
22-3 | 1415 | B | 8 | 125 |  |  | 0
22-4 | 1414 | B | 8 | 125 |  |  | 0
VAV-1.22 |  |  |  | 450 |  | 0 | 0

## RTU-6 SGRD (3)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-6 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
23-1 | 1419 | B | 8 | 100 |  |  | 0
23-2 | 1418 | B | 8 | 200 |  |  | 0
VAV-1.23 |  |  |  | 300 |  | 0 | 0
24-1 | 1424 | B | 8 | 150 |  |  | 0
24-2 | 1424 | B | 8 | 150 |  |  | 0
24-3 | 1424 | B | 8 | 150 |  |  | 0
24-4 | 1424 | B | 8 | 150 |  |  | 0
VAV-1.24 |  |  |  | 600 |  | 0 | 0
25-1 | 1426 | B | 10 | 275 |  |  | 0
25-2 | 1426 | B | 10 | 275 |  |  | 0
25-3 | 1425 | B | 8 | 150 |  |  | 0
VAV-1.25 |  |  |  | 700 |  | 0 | 0
26-1 | SECURITY | B | 8 | 150 |  |  | 0
26-2 | SECURITY | B | 6 | 75 |  |  | 0
26-3 | 1422 | B | 8 | 150 |  |  | 0
26-4 | 1423 | B | 8 | 175 |  |  | 0
VAV-1.26 |  |  |  | 550 |  | 0 | 0

## RTU-6 SGRD (4)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-6 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
27-1 | 1509 | A | 6 | 50 |  |  | 0
27-2 | 1508 | A | 6 | 75 |  |  | 0
27-3 | 1502 | D |  | 100 |  |  | 0
27-4 | 1501 | D |  | 150 |  |  | 0
27-5 | 1501 | D |  | 150 |  |  | 0
27-6 | 1501 | D |  | 150 |  |  | 0
27-7 | 1501 | D |  | 150 |  |  | 0
27-8 | 1501 | D |  | 125 |  |  | 0
27-9 | 1501 | D |  | 125 |  |  | 0
27-10 | 1503 | B | 6 | 100 |  |  | 0
27-11 | 1504 | B | 6 | 100 |  |  | 0
27-12 | 1505 | D |  | 125 |  |  | 0
VAV-1.27 |  |  |  | 1400 |  | 0 | 0
36-1 | 1501 | D |  | 170 |  |  | 0
36-2 | 1501 | D |  | 165 |  |  | 0
36-3 | 1501 | D |  | 165 |  |  | 0
36-4 | 1501 | D |  | 165 |  |  | 0
36-5 | 1501 | D |  | 170 |  |  | 0
36-6 | 1501 | D |  | 165 |  |  | 0
VAV-1.36 |  |  |  | 1000 |  | 0 | 0
37-1 | 1403 | B | 8X6 | 150 |  |  | 0
VAV-1.37 |  |  |  | 150 |  | 0 | 0
38-1 | 1402 | B | 8 | 150 |  |  | 0
38-2 | 1402 | B | 8 | 150 |  |  | 0
VAV-1.38 |  |  |  | 300 |  | 0 | 0

## RTU-7
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-7 (EXISTING) |  | Building A
Unit Data |  | Test Data
Manufacturer | McQuay |  | Design | Actual
Model Num | OAH017FDAC | SF CFM | 8500 |  | 7675 | VAV TOTAL
Serial Num |  | SF RPM
Configuration |  | RA CFM | 6750
Num OA Filters |  | OA CFM | 1750
OA Filter Size |  | RL VOLTAGE
Num Final Filter |  | RL AMPERAGE
Final Filter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-7 VAV's
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-7 VAV's
Asset | Area Served | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL | UNIT SIZE | NOTES
VAV-1.56 | 1338 | REHEAT | 10 | 900 |  | 225 |  | 360 |  |  | 900 | 10 | SUBMITTAL IS 360 CFM
VAV-1.57 | 1337 | REHEAT | 10 | 1000 |  | 250 |  | 400 |  |  | 1000 | 10 | SUBMITTAL IS 400 CFM
VAV-1.58 | 1339 | REHEAT | 10 | 900 |  | 225 |  | 360 |  |  | 900 | 10 | SUBMITTAL IS 360 CFM
VAV-1.59 | 1341 | REHEAT | 10 | 900 |  | 225 |  | 360 |  |  | 900 | 10 | SUBMITTAL IS 360 CFM
VAV-1.60 | 1340 | REHEAT | 10 | 1000 |  | 250 |  | 400 |  |  | 1000 | 10 | SUBMITTAL IS 400 CFM
VAV-1.61 | 1336 | REHEAT | 10 | 950 |  | 240 |  | 380 |  |  | 950 | 10 | SUBMITTAL IS 380 CFM
VAV-1.62 | 1327 | REHEAT | 10 | 1300 |  | 275 |  | 440 |  |  | 1300 | 10 | SUBMITTAL IS 440 CFM
VAV-1.63 | 1330 | REHEAT | 5 | 225 |  | 60 |  | 90 |  |  | 225 | 5 | SUBMITTAL IS 90 CFM
VAV-1.64 | 1329 | REHEAT | 5 | 150 |  | 40 |  | 60 |  |  | 150 | 5 | SUBMITTAL IS 60 CFM
VAV-1.65 | 1334 | REHEAT | 5 | 200 |  | 50 |  | 80 |  |  | 200 | 5 | SUBMITTAL IS 80 CFM
VAV-1.66 | 1333 | REHEAT | 5 | 200 |  | 50 |  | 80 |  |  | 200 | 5 | SUBMITTAL IS 80 CFM
VAV-1.67 | 1328 | REHEAT | 5 | 150 |  | 40 |  | 60 |  |  | 150 | 5 | SUBMITTAL IS 60 CFM
RTU-7 |  |  |  | 7875 | 0
Note on C7: NTAB: BILLINGSLEY ONLY

## RTU-7 SGRD (1)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-7 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
156-1 | 1338 | B | 8 | 150 |  |  | 0
156-2 | 1338 | B | 8 | 150 |  |  | 0
156-3 | 1338 | B | 8 | 150 |  |  | 0
156-4 | 1338 | B | 8 | 150 |  |  | 0
156-5 | 1338 | B | 8 | 150 |  |  | 0
156-6 | 1338 | B | 8 | 150 |  |  | 0
VAV-1.56 |  |  |  | 900 |  | 0 | 0
157-1 | 1337 | B | 8 | 125 |  |  | 0
157-2 | 1337 | B | 8 | 125 |  |  | 0
157-3 | 1337 | B | 8 | 125 |  |  | 0
157-4 | 1337 | B | 8 | 125 |  |  | 0
157-5 | 1337 | B | 8 | 125 |  |  | 0
157-6 | 1337 | B | 8 | 125 |  |  | 0
157-7 | 1337 | B | 8 | 125 |  |  | 0
157-8 | 1337 | B | 8 | 125 |  |  | 0
VAV-1.57 |  |  |  | 1000 |  | 0 | 0
158-1 | 1339 | B | 8 | 150 |  |  | 0
158-2 | 1339 | B | 8 | 150 |  |  | 0
158-3 | 1339 | B | 8 | 150 |  |  | 0
158-4 | 1339 | B | 8 | 150 |  |  | 0
158-5 | 1339 | B | 8 | 150 |  |  | 0
158-6 | 1339 | B | 8 | 150 |  |  | 0
VAV-1.58 |  |  |  | 900 |  |  | 0

## RTU-7 SGRD (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-7 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
159-1 | 1341 | B | 8 | 150 |  |  | 0
159-2 | 1341 | B | 8 | 150 |  |  | 0
159-3 | 1341 | B | 8 | 150 |  |  | 0
159-4 | 1341 | B | 8 | 150 |  |  | 0
159-5 | 1341 | B | 8 | 150 |  |  | 0
159-6 | 1341 | B | 8 | 150 |  |  | 0
VAV-1.59 |  |  |  | 900 |  | 0 | 0
160-1 | 1340 | B | 8 | 125 |  |  | 0
160-2 | 1340 | B | 8 | 125 |  |  | 0
160-3 | 1340 | B | 8 | 125 |  |  | 0
160-4 | 1340 | B | 8 | 125 |  |  | 0
160-5 | 1340 | B | 8 | 125 |  |  | 0
160-6 | 1340 | B | 8 | 125 |  |  | 0
160-7 | 1340 | B | 8 | 125 |  |  | 0
160-8 | 1340 | B | 8 | 125 |  |  | 0
VAV-1.60 |  |  |  | 1000 |  | 0 | 0
161-1 | 1336 | B | 8 | 150 |  |  | 0
161-2 | 1336 | B | 8 | 150 |  |  | 0
161-3 | 1336 | B | 8 | 175 |  |  | 0
161-4 | 1336 | B | 8 | 175 |  |  | 0
161-5 | 1336 | B | 8 | 150 |  |  | 0
161-6 | 1336 | B | 8 | 150 |  |  | 0
VAV-1.61 |  |  |  | 950 |  |  | 0

## RTU-7 SGRD (3)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-7 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
162-1 | 1327 | B | 8 | 150 |  |  | 0
162-2 | 1327 | B | 8 | 175 |  |  | 0
162-3 | 1327 | B | 8 | 175 |  |  | 0
162-4 | 1327 | B | 8 | 150 |  |  | 0
162-5 | 1327 | B | 8 | 150 |  |  | 0
162-6 | 1327 | B | 8 | 175 |  |  | 0
162-7 | 1327 | B | 8 | 175 |  |  | 0
162-8 | 1327 | B | 8 | 150 |  |  | 0
VAV-1.62 |  |  |  | 1300 |  | 0 | 0
163-1 | 1330 | B | 8 | 175 |  |  | 0
163-2 | 1335 | B | 6 | 50 |  |  | 0
VAV-1.63 |  |  |  | 225 |  | 0 | 0
164-1 | 1329 | B | 6X6 | 150 |  |  | 0
VAV-1.64 |  |  |  | 150 |  | 0 | 0
165-1 | 1331 | B | 6 | 100 |  |  | 0
165-2 | 1334 | B | 6 | 100 |  |  | 0
VAV-1.65 |  |  |  | 200 |  | 0 | 0
166-1 | 1332 | B | 6 | 100 |  |  | 0
166-2 | 1333 | B | 6 | 100 |  |  | 0
VAV-1.66 |  |  |  | 200 |  | 0 | 0
167-1 | 1328 | B | 6X6 | 150 |  |  | 0
VAV-1.67 |  |  |  | 150 |  | 0 | 0

## RTU-8
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-8 (EXISTING) |  | Building A
Unit Data |  | Test Data
Manufacturer | McQuay |  | Design | Actual
Model Num | OAH025FDAC | SF CFM | 13500 |  | 11125 | VAV TOTAL
Serial Num |  | SF RPM
Configuration |  | RA CFM | 11375
Num OA Filters |  | OA CFM | 2125
OA Filter Size |  | RL VOLTAGE
Num Final Filter |  | RL AMPERAGE
Final Filter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-8 VAV's
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-8 VAV's
Asset | Area Served | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL | UNIT SIZE | NOTES
VAV-1.68 | 1729 | REHEAT | 8 | 450 |  | 115 |  | 180 |  |  | 450 | 8 | SUBMITTAL IS 180 CFM
VAV-1.69 | 1342 | REHEAT | 10 | 1300 |  | 275 |  | 440 |  |  | 1300 | 10 | SUBMITTAL IS 440 CFM
VAV-1.70 | 1728 | REHEAT | 12 | 1500 |  | 375 |  | 600 |  |  | 1500 | 12 | SUBMITTAL IS 600 CFM
VAV-1.71 | 1724 | REHEAT | 10 | 1000 |  | 250 |  | 440 |  |  | 1000 | 10 | SUBMITTAL IS 440 CFM
VAV-1.72 | 1727 | REHEAT | 10 | 750 |  | 190 |  | 300 |  |  | 750 | 10 | SUBMITTAL IS 300 CFM
VAV-1.73 | CORRIDOR | REHEAT | 10 | 925 |  | 235 |  | 370 |  |  | 925 | 10 | SUBMITTAL IS 370 CFM
VAV-1.74 | 1725 | REHEAT | 10 | 1000 |  | 250 |  | 400 |  |  | 1000 | 10 | SUBMITTAL IS 400 CFM
VAV-1.75 | 1723 | REHEAT | 10 | 1000 |  | 250 |  | 440 |  |  | 1000 | 10 | SUBMITTAL IS 400 CFM
VAV-1.76 | 1326 | REHEAT | 10 | 1300 |  | 275 |  | 440 |  |  | 1300 | 10 | SUBMITTAL IS 440 CFM
VAV-1.77 | 1722 | REHEAT | 10 | 1175 |  | 275 |  | 440 |  |  | 1175 | 10 | SUBMITTAL IS 440 CFM
VAV-1.78 | 1721 | REHEAT | 10 | 1200 |  | 300 |  | 480 |  |  | 1200 | 10 | SUBMITTAL IS 480 CFM
11600
Note on C7: NTAB: BILLINGSLEY ONLY

## RTU-8 SGRD (1)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-8 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
168-1 | 1730 | B | 8 | 200 |  |  | 0
168-2 | 1730 | B | 8 | 125 |  |  | 0
168-3 | 1730 | B | 8 | 125 |  |  | 0
VAV-1.68 |  |  |  | 450 |  | 0 | 0
169-1 | 1342 | B | 8 | 150 |  |  | 0
169-2 | 1342 | B | 8 | 175 |  |  | 0
169-3 | 1342 | B | 8 | 150 |  |  | 0
169-4 | 1342 | B | 8 | 175 |  |  | 0
169-5 | 1342 | B | 8 | 175 |  |  | 0
169-6 | 1342 | B | 8 | 150 |  |  | 0
169-7 | 1342 | B | 8 | 150 |  |  | 0
169-8 | 1342 | B | 8 | 175 |  |  | 0
VAV-1.69 |  |  |  | 1300 |  | 0 | 0
170-1 | 1728 | B | 8 | 125 |  |  | 0
170-2 | 1728 | B | 8 | 125 |  |  | 0
170-3 | 1728 | B | 8 | 125 |  |  | 0
170-4 | 1728 | B | 8 | 125 |  |  | 0
170-5 | 1728 | B | 8 | 125 |  |  | 0
170-6 | 1728 | B | 8 | 125 |  |  | 0
170-7 | 1728 | B | 8 | 125 |  |  | 0
170-8 | 1728 | B | 8 | 125 |  |  | 0
170-9 | 1728 | B | 8 | 125 |  |  | 0
170-10 | 1728 | B | 8 | 125 |  |  | 0
170-11 | 1728 | B | 8 | 125 |  |  | 0
170-12 | 1728 | B | 8 | 125 |  |  | 0
VAV-1.70 |  |  |  | 1500 |  | 0 | 0

## RTU-8 SGRD (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-8 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
171-1 | 1724 | B | 8 | 125 |  |  | 0
171-2 | 1724 | B | 8 | 125 |  |  | 0
171-3 | 1724 | B | 8 | 125 |  |  | 0
171-4 | 1724 | B | 8 | 125 |  |  | 0
171-5 | 1724 | B | 8 | 125 |  |  | 0
171-6 | 1724 | B | 8 | 125 |  |  | 0
171-7 | 1724 | B | 8 | 125 |  |  | 0
171-8 | 1724 | B | 8 | 125 |  |  | 0
VAV-1.71 |  |  |  | 1000 |  | 0 | 0
172-1 | 1727 | B | 8 | 125 |  |  | 0
172-2 | 1727 | B | 8 | 125 |  |  | 0
172-3 | 1727 | B | 8 | 125 |  |  | 0
172-4 | 1727 | B | 8 | 125 |  |  | 0
172-5 | 1727 | B | 8 | 125 |  |  | 0
172-6 | 1727 | B | 8 | 125 |  |  | 0
VAV-1.72 |  |  |  | 750 |  |  | 0
173-1 | CORRIDOR | B | 8 | 200 |  |  | 0
173-2 | CORRIDOR | B | 8 | 175 |  |  | 0
173-3 | CORRIDOR | B | 8 | 200 |  |  | 0
173-4 | CORRIDOR | B | 8 | 175 |  |  | 0
173-5 | CORRIDOR | B | 8 | 175 |  |  | 0
VAV-1.73 |  |  |  | 925 |  |  | 0

## RTU-8 SGRD (3)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-8 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
174-1 | 1725 | B | 8 | 125 |  |  | 0
174-2 | 1725 | B | 8 | 125 |  |  | 0
174-3 | 1725 | B | 8 | 125 |  |  | 0
174-4 | 1725 | B | 8 | 125 |  |  | 0
174-5 | 1725 | B | 8 | 125 |  |  | 0
174-6 | 1725 | B | 8 | 125 |  |  | 0
174-7 | 1725 | B | 8 | 125 |  |  | 0
174-8 | 1725 | B | 8 | 125 |  |  | 0
VAV-1.74 |  |  |  | 1000 |  | 0 | 0
175-1 | 1723 | B | 8 | 125 |  |  | 0
175-2 | 1723 | B | 8 | 125 |  |  | 0
175-3 | 1723 | B | 8 | 125 |  |  | 0
175-4 | 1723 | B | 8 | 125 |  |  | 0
175-5 | 1723 | B | 8 | 125 |  |  | 0
175-6 | 1723 | B | 8 | 125 |  |  | 0
175-7 | 1723 | B | 8 | 125 |  |  | 0
175-8 | 1723 | B | 8 | 125 |  |  | 0
VAV-1.75 |  |  |  | 1000 |  | 0 | 0
176-1 | 1326 | B | 8 | 150 |  |  | 0
176-2 | 1326 | B | 8 | 175 |  |  | 0
176-3 | 1326 | B | 8 | 175 |  |  | 0
176-4 | 1326 | B | 8 | 150 |  |  | 0
176-5 | 1326 | B | 8 | 150 |  |  | 0
176-6 | 1326 | B | 8 | 175 |  |  | 0
176-7 | 1326 | B | 8 | 150 |  |  | 0
176-8 | 1326 | B | 8 | 175 |  |  | 0
VAV-1.76 |  |  |  | 1300 |  |  | 0

## RTU-8 SGRD (4)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: RTU-8 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
177-1 | 1722 | B | 6 | 100 |  |  | 0
177-2 | 1722 | B | 6 | 100 |  |  | 0
177-3 | 1722 | B | 6 | 100 |  |  | 0
177-4 | 1722 | B | 6 | 100 |  |  | 0
177-5 | 1722 | B | 6 | 100 |  |  | 0
177-6 | 1722 | B | 6 | 100 |  |  | 0
177-7 | 1700A | B | 8 | 200 |  |  | 0
177-8 | 1700A | B | 8 | 175 |  |  | 0
177-9 | 1700A | B | 8 | 200 |  |  | 0
VAV-1.77 |  |  |  | 1175 |  | 0 | 0
178-1 | 1721 | B | 8 | 125 |  |  | 0
178-2 | 1721 | B | 8 | 125 |  |  | 0
178-3 | 1719 | B | 8 | 200 |  |  | 0
178-4 | 1721 | B | 8 | 125 |  |  | 0
178-5 | 1721 | B | 8 | 125 |  |  | 0
178-6 | 1721 | B | 8 | 125 |  |  | 0
178-7 | 1721 | B | 8 | 125 |  |  | 0
178-8 | 1721 | B | 8 | 125 |  |  | 0
178-9 | 1721 | B | 8 | 125 |  |  | 0
VAV-1.78 |  |  |  | 1200 |  | 0 | 0

## AHU-9
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: AHU-9 (EXISTING) |  | Area: BUILDING A, AREA B
Supply Side
Unit Data |  |  | Test Data |  |  | USE FOR:
Manufacturer | McQuay |  |  | Design | Actual | VAV's
Model Number | EXISTING |  | Supply CFM | 17500 |  | No Return Fan
Serial Number |  |  | Min OA CFM | 3075
Configuration |  |  | Return CFM | 14425
No. Pre Filters / Size |  |  | Fan RPM |  |  | Remove unused fields:
No. Pre Filters / Size |  |  | Operating HZ |  |  | Heat Wheel
No. Pre Filters / Size |  |  | RL Voltage |  |  | CW/HW Coil (Change to DX coil if applicable)
No. Final Filters / Size |  |  | RL Amperage
No. Final Filters / Size |  |  | Motor B.H.P. |  |  | 14625 | VAV TOTAL
No. Final Filters / Size
Performance Data
Motor Data X |  |  |  | Design | Actual
Motor MFG / Frame |  |  | Suction S.P.
Horsepower / RPM |  |  | Discharge S.P.
Rated Volts / Phase |  |  | Total SP
Rated Amperage / SF |  |  | System S.P. Set Point
CW Coil P.D.
Drive Data |  |  | HW Coil P.D.
Motor Sheave Size / Bore |  |  | Final Filters P.D.
Fan Sheave Size / Bore |  |  | Heat Wheel P.D.
Belt CL Distance |  |  | Heat Wheel P.D.
No. Belts / Size |  |  | Pre Filters P.D.
Total ESP

## AHU-9 VAV's
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: AHU-9 VAV's
Asset | Area Served | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max) | GRD TOTAL | UNIT SIZE | NOTES
VAV-1.43 | 1720 | REHEAT | 10 | 1000 |  | 275 |  | 400 |  |  | 1000 | 10 | SUBMITTAL IS 400 CFM
VAV-1.47 | 1718 | REHEAT | 10 | 700 |  | 175 |  | 280 |  |  | 700 | 10 | SUBMITTAL IS 280 CFM
VAV-1.48 | 1717 | REHEAT | 10 | 1100 |  | 275 |  | 440 |  |  | 1100 | 10 | SUBMITTAL IS 440 CFM
VAV-1.49 | 1714 | REHEAT | 10 | 1100 |  | 275 |  | 440 |  |  | 1100 | 10 | SUBMITTAL IS 440 CFM
VAV-1.50 | 1713 | REHEAT | 10 | 1200 |  | 300 |  | 480 |  |  | 1200 | 10 | SUBMITTAL IS 480 CFM
VAV-1.51 | 1709 | REHEAT | 6 | 350 |  | 90 |  | 140 |  |  | 350 | 6 | SUBMITTAL IS 140 CFM
VAV-1.52 | 1705 | REHEAT | 8 | 525 |  | 135 |  | 210 |  |  | 525 | 8 | SUBMITTAL IS 210 CFM
VAV-1.53 | 1706 | REHEAT | 5 | 175 |  | 45 |  | 70 |  |  | 175 | 5 | SUBMITTAL IS 70 CFM
VAV-1.54 | 1710 | REHEAT | 6 | 250 |  | 65 |  | 100 |  |  | 250 | 6 | SUBMITTAL IS 100 CFM
VAV-1.55 | 1702 | REHEAT | 10 | 1100 |  | 275 |  | 440 |  |  | 1100 | 10 | SUBMITTAL IS 440 CFM
VAV-1.79 | 1309 | REHEAT | 10 | 1275 |  | 320 |  | 510 |  |  | 1275 | 10 | SUBMITTAL IS 510 CFM
VAV-1.80 | 1311 | REHEAT | 6 | 300 |  | 75 |  | 120 |  |  | 300 | 6 | SUBMITTAL IS 120 CFM
VAV-1.81 | 1321 | REHEAT | 8 | 600 |  | 150 |  | 240 |  |  | 600 | 8 | SUBMITTAL IS 240 CFM
VAV-1.82 | 1301 | REHEAT | 6 | 250 |  | 65 |  | 100 |  |  | 250 | 6 | SUBMITTAL IS 100 CFM
VAV-1.83 | 1312 | REHEAT | 8 | 650 |  | 165 |  | 260 |  |  | 650 | 8 | SUBMITTAL IS 260 CFM
VAV-1.84 | 1317 | REHEAT | 10 | 900 |  | 225 |  | 360 |  |  | 900 | 10 | SUBMITTAL IS 360 CFM
VAV-1.85 | 1303 | REHEAT | 10 | 700 |  | 175 |  | 280 |  |  | 700 | 10 | SUBMITTAL IS 280 CFM
VAV-1.86 | 1316 | REHEAT | 10 | 825 |  | 210 |  | 330 |  |  | 825 | 10 | SUBMITTAL IS 330 CFM
VAV-1.87 | 1315 | REHEAT | 8 | 425 |  | 110 |  | 170 |  |  | 425 | 8 | SUBMITTAL IS 170 CFM
VAV-1.88 | 1302 | REHEAT | 10 | 900 |  | 225 |  | 360 |  |  | 900 | 10 | SUBMITTAL IS 360 CFM
VAV-1.89 | RECPT | REHEAT | 6 | 200 |  | 50 |  | 100 |  |  | 200 | 6 | SUBMITTAL IS 100 CFM
AHU-9 |  |  |  | 14525 | 0 |  |  | 5830 | 0
Note on C7: NTAB: BILLINGSLEY ONLY

## AHU-9 SGRD (1)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: AHU-9 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
143-1 | 1720 | B | 8 | 125 |  |  | 0
143-2 | 1720 | B | 8 | 125 |  |  | 0
143-3 | 1720 | B | 8 | 125 |  |  | 0
143-4 | 1720 | B | 8 | 125 |  |  | 0
143-5 | 1720 | B | 8 | 125 |  |  | 0
143-6 | 1720 | B | 8 | 125 |  |  | 0
143-7 | 1720 | B | 8 | 125 |  |  | 0
143-8 | 1720 | B | 8 | 125 |  |  | 0
VAV-1.43 |  |  |  | 1000 |  | 0 | 0
147-1 | 1718 | B | 8 | 175 |  |  | 0
147-2 | 1718 | B | 8 | 175 |  |  | 0
147-3 | 1718 | B | 8 | 175 |  |  | 0
147-4 | 1718 | B | 8 | 175 |  |  | 0
VAV-1.47 |  |  |  | 700 |  | 0 | 0
148-1 | 1717 | B | 8 | 125 |  |  | 0
148-2 | 1717 | B | 8 | 125 |  |  | 0
148-3 | 1717 | B | 8 | 150 |  |  | 0
148-4 | 1717 | B | 8 | 150 |  |  | 0
148-5 | 1717 | B | 8 | 125 |  |  | 0
148-6 | 1717 | B | 8 | 125 |  |  | 0
148-7 | 1717 | B | 8 | 150 |  |  | 0
148-8 | 1717 | B | 8 | 150 |  |  | 0
VAV-1.48 |  |  |  | 1100 |  |  | 0

## AHU-9 SGRD (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: AHU-9 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
149-1 | 1714 | B | 8 | 175 |  |  | 0
149-2 | 1714 | B | 8 | 175 |  |  | 0
149-3 | 1714 | B | 8 | 175 |  |  | 0
149-4 | 1714 | B | 8 | 175 |  |  | 0
149-5 | 1714 | B | 8 | 200 |  |  | 0
149-6 | 1714 | B | 8 | 200 |  |  | 0
VAV-1.49 |  |  |  | 1100 |  | 0 | 0
150-1 | 1713 | B | 6 | 100 |  |  | 0
150-2 | 1713 | B | 8 | 175 |  |  | 0
150-3 | 1713 | B | 8 | 175 |  |  | 0
150-4 | 1713 | B | 8 | 175 |  |  | 0
150-5 | 1713 | B | 8 | 175 |  |  | 0
150-6 | 1713 | B | 8 | 200 |  |  | 0
150-7 | 1713 | B | 8 | 200 |  |  | 0
VAV-1.50 |  |  |  | 1200 |  | 0 | 0
151-1 | 1708 | B | 6 | 100 |  |  | 0
151-2 | 1707 | B | 6 | 100 |  |  | 0
151-3 | 1709 | B | 6 | 100 |  |  | 0
151-4 | 1700B | B | 6 | 50 |  |  | 0
VAV-1.51 |  |  |  | 350 |  | 0 | 0
152-1 | 1705 | B | 8 | 175 |  |  | 0
152-2 | 1705 | B | 8 | 200 |  |  | 0
152-3 | 1704 | B | 8 | 150 |  |  | 0
VAV-1.52 |  |  |  | 525 |  | 0 | 0
153-1 | 1706 | B | 8X6 | 175 |  |  | 0
VAV-1.53 |  |  |  | 175 |  | 0 | 0

## AHU-9 SGRD (3)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: AHU-9 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
154-1 | 1711 | B | 6 | 100 |  |  | 0
154-2 | 1700B | B | 6 | 50 |  |  | 0
154-3 | 1710 | B | 6 | 100 |  |  | 0
VAV-1.54 |  |  |  | 250 |  | 0 | 0
155-1 | 1701 | B | 10 | 300 |  |  | 0
155-2 | 1702 | B | 10 | 300 |  |  | 0
155-3 | 1703 | B | 8 | 250 |  |  | 0
155-4 | 1703 | B | 8 | 250 |  |  | 0
VAV-1.55 |  |  |  | 1100 |  | 0 | 0
179-1 | 1306 | B | 6 | 75 |  |  | 0
179-2 | 1307 | B | 6 | 50 |  |  | 0
179-3 | 1308 | B | 6 | 50 |  |  | 0
179-4 | 1309 | B | 8 | 125 |  |  | 0
179-5 | 1309 | B | 8 | 125 |  |  | 0
179-6 | 1309 | B | 8 | 125 |  |  | 0
179-7 | 1309 | B | 8 | 125 |  |  | 0
179-8 | 1309 | B | 8 | 150 |  |  | 0
179-9 | 1309 | B | 8 | 150 |  |  | 0
179-10 | 1309 | B | 8 | 150 |  |  | 0
179-11 | 1309 | B | 8 | 150 |  |  | 0
VAV-1.79 |  |  |  | 1275 |  |  | 0
180-1 | 1311 | B | 10X8 | 300 |  |  | 0
VAV-1.80 |  |  |  | 300 |  | 0 | 0

## AHU-9 SGRD (4)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: AHU-9 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
181-1 | 1300B | B | 8 | 175 |  |  | 0
181-2 | 1321 | B | 6 | 50 |  |  | 0
181-3 | CORRIDOR | B | 8 | 125 |  |  | 0
181-4 | CORRIDOR | B | 8 | 125 |  |  | 0
181-5 | CORRIDOR | B | 8 | 125 |  |  | 0
VAV-1.81 |  |  |  | 600 |  | 0 | 0
182-1 | 1301 | B | 8 | 125 |  |  | 0
182-2 | 1301 | B | 8 | 125 |  |  | 0
VAV-1.82 |  |  |  | 250 |  | 0 | 0
183-1 | 1312 | B | 8 | 150 |  |  | 0
183-2 | 1312 | B | 8 | 175 |  |  | 0
183-3 | 1312 | B | 8 | 150 |  |  | 0
183-4 | 1312 | B | 8 | 175 |  |  | 0
VAV-1.83 |  |  |  | 650 |  | 0 | 0
184-1 | 1317 | B | 8 | 150 |  |  | 0
184-2 | 1317 | B | 8 | 150 |  |  | 0
184-3 | 1317 | B | 8 | 150 |  |  | 0
184-4 | 1317 | B | 8 | 150 |  |  | 0
184-5 | 1317 | B | 8 | 150 |  |  | 0
184-6 | 1317 | B | 8 | 150 |  |  | 0
VAV-1.84 |  |  |  | 900 |  | 0 | 0
185-1 | 1305 | B | 6 | 100 |  |  | 0
185-2 | 1300A | B | 8 | 200 |  |  | 0
185-3 | 1300A | B | 8 | 200 |  |  | 0
185-4 | 1304 | B | 6 | 100 |  |  | 0
185-5 | 1303 | B | 6 | 100 |  |  | 0
VAV-1.85 |  |  |  | 700 |  | 0 | 0

## AHU-9 SGRD (5)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: AHU-9 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
186-1 | 1316 | B | 8 | 150 |  |  | 0
186-2 | 1316 | B | 8 | 125 |  |  | 0
186-3 | 1316 | B | 8 | 150 |  |  | 0
186-4 | 1316 | B | 8 | 125 |  |  | 0
186-5 | 1316 | B | 8 | 150 |  |  | 0
186-6 | 1316 | B | 8 | 125 |  |  | 0
VAV-1.86 |  |  |  | 825 |  | 0 | 0
187-1 | 1313 | B | 8 | 150 |  |  | 0
187-2 | 1315 | B | 8 | 150 |  |  | 0
187-3 | 1315 | B | 8 | 125 |  |  | 0
VAV-1.87 |  |  |  | 425 |  | 0 | 0
188-1 | 1302 | B | 8 | 150 |  |  | 0
188-2 | 1302 | B | 8 | 150 |  |  | 0
188-3 | 1302 | B | 8 | 150 |  |  | 0
188-4 | 1302 | B | 8 | 150 |  |  | 0
188-5 | 1302 | B | 8 | 150 |  |  | 0
188-6 | 1302 | B | 8 | 150 |  |  | 0
VAV-1.88 |  |  |  | 900 |  | 0 | 0
189-1 | RECPT | C | 8 | 200 |  |  | 0
VAV-1.89 |  |  |  | 200 |  | 0 | 0

## AHU-9 SGRD (6)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: AHU-9 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
186-1 | 1316 | B | 8 | 150 |  |  | 0
186-2 | 1316 | B | 8 | 125 |  |  | 0
186-3 | 1316 | B | 8 | 150 |  |  | 0
186-4 | 1316 | B | 8 | 125 |  |  | 0
186-5 | 1316 | B | 8 | 150 |  |  | 0
186-6 | 1316 | B | 8 | 125 |  |  | 0
VAV-1.86 |  |  |  | 825 |  | 0 | 0
187-1 | 1313 | B | 8 | 150 |  |  | 0
187-2 | 1315 | B | 8 | 150 |  |  | 0
187-3 | 1315 | B | 8 | 125 |  |  | 0
VAV-1.87 |  |  |  | 425 |  | 0 | 0
188-1 | 1302 | B | 8 | 150 |  |  | 0
188-2 | 1302 | B | 8 | 150 |  |  | 0
188-3 | 1302 | B | 8 | 150 |  |  | 0
188-4 | 1302 | B | 8 | 150 |  |  | 0
188-5 | 1302 | B | 8 | 150 |  |  | 0
188-6 | 1302 | B | 8 | 150 |  |  | 0
VAV-1.88 |  |  |  | 900 |  | 0 | 0
189-1 | RECPT | C | 8 | 200 |  |  | 0
VAV-1.89 |  |  |  | 200 |  | 0 | 0

## FPB's
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: Fan Powered Boxes
Asset | Area Served | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Min CFM | Design Fan + Heat CFM | Actual Fan + Heat CFM | Ak (max)
BUILDING A
FPB-1323 | 1323 | EXISTING |  | 950
BRASWELL
FPB-2605 | 2605 | EXISTING | 12 | 1350
FPB-2602 | 2602 | EXISTING | 12 | 1550
FPB-2601 | 2601 | EXISTING | 10 | 1300
FPB-2000 | 2000 | EXISTING |  | 1400
FPB-2129 | 2129 | EXISTING |  | 450
FPB-2401 | 2401 | EXISTING | 12 | 1500
FPB-2321 | 2321 | EXISTING |  | 700
FPB-2706A | 2706 | EXISTING | [8 empty] | NO GRD'S SHOWN
FPB-2706B | 2706 | EXISTING | [8 empty] | NO GRD'S SHOWN
Note on C7: NTAB: BILLINGSLEY ONLY
Note on J7: NTAB: Fan PLUS Heat CFM

## FPB SGRD (1)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: FPB's SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
BUILDING A | [6 empty] | #DIV/0!
1323-1 | 1325 | B | 8 | 175 |  |  | 0
1323-2 | 1324 | B | 8 | 175 |  |  | 0
1323-3 | 1323 | B |  | 125 |  |  | 0
1323-4 | 1319 | B | 8 | 175 |  |  | 0
1323-5 | 1323 | B |  | 125 |  |  | 0
1323-6 | 1320 | B | 8 | 175 |  |  | 0
FPB-1323 |  |  |  | 950 |  |  | 0
BRASWELL
2605-1 | 2605 | B | 12 | 300 |  |  | 0
2605-2 | 2605 | B | 12 | 300 |  |  | 0
2605-3 | 2010 | B | 8 | 150 |  |  | 0
2605-4 | 2605 | B | 12 | 300 |  |  | 0
2605-5 | 2605 | B | 12 | 300 |  |  | 0
FPB-2605 |  |  |  | 1350 |  | 0 | 0
2602-1 | 2602 | B | 12 | 300 |  |  | 0
2602-2 | 2602 | B | 12 | 300 |  |  | 0
2602-3 | CORRIDOR | B | 10 | 250 |  |  | 0
2602-4 | 2604 | B | 6 | 100 |  |  | 0
2602-5 | 2602 | B | 12 | 300 |  |  | 0
2602-6 | 2602 | B | 12 | 300 |  |  | 0
FPB-2602 |  |  |  | 1550 |  | 0 | 0
2601-1 | CORRIDOR | B | 10 | 250 |  |  | 0
2601-2 | 2601 | B | 14 | 400 |  |  | 0
2601-3 | CORRIDOR | B | 10 | 250 |  |  | 0
2601-4 | 2601 | B | 14 | 400 |  |  | 0
FPB-2601 |  |  |  | 1300 |  | 0 | 0

## FPB SGRD (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: FPB's SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
BRASWELL
2000-1 | 2000 | B | 10 | 200 |  |  | 0
2000-2 | RESTROOM | B | 10 | 200 |  |  | 0
2000-3 | RESTROOM | B | 10 | 200 |  |  | 0
2000-4 | 2000 | A | 12 | 400 |  |  | 0
2000-5 | 2000 | A | 12 | 400 |  |  | 0
FPB-2000 |  |  |  | 1400 |  | 0 | 0
2129-1 | 2129 | B | 10 | 250 |  |  | 0
2129-2 | 2132 | B | 10 | 200 |  |  | 0
FPB-2129 |  |  |  | 450 |  | 0 | 0
2401-1 | 2404 | B | 6 | 100 |  |  | 0
2401-2 | 2401 | B | 12 | 350 |  |  | 0
2401-3 | 2401 | B | 12 | 350 |  |  | 0
2401-4 | 2401 | B | 12 | 350 |  |  | 0
2401-5 | 2401 | B | 12 | 350 |  |  | 0
FPB-2401 |  |  |  | 1500 |  | 0 | 0
2321-1 | CORRIDOR | B |  | 200 |  |  | 0
2321-2 | 2321 | B |  | 100 |  |  | 0
2321-3 | 2321 | B |  | 400 |  |  | 0
FPB-2321 |  |  |  | 700 |  | 0 | 0

## F-1
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: F-1 |  |  | Area: TLT 251 (BUILDING A, AREA A)
Unit Data |  |  |  |  | Test Data
MFG |  | GREENHECK |  |  |  | Design | Actual
Model Num |  | SP-80-VG |  |  | CFM | 75
Serial Num |  |  |  |  | Fan RPM | 935
Type |  | CEILING |  |  | RL Voltage | 120
RL Amperage
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP | 0.3
Frame
Horsepower
Motor Rpm
Phase |  | 1
Voltage (rated) |  | 120
Amperage (rated)
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
-

## F-2
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: F-2 |  |  | Area: ELEC 228 (BUILDING A, AREA A)
Unit Data |  |  |  |  | Test Data
MFG |  | GREENHECK |  |  |  | Design | Actual
Model Num |  | SQ-99-VG |  |  | CFM | 500
Serial Num |  |  |  |  | Fan RPM | 1362
Type |  | INLINE |  |  | RL Voltage | 120
RL Amperage
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP | 0.5
Frame
Horsepower
Motor Rpm
Phase |  | 1
Voltage (rated) |  | 120
Amperage (rated)
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
-

## F-4
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: F-4 |  |  | Area: ELEC 195 (BUILDING A, AREA B)
Unit Data |  |  |  |  | Test Data
MFG |  | GREENHECK |  |  |  | Design | Actual
Model Num |  | SQ-99-VG |  |  | CFM | 500
Serial Num |  |  |  |  | Fan RPM | 1362
Type |  | INLINE |  |  | RL Voltage | 120
RL Amperage
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP | 0.5
Frame
Horsepower
Motor Rpm
Phase |  | 1
Voltage (rated) |  | 120
Amperage (rated)
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
-

## F-5
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: F-5 |  |  | Area: E.C. DATA 177 (BUILDING A, AREA B)
Unit Data |  |  |  |  | Test Data
MFG |  | GREENHECK |  |  |  | Design | Actual
Model Num |  | SQ-99-VG |  |  | CFM [1] | 500
Serial Num |  |  |  |  | Fan RPM | 1362
Type |  | INLINE |  |  | RL Voltage | 120
RL Amperage
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP | 0.5
Frame
Horsepower
Motor Rpm
Phase |  | 1
Voltage (rated) |  | 120
Amperage (rated)
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
F5-1 | 1320 | J | 10 | 250 |  |  | 0
F5-2 | 1324 | J | 10 | 275 |  |  | 0
F5-3 | 1319 | J | 10 | 250 |  |  | 0
F5-4 | 1325 | J | 10 | 275 |  |  | 0
|  |  |  | 1050 |  | 0 | 0
NOTES: | [1] DESIGN IS 500 CFM, GRILLE TOTAL IS 1050 PLUS 1 UNMARKED
-

## F-5 (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: F-5 (2) |  | Area: E.C. ELEC 1715 (BUILDING A, AREA B)
Unit Data |  |  | Test Data
MFG | GREENHECK |  |  | Design | Actual
Model Num | SQ-99-VG |  | CFM [1] | 500
Serial Num |  |  | Fan RPM | 1362
Type | INLINE |  | RL Voltage | 120
RL Amperage
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP | 0.5
Frame
Horsepower
Motor Rpm
Phase | 1
Voltage (rated) | 120
Amperage (rated)
Service Factor
-

## F-6
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: F-6 |  |  | Area: PRINT SHOP 245 (BUILDING A, AREA A)
Unit Data |  |  |  |  | Test Data
MFG |  | GREENHECK |  |  |  | Design | Actual
Model Num |  | G-095-VG |  |  | CFM | 800
Serial Num |  |  |  |  | Fan RPM | 1538
Type |  | CRE DNBLAST |  |  | RL Voltage | 120
RL Amperage
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP | 0.3
Frame
Horsepower
Motor Rpm
Phase |  | 1
Voltage (rated) |  | 120
Amperage (rated)
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
F6-1 | 1501 | J |  | 800 |  |  | 0
-

## HW VALVES (1)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: HW VALVES |  |  |  | Service: HOT WATER
Asset | Location | MFG | Model | Size | Type | Design GPM | Setting | Delta P | Final GPM | % to Design | RTU/AHU
VAV-1.1 | 1105 |  |  | 0.75 |  | 3.4 |  |  |  | 0 | RTU-3
VAV-1.2 | 1116 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-3
VAV-1.3 | 1113 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-3
VAV-1.4 | 1107 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-3
CAV-1.28 | 1101 |  |  | 0.75 |  | 3.8 |  |  |  | 0 | RTU-3
CAV-1.29 | 1101 |  |  | 0.75 |  | 2.9 |  |  |  | 0 | RTU-3
VAV-1.30 | 1102 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-3
VAV-1.31 | 1103 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-3
VAV-1.32 | 1104 |  |  | 0.75 |  | 2.4 |  |  |  | 0 | RTU-3
VAV-1.33 | 1111 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-3
VAV-1.34 | 1110 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-3
VAV-1.35 | 1108 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-3
VAV-1.5 | 1214 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.6 | 1215 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.7 | 1213 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.8 | 1206 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.9 | 1205 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.10 | 1202 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.39 | 1211 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.40 | 1216 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-5
VAV-1.41 | 1218 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-5
VAV-1.42 | 1219 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-5
VAV-1.44 | 1217 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.45 | 1210 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-5
VAV-1.46 | 1204 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-5
VAV-1.11 | 1513 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.12 | 1518 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.13 | CORRIDOR |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-6
VAV-1.14 | 1511 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.15 | 1404 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.16 | 1401 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.17 | 1406 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6

## HW VALVES (2)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: HW VALVES |  |  |  | Service: HOT WATER
Asset | Location | MFG | Model | Size | Type | Design GPM | Setting | Delta P | Final GPM | % to Design | RTU/AHU
VAV-1.18 | 1411 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.19 | 1408 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.20 | 1412 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.21 | 1417 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.22 | 1414 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.23 | 1418 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.24 | 1424 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.25 | 1425 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.26 | 1423 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.27 | 1501 |  |  | 0.5 |  | 1.7 |  |  |  | 0 | RTU-6
VAV-1.36 | 1501 |  |  | 0.5 |  | 1.2 |  |  |  | 0 | RTU-6
VAV-1.37 | 1403 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.38 | 1402 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-6
VAV-1.43 | 1720 |  |  | 0.5 |  | 1.3 |  |  |  | 0 | AHU-9
VAV-1.47 | 1718 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.48 | 1717 |  |  | 0.5 |  | 1.3 |  |  |  | 0 | AHU-9
VAV-1.49 | 1714 |  |  | 0.5 |  | 1.3 |  |  |  | 0 | AHU-9
VAV-1.50 | 1713 |  |  | 0.5 |  | 1.4 |  |  |  | 0 | AHU-9
VAV-1.51 | 1709 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.52 | 1705 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.53 | 1706 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.54 | 1710 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.55 | 1702 |  |  | 0.5 |  | 1.3 |  |  |  | 0 | AHU-9
VAV-1.79 | 1309 |  |  | 0.5 |  | 1.5 |  |  |  | 0 | AHU-9
VAV-1.80 | 1311 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.81 | 1321 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.82 | 1301 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.83 | 1312 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.84 | 1317 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | AHU-9
VAV-1.85 | 1303 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.86 | 1316 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.87 | 1315 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9
VAV-1.88 | 1302 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | AHU-9
VAV-1.89 | RECPT |  |  | 0.5 |  | 0.3 |  |  |  | 0 | AHU-9

## HW VALVES (3)
National TAB
Project: SPCC OCH Campus Renovation
Address: 4209 Old Charlotte Hwy Monroe, NC 28110
Asset: HW VALVES |  |  |  | Service: HOT WATER
Asset | Location | MFG | Model | Size | Type | Design GPM | Setting | Delta P | Final GPM | % to Design | RTU/AHU
VAV-1.56 | 1338 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-7
VAV-1.57 | 1337 |  |  | 0.5 |  | 1.2 |  |  |  | 0 | RTU-7
VAV-1.58 | 1339 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-7
VAV-1.59 | 1341 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-7
VAV-1.60 | 1340 |  |  | 0.5 |  | 1.2 |  |  |  | 0 | RTU-7
VAV-1.61 | 1336 |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-7
VAV-1.62 | 1327 |  |  | 0.5 |  | 1.3 |  |  |  | 0 | RTU-7
VAV-1.63 | 1330 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-7
VAV-1.64 | 1329 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-7
VAV-1.65 | 1334 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-7
VAV-1.66 | 1333 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-7
VAV-1.67 | 1328 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-7
VAV-1.68 | 1729 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-8
VAV-1.69 | 1342 |  |  | 0.5 |  | 1.3 |  |  |  | 0 | RTU-8
VAV-1.70 | 1728 |  |  | 0.5 |  | 1.8 |  |  |  | 0 | RTU-8
VAV-1.71 | 1724 |  |  | 0.5 |  | 1.2 |  |  |  | 0 | RTU-8
VAV-1.72 | 1727 |  |  | 0.5 |  | 0.3 |  |  |  | 0 | RTU-8
VAV-1.73 | CORRIDOR |  |  | 0.5 |  | 1.1 |  |  |  | 0 | RTU-8
VAV-1.74 | 1725 |  |  | 0.5 |  | 1.2 |  |  |  | 0 | RTU-8
VAV-1.75 | 1723 |  |  | 0.5 |  | 1.2 |  |  |  | 0 | RTU-8
VAV-1.76 | 1326 |  |  | 0.5 |  | 1.3 |  |  |  | 0 | RTU-8
VAV-1.77 | 1722 |  |  | 0.5 |  | 1.3 |  |  |  | 0 | RTU-8
VAV-1.78 | 1721 |  |  | 0.5 |  | 1.4 |  |  |  | 0 | RTU-8