## RTU-1
National TAB
Project: 5.11 Tactical
Address: 2304 Sir Barton Way, Ste 130 Lexington, KY
Asset: RTU-1 (EXISTING)
Unit Data |  | Test Data
Manufacturer | CARRIER |  | Design | Actual
Model Num | 48FCDM12 | SF CFM | 3840
Serial Num |  | SF RPM
Configuration | VERTICAL | RA CFM | 3040
Num OA Filters |  | OA CFM | 800
OA Filter Size |  | RL VOLTAGE | 208-230
Num PreFilter |  | RL AMPERAGE
PreFilter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase | 3 | DX Coil PD * |  | *
Rated Voltage | 208-230 | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor

## RTU-1 SUPPLY
National TAB
Project: 5.11 Tactical
Address: 2304 Sir Barton Way, Ste 130 Lexington, KY
Asset: RTU-1 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
1-1 | BOH HALL | SD-2 | 8X6 | 200 |  |  | 0
1-2 | OFFICE | SD-3 | 24X24 | 50 |  |  | 0
1-3 | OFFICE | SD-3 | 24X24 | 50 |  |  | 0
1-4 | RESTROOM | SD-3 | 24X24 | 50 |  |  | 0
1-5 | RESTROOM | SD-3 | 24X24 | 50 |  |  | 0
1-6 | BOH | SD-2 | 8X6 | 150 |  |  | 0
1-7 | BOH | SD-2 | 8X6 | 150 |  |  | 0
1-8 | BOH | SD-2 | 8X6 | 175 |  |  | 0
1-9 | SALES | SD-1 | 14X6 | 175 |  |  | 0
1-10 | SALES | SD-1 | 14X6 | 310 |  |  | 0
1-11 | SALES | SD-1 | 14X6 | 310 |  |  | 0
1-12 | SALES | SD-1 | 14X6 | 310 |  |  | 0
1-13 | SALES | SD-1 | 14X6 | 310 |  |  | 0
1-14 | SALES | SD-1 | 14X6 | 310 |  |  | 0
1-15 | SALES | SD-1 | 14X6 | 310 |  |  | 0
1-16 | SALES | SD-1 | 14X6 | 310 |  |  | 0
1-17 | SALES | SD-1 | 14X6 | 310 |  |  | 0
1-18 | SALES | SD-1 | 14X6 | 310 |  |  | 0
RTU-1 |  |  |  | 3840 |  | 0 | 0

## RTU-2
National TAB
Project: 5.11 Tactical
Address: 2304 Sir Barton Way, Ste 130 Lexington, KY
Asset: RTU-2 (EXISTING)
Unit Data |  | Test Data
Manufacturer | CARRIER |  | Design | Actual
Model Num | 48FCDM12 | SF CFM | 3850
Serial Num |  | SF RPM
Configuration | VERTICAL | RA CFM | 3050
Num OA Filters |  | OA CFM | 800
OA Filter Size |  | RL VOLTAGE | 208-230
Num PreFilter |  | RL AMPERAGE
PreFilter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase | 3 | DX Coil PD * |  | *
Rated Voltage | 208-230 | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor

## RTU-2 SUPPLY
National TAB
Project: 5.11 Tactical
Address: 2304 Sir Barton Way, Ste 130 Lexington, KY
Asset: RTU-2 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
2-1 | HALL | SD-2 | 8X6 | 150 |  |  | 0
2-2 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-3 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-4 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-5 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-6 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-7 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-8 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-9 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-10 | SALES | SD-1 | 14X6 | 370 |  |  | 0
2-11 | SALES | SD-1 | 14X6 | 370 |  |  | 0
|  |  |  | 3850 |  | 0 | 0

## EF-1
National TAB
Project: 5.11 Tactical
Address: 2304 Sir Barton Way, Ste 130 Lexington, KY
Asset: EF-1 (EXISTING) |  | Area: RESTROOM
Unit Data |  |  | Test Data
MFG | EXISTING |  |  | Design | Actual
Model Num | EXISTING |  | CFM | 70
Serial Num |  |  | Fan RPM
Type | CEILING |  | RL Voltage | 120
RL Amperage
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP
Frame
Horsepower
Motor Rpm
Phase | 1
Voltage (rated) | 120
Amperage (rated)
Service Factor
-

## EF-2
National TAB
Project: 5.11 Tactical
Address: 2304 Sir Barton Way, Ste 130 Lexington, KY
Asset: EF-2 (EXISTING) |  | Area: RESTROOM
Unit Data |  |  | Test Data
MFG | EXISTING |  |  | Design | Actual
Model Num | EXISTING |  | CFM | 70
Serial Num |  |  | Fan RPM
Type | CEILING |  | RL Voltage | 120
RL Amperage
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP
Frame
Horsepower
Motor Rpm
Phase | 1
Voltage (rated) | 120
Amperage (rated)
Service Factor
-