## RTU-1A
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: RTU-1A
Unit Data |  | Test Data
Manufacturer | CARRIER |  | Design | Actual
Model Num | 50FC-M28B2A6-3F2A0 | SF CFM | 10000
Serial Num |  | SF RPM | 1657
Configuration | VERTIAL | RA CFM | 8000
|  | OA CFM | 2000
|  | RL VOLTAGE | 460
Num Return Filter | 9 | RL AMPERAGE | 3.5
Final Return Size | 20x25x2 | OA Damper Position
|  | Brake Horsepower | 4.3
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower | 10 | Fan Discharge SP
Motor RPM |  | Fan Total SP | 0.6
Phase | 3 | DX Coil PD * |  | *
Rated Voltage | 460 | Pre Filter PD |  | *combined
Rated Amperage | 3.5 | Total ESP | 0.5
Service Factor

## RTU-1A SGRD
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: RTU-1A SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
1A-1 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1A-2 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1A-3 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1A-4 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1A-5 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1A-6 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1A-7 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1A-8 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
|  |  |  | 10000 |  | 0 | 0

## RTU-1B
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: RTU-1B
Unit Data |  | Test Data
Manufacturer | CARRIER |  | Design | Actual
Model Num | 50FC-M28B2A6-3F2A0 | SF CFM | 10000
Serial Num |  | SF RPM | 1657
Configuration | VERTIAL | RA CFM | 8000
|  | OA CFM | 2000
|  | RL VOLTAGE | 460
Num Return Filter | 9 | RL AMPERAGE | 3.5
Final Return Size | 20x25x2 | OA Damper Position
|  | Brake Horsepower | 4.3
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower | 10 | Fan Discharge SP
Motor RPM |  | Fan Total SP | 0.6
Phase | 3 | DX Coil PD * |  | *
Rated Voltage | 460 | Pre Filter PD |  | *combined
Rated Amperage | 3.5 | Total ESP | 0.5
Service Factor

## RTU-1B SGRD
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: RTU-1B SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
1B-1 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1B-2 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1B-3 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1B-4 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1B-5 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1B-6 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1B-7 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
1B-8 | 306 | SG-3 | 24X12 | 1250 |  |  | 0
|  |  |  | 10000 |  | 0 | 0

## AHU-2
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: AHU-2 |  | Area: AUX GYM
Unit Data |  |  | Test Data
Manufacurer | CARRIER |  |  | Design | Actual
Model Number | FV4CNB006L00 |  | SF CFM | 1635
Serial Number |  |  | SF RPM
Configuration |  |  | RA CFM | 1035
No. Pre Filters / Size |  |  | OA CFM | 600
|  |  | RL VOLTAGE | 208
|  |  | RL AMPERAGE | 6.8
Motor B.H.P.
Motor Data |  |  | Performance Data
Motor MFG |  |  |  | Design | Actual
Frame |  |  | Suction S.P.
HP | 0.75 |  | Discharge S.P.
RPM |  |  | Total SP
Phase | 1 |  | CW Coil P.D.
Volts | 208 |  | HW Coil P.D.
Amps | 6.8 |  | Final Filters P.D.
Heat Wheel P.D.
Pre Filters P.D.
|  |  | Total ESP | 0.5

## AHU-2 SGRD
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: AHU-2 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
2-1 | 315 | SG-4 | 24X6 | 545 |  |  | 0
2-2 | 315 | SG-4 | 24X6 | 545 |  |  | 0
2-3 | 315 | SG-4 | 24X6 | 545 |  |  | 0
|  |  |  | 1635 |  |  | 0

## AHU-3
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: AHU-3 |  | Area: AUX GYM
Unit Data |  |  | Test Data
Manufacurer | CARRIER |  |  | Design | Actual
Model Number | 40RUAA25T1A6-0A0A0 |  | SF CFM | 8000
Serial Number |  |  | SF RPM | 851
Configuration |  |  | RA CFM | 5900
No. Pre Filters / Size |  |  | OA CFM | 2100
|  |  | RL VOLTAGE | 460
|  |  | RL AMPERAGE | 9.1
|  |  | Motor B.H.P. | 4.0
Motor Data |  |  | Performance Data
Motor MFG |  |  |  | Design | Actual
Frame |  |  | Suction S.P.
HP |  |  | Discharge S.P.
RPM |  |  | Total SP | 0.67
Phase | 3 |  | CW Coil P.D.
Volts | 460 |  | HW Coil P.D.
Amps | 9.1 |  | Final Filters P.D.
Heat Wheel P.D.
Drive Data |  |  | Pre Filters P.D.
Motor Sheave Size |  |  | Total ESP | 0.5
Motor Bore Size
Fan Sheave Size
Fan Bore Size
Belt CL Distance
No of Belts
Belt Size

## AHU-3 SGRD
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: AHU-3 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
3-1 | 315 | SG-1 | 36X12 | 1600 |  |  | 0
3-2 | 315 | SG-1 | 36X12 | 1600 |  |  | 0
3-3 | 315 | SG-1 | 36X12 | 1600 |  |  | 0
3-4 | 315 | SG-1 | 36X12 | 1600 |  |  | 0
3-5 | 315 | SG-1 | 36X12 | 1600 |  |  | 0
|  |  |  | 8000 |  | 0 | 0

## HW Circuit Setter
National TAB
Project: Madeira HS Gym HVAC Repl (Cincinnati, OH)
Address: 7465 Loannes Dr Cincinnati, OH 45243
Asset: HW CIRCUIT SETTERS |  |  |  | Service: HOT WATER
Asset | Location | MFG | Model | Size | Type | Design GPM | Setting | Delta P | Final GPM | % to Design
HWC-2 | AHU-2 |  |  |  |  | 34.5 |  | 10
HWC-3 | AHU-3 |  |  |  |  | 7.5 |  | 10
[6 empty] | 42 |  |  | 0