## RTU-1
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: RTU-1 (EXISTING)
Unit Data |  | Test Data
Manufacturer |  |  | Design | Actual
Model Num |  | SF CFM | 4975
Serial Num |  | SF RPM
Configuration | VERTICAL | RA CFM | 4095
Num OA Filters |  | OA CFM | 880
OA Filter Size |  | RL VOLTAGE
Num PreFilter |  | RL AMPERAGE
PreFilter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-1 GRD
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: AHU-1 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
1-1 | 127 | SD-2 | 8 | 125 |  |  | 0
1-2 | 126 | SD-2 | 8 | 125 |  |  | 0
1-3 | 101 | SD-3 | 10 | 300 |  |  | 0
1-4 | 101 | SD-3 | 10 | 300 |  |  | 0
1-5 | 101 | SD-3 | 10 | 300 |  |  | 0
1-6 | 101 | SL-1 | 10 | 275 |  |  | 0
1-7 | 101 | SL-1 | 10 | 275 |  |  | 0
1-8 | 101 | SL-1 | 10 | 275 |  |  | 0
1-9 | 101 | SL-1 | 10 | 275 |  |  | 0
1-10 | 124 | SD-1 | 6 | 50 |  |  | 0
1-11 | 125 | SD-2 | 8 | 175 |  |  | 0
1-12 | 128 | SD-2 | 8 | 125 |  |  | 0
1-13 | 129 | SD-2 | 8 | 125 |  |  | 0
1-14 | 130 | SD-2 | 8 | 125 |  |  | 0
1-15 | 131 | SD-2 | 8 | 125 |  |  | 0
1-16 | 101 | SL-1 | 10 | 275 |  |  | 0
1-17 | 101 | SL-1 | 10 | 275 |  |  | 0
1-18 | 101 | SD-3 | 10 | 300 |  |  | 0
1-19 | 101 | SL-1 | 10 | 275 |  |  | 0
1-20 | 101 | SL-1 | 10 | 275 |  |  | 0
1-21 | 101 | SL-1 | 10 | 275 |  |  | 0
1-22 | 132 | SD-2 | 8 | 125 |  |  | 0
1-23 | 133 | SD-2 | 8 | 200 |  |  | 0
RTU-1 |  |  |  | 4975 |  | 0 | 0

## RTU-2
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: RTU-2 (EXISTING)
Unit Data |  | Test Data
Manufacturer |  |  | Design | Actual
Model Num |  | SF CFM | 5000
Serial Num |  | SF RPM
Configuration | VERTICAL | RA CFM | 4400
Num OA Filters |  | OA CFM | 600
OA Filter Size |  | RL VOLTAGE
Num PreFilter |  | RL AMPERAGE
PreFilter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-2 GRD
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: AHU-2 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
2-1 | 120 | SD-4 | 6 | 100 |  |  | 0
2-2 | 026 | SD-1 | 6 | 50 |  |  | 0
2-3 | 121 | SD-4 | 6 | 100 |  |  | 0
2-4 | 118 | SD-3 | 10 | 275 |  |  | 0
2-5 | 118 | SD-3 | 10 | 300 |  |  | 0
2-6 | 118 | SD-3 | 10 | 300 |  |  | 0
2-7 | 102 | SL-1 | 8 | 200 |  |  | 0
2-8 | 102 | SL-1 | 8 | 200 |  |  | 0
2-9 | 102 | SL-1 | 8 | 200 |  |  | 0
2-10 | 102 | SL-1 | 8 | 200 |  |  | 0
2-11 | 118 | SL | 8 | 275 |  |  | 0
2-12 | 118 | SL | 8 | 275 |  |  | 0
2-13 | 118 | SD-3 | 10 | 275 |  |  | 0
2-14 | 125 | SL-2 | 10 | 275 |  |  | 0
2-15 | 125 | SL-2 | 10 | 275 |  |  | 0
2-16 | 125 | SD-3 | 10 | 300 |  |  | 0
2-17 | 125 | SD-3 | 10 | 300 |  |  | 0
2-18 | 125 | SL-2 | 10 | 275 |  |  | 0
2-19 | 125 | SL-1 | 10 | 275 |  |  | 0
2-20 | 125 | SL-2 | 10 | 275 |  |  | 0
2-21 | 125 | SL-1 | 10 | 275 |  |  | 0
RTU-2 |  |  |  | 5000 |  | 0 | 0

## RTU-3
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: RTU-3 (EXISTING)
Unit Data |  | Test Data
Manufacturer |  |  | Design | Actual
Model Num |  | SF CFM | 2000
Serial Num |  | SF RPM
Configuration | VERTICAL | RA CFM | 1850
Num OA Filters |  | OA CFM | 150
OA Filter Size |  | RL VOLTAGE
Num PreFilter |  | RL AMPERAGE
PreFilter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-3 GRD
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: AHU-3 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
3-1 | 027 | SR | 10 | 400 |  |  | 0
3-2 | 122 | SD-5 | 8 | 200 |  |  | 0
3-3 | 115 | SD4 | 6 | 50 |  |  | 0
3-4 | 113 | SD-5 | 8 | 150 |  |  | 0
3-5 | 111 | SD-1 | 6 | 100 |  |  | 0
3-6 | 116 | SD-2 | 8 | 200 |  |  | 0
3-7 | 116 | SD-2 | 8 | 200 |  |  | 0
3-8 | 112 | SD-2 | 8 | 200 |  |  | 0
3-9 | 109 | SD-3 | 10 | 250 |  |  | 0
3-10 | 109 | SD-3 | 10 | 250 |  |  | 0
RTU-3 |  |  |  | 2000 |  | 0 | 0

## RTU-4
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: RTU-4 (EXISTING)
Unit Data |  | Test Data
Manufacturer |  |  | Design | Actual
Model Num |  | SF CFM | 1400
Serial Num |  | SF RPM
Configuration | VERTICAL | RA CFM | 1150
Num OA Filters |  | OA CFM | 250
OA Filter Size |  | RL VOLTAGE
Num PreFilter |  | RL AMPERAGE
PreFilter Size |  | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG |  |  | Design | Actual
Frame |  | Fan Suction SP
Horsepower |  | Fan Discharge SP
Motor RPM |  | Fan Total SP
Phase |  | DX Coil PD * |  | *
Rated Voltage |  | Pre Filter PD |  | *combined
Rated Amperage |  | Total ESP
Service Factor
Drive Data
Motor Sheave Size / Bore
Fan Sheave Size / Bore
Belt CL Distance
No. Belts / Size

## RTU-4 GRD
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: AHU-4 SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
4-1 | 110 | SD-2 | 8 | 200 |  |  | 0
4-2 | 110 | SD-2 | 8 | 200 |  |  | 0
4-3 | 110 | SD-2 | 8 | 200 |  |  | 0
4-4 | 106 | SD-2 | 8 | 200 |  |  | 0
4-5 | 105 | SD-2 | 8 | 200 |  |  | 0
4-6 | 104 | SD-2 | 8 | 200 |  |  | 0
4-7 | 103 | SD-2 | 8 | 200 |  |  | 0
|  |  |  | 1400 |  | 0 | 0

## EF-1
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: EF-1 |  | Area: 140
Unit Data |  |  | Test Data
MFG | GREENHECK |  |  | Design | Actual
Model Num | SP-A250 |  | CFM | 244
Serial Num |  |  | Fan RPM | 1000
Type | CEILING |  | RL Voltage | 115
|  |  | RL Amperage | 0.56
Motor Data |  |  | Suction ESP
Motor MFG |  |  | Total ESP | 0.282
Frame
Horsepower | 83W
Motor Rpm
Phase | 1
Voltage (rated) | 115
Amperage (rated) | 0.56
Service Factor
-

## EF-2
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: Exhaust Fan |  |  | Area: 120
Unit Data |  |  |  |  | Drive Data
MFG |  |  |  |  | Motor Sheave Size
Model Num |  |  |  |  | Motor Bore Size
Serial Num |  |  |  |  | Fan Sheave Size
Type |  | EXISTING |  |  | Fan Bore Size
Belt CL Distance
Motor Data |  |  |  |  | No of Belts
Motor MFG |  |  |  |  | Belt Size
Frame
Horsepower |  |  |  |  | Test Data
Motor Rpm | [5 empty] | Design | Actual
Phase |  |  |  |  | CFM | 300
Voltage (rated) |  |  |  |  | Fan RPM
Amperage (rated) |  |  |  |  | RL Voltage
Service Factor |  |  |  |  | RL Amperage
Suction ESP
Total ESP
Brake Horse Power
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
E2-1 | 120 | EG | 8 | 150 |  |  | 0
E2-2 | 121 | EG | 8 | 150 |  |  | 0
|  |  |  | 300 |  | 0 | 0
-

## EF-3
National TAB
Project: Joseph Airport Hyundai Reno
Address: 1220 W National Rd Vandalia, OH 45377
Asset: EF-3 |  |  | Area: 113
Unit Data |  |  |  |  | Drive Data
MFG |  |  |  |  | Motor Sheave Size
Model Num |  |  |  |  | Motor Bore Size
Serial Num |  |  |  |  | Fan Sheave Size
Type |  | EXISTING |  |  | Fan Bore Size
Belt CL Distance
Motor Data |  |  |  |  | No of Belts
Motor MFG |  |  |  |  | Belt Size
Frame
Horsepower |  |  |  |  | Test Data
Motor Rpm | [5 empty] | Design | Actual
Phase |  |  |  |  | CFM | 320
Voltage (rated) |  |  |  |  | Fan RPM
Amperage (rated) |  |  |  |  | RL Voltage
Service Factor |  |  |  |  | RL Amperage
Suction ESP
Total ESP
Brake Horse Power
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
E3-1 | 113 | EG-1 | 8 | 170 |  |  | 0
E3-2 | 115 | EG-1 | 6 | 75 |  |  | 0
E3-3 | 113 RR | EG-1 | 6 | 75 |  |  | 0
|  |  |  | 320 |  | 0 | 0
-