## Change Order Request Summary
|  |  | APPROVER: | APPROVER:
NOTES:
CONTRACTOR CHANGE ORDER REQUEST SUMMARY
Project Name: |  | Walgreens HVAC Planned Program |  |  |  |  | Change Order NO#: | 1
Contract NO#: |  | 4200247053 |  |  |  |  | Date: | 2023-01-19
Contractor Name: |  | National TAB |  |  |  |  | FY: | 2023
Walgreens Store #: |  | 4708
Description of Change:
Additional cost to return to store #4708 to rebalance RTU5, EFs 1,5. Retake store pressure, temperature and humidity readings. Previous visit, damper for diffuser 2 on RTU-5 was damaged and needs to be repaired. EF-1 was not operational. EF-5 did not have a speed controller installed and the ductwork was not connected. IC is in the process of correcting and we will schedule once confirmed as completed.
| Item | Detail |  | Cost | Qty | Subtotal | Taxes | Total
| Labor | Return trip |  | 2200 | 1 | 2200 | 0 | 2200
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 1 | 0 | 0 | 0
| Total General Contractor Change Order Request Amount = |  |  |  |  | 2200 | 0 | 2200
Labor
Material
Material
Material
Equipment
Shipping
Taxes
Overhead