## SCU-8-1
National TAB
Project: CW 2999 - Shell Building
Address: 2999 Olympus Blvd Dallas, TX
Asset: SCU-8-1
Unit Data |  | Test Data
Manufacturer | DAIKIN |  | Design | Actual
Model Num | SWP099HSH | SF CFM | 32000
Serial Num | FB0U210602250 | SF RPM | 1014
Configuration | HORIZONTAL | RA CFM | 28000
|  | OA CFM | 4000
|  | RL VOLTAGE | 460
Num PreFilter | 20 | RL AMPERAGE | 57
PreFilter Size | 24X24X4 | OA Damper Position
Brake Horsepower
Motor Data |  | Performance Data
Motor MFG | BALDOR |  | Design | Actual
Frame | 326T | Fan Suction SP
Horsepower | 50 | Fan Discharge SP
Motor RPM | 1775 | Fan Total SP | 4.21
Phase | 3 | CX Coil PD * |  | *
Rated Voltage | 460 | Pre Filter PD |  | *combined
Rated Amperage | 57 | Total ESP | 3
Service Factor | 1
Drive Data
Motor Sheave Size / Bore | 3B94SK / 2.125
Fan Sheave Size / Bore | 3B5V160 / 2.4375
Belt CL Distance | 47.5
No. Belts / Size | 3 / BX133
NOTES: | Design values are for 100%
Outside Air is supplied by a VAV from OAHU.

## FPB - PARALLEL
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: Parallel Fan Powered Boxes
Asset | Area Served | Address | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Min CFM | Design Fan + Heat CFM | Actual Fan + Heat CFM | Ak (max)
FPB-8-1 | 840A |  |  | 16 | 2000 |  | 500 |  | 1400
FPB-8-2 | 800B |  |  | 14 | 1530 |  | 383 |  | 1071
FPB-8-3 | 840 |  |  | 14 | 1500 |  | 375 |  | 1050
FPB-8-4 | 840B |  |  | 14 | 1500 |  | 375 |  | 1050
FPB-8-5 | 826 |  |  | 10 | 660 |  | 165 |  | 462
FPB-8-6 | 825 |  |  | 12 | 1280 |  | 320 |  | 896
FPB-8-7 | 820 |  |  | 8 | 540 |  | 135 |  | 378
FPB-8-8 | 819 |  |  | 10 | 930 |  | 233 |  | 651
FPB-8-9 | 816 |  |  | 12 | 1020 |  | 255 |  | 714
FPB-8-10 | 801C |  |  | 12 | 1110 |  | 278 |  | 777
FPB-8-11 | 850 |  |  | 10 | 850 |  | 213 |  | 595
FPB-8-12 | 864 |  |  | 10 | 935 |  | 234 |  | 655
FPB-8-13 | 864 |  |  | 14 | 1540 |  | 385 |  | 1078
FPB-8-14 | 895 |  |  | 14 | 1530 |  | 383 |  | 1071
FPB-8-15 | 895 |  |  | 12 | 1440 |  | 360 |  | 1008
FPB-8-16 | 890A |  |  | 14 | 1605 |  | 401 |  | 1124
Note on C7: NTAB: BILLINGSLEY ONLY
Note on J7: NTAB: Fan PLUS Heat CFM

## FPB SGRD (1)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: FPB SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F81-1 | 840A | F | 16X6 | 255 |  |  | 0
F81-2 | 840A | F | 16X6 | 255 |  |  | 0
F81-3 | 840A | F | 16X6 | 255 |  |  | 0
F81-4 | 840A | F | 16X6 | 255 |  |  | 0
F81-5 | 840A | F | 16X6 | 255 |  |  | 0
F81-6 | 840A | F | 16X6 | 255 |  |  | 0
F81-7 | 840A | F | 16X6 | 235 |  |  | 0
F81-8 | 840A | F | 16X6 | 235 |  |  | 0
FPB-8-1 |  |  |  | 2000 |  | 0 | 0
F82-1 | 800B | F | 16X6 | 255 |  |  | 0
F82-2 | 800B | F | 16X6 | 255 |  |  | 0
F82-3 | 800B | F | 16X6 | 255 |  |  | 0
F82-4 | 800B | F | 16X6 | 255 |  |  | 0
F82-5 | 800B | F | 16X6 | 255 |  |  | 0
F82-6 | 800B | F | 16X6 | 255 |  |  | 0
FPB-8-2 |  |  |  | 1530 |  | 0 | 0
F83-1 | 840 | F | 16X6 | 245 |  |  | 0
F83-2 | 840 | F | 16X6 | 245 |  |  | 0
F83-3 | 840 | F | 16X6 | 245 |  |  | 0
F83-4 | 840 | F | 16X6 | 255 |  |  | 0
F83-5 | 840 | F | 16X6 | 255 |  |  | 0
F83-6 | 840 | F | 16X6 | 255 |  |  | 0
FPB-8-3 |  |  |  | 1500 |  | 0 | 0

## FPB SGRD (2)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: FPB SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F84-1 | 840B | F | 16X6 | 255 |  |  | 0
F84-2 | 840B | F | 16X6 | 255 |  |  | 0
F84-3 | 840B | F | 16X6 | 255 |  |  | 0
F84-4 | 840B | F | 16X6 | 245 |  |  | 0
F84-5 | 840B | F | 16X6 | 245 |  |  | 0
F84-6 | 840B | F | 16X6 | 245 |  |  | 0
FPB-8-4 |  |  |  | 1500 |  | 0 | 0
F85-1 | 826 | C | 10 | 165 |  |  | 0
F85-2 | 826 | C | 10 | 165 |  |  | 0
F85-3 | 826 | C | 10 | 165 |  |  | 0
F85-4 | 826 | C | 10 | 165 |  |  | 0
FPB-8-5 |  |  |  | 660 |  | 0 | 0
F86-1 | 822 | C | 10 | 180 |  |  | 0
F86-2 | 822 | C | 10 | 180 |  |  | 0
F86-3 | 823 | C | 10 | 180 |  |  | 0
F86-4 | 823 | C | 10 | 180 |  |  | 0
F86-5 | 824 | C | 10 | 180 |  |  | 0
F86-6 | 824 | C | 10 | 180 |  |  | 0
F86-7 | 825 | C | 10 | 200 |  |  | 0
FPB-8-6 |  |  |  | 1280 |  | 0 | 0
F87-1 | 821 | C | 10 | 260 |  |  | 0
F87-2 | 820 | C | 8 | 90 |  |  | 0
F87-3 | 820 | C | 10 | 190 |  |  | 0
FPB-8-7 |  |  |  | 540 |  | 0 | 0

## FPB SGRD (3)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: FPB SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F88-1 | 819 | C | 8 | 110 |  |  | 0
F88-2 | 819 | C | 10 | 205 |  |  | 0
F88-3 | 819 | C | 10 | 205 |  |  | 0
F88-4 | 819 | C | 10 | 205 |  |  | 0
F88-5 | 819 | C | 10 | 205 |  |  | 0
FPB-8-8 |  |  |  | 930 |  | 0 | 0
F89-1 | 817 | C | 10 | 170 |  |  | 0
F89-2 | 817 | C | 8 | 85 |  |  | 0
F89-3 | 818 | C | 10 | 170 |  |  | 0
F89-4 | 818 | C | 8 | 85 |  |  | 0
F89-5 | 817 | C | 10 | 170 |  |  | 0
F89-6 | 816 | C | 10 | 170 |  |  | 0
F89-7 | 816 | C | 10 | 170 |  |  | 0
FPB-8-9 |  |  |  | 1020 |  | 0 | 0
#DIV/0!
F810-1 | 801C | C3 | 10 | 170 |  |  | 0
F810-2 | 801C | C3 | 10 | 170 |  |  | 0
F810-3 | 801C | C3 | 10 | 230 |  |  | 0
F810-4 | 801C | C3 | 10 | 180 |  |  | 0
F810-5 | 801C | C3 | 10 | 180 |  |  | 0
F810-6 | 801C | C3 | 10 | 180 |  |  | 0
FPB-8-10 |  |  |  | 1110 |  | 0 | 0
F811-1 | 850 | C3 | 10 | 170 |  |  | 0
F811-2 | 850 | C3 | 10 | 170 |  |  | 0
F811-3 | 850 | C3 | 10 | 200 |  |  | 0
F811-4 | 850 | C3 | 10 | 140 |  |  | 0
F811-5 | 850 | C3 | 10 | 170 |  |  | 0
FPB-8-11 |  |  |  | 850 |  | 0 | 0

## FPB SGRD (4)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: FPB SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F812-1 | 864 | C1 |  | 255 |  |  | 0
F812-2 | 864 | C3 | 10 | 170 |  |  | 0
F812-3 | 864 | C3 | 10 | 170 |  |  | 0
F812-4 | 864 | C3 | 10 | 170 |  |  | 0
F812-5 | 864 | C3 | 10 | 170 |  |  | 0
FPB-8-12 |  |  |  | 935 |  | 0 | 0
F813-1 | 864 | C3 | 10 | 260 |  |  | 0
F813-2 | 864 | C3 | 10 | 260 |  |  | 0
F813-3 | 864 | C3 | 10 | 170 |  |  | 0
F813-4 | 864 | C3 | 10 | 170 |  |  | 0
F813-5 | 864 | C3 | 10 | 170 |  |  | 0
F813-6 | 864 | C3 | 10 | 170 |  |  | 0
F813-7 | 864 | C3 | 10 | 170 |  |  | 0
F813-8 | 864 | C3 | 10 | 170 |  |  | 0
FPB-8-13 |  |  |  | 1540 |  | 0 | 0
F814-1 | 895 | C3 | 12 | 290 |  |  | 0
F814-2 | 895 | F | 10X6 | 170 |  |  | 0
F814-3 | 895 | C3 | 12 | 290 |  |  | 0
F814-4 | 895 | C3 | 10 | 260 |  |  | 0
F814-5 | 895 | C3 | 10 | 260 |  |  | 0
F814-6 | 895 | C3 | 10 | 260 |  |  | 0
FPB-8-14 |  |  |  | 1530 |  | 0 | 0

## FPB SGRD (5)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: FPB SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
F815-1 | 895 | C1 | 8 | 150 |  |  | 0
F815-2 | 895 | F | 16X6 | 255 |  |  | 0
F815-3 | 895 | C3 | 10 | 260 |  |  | 0
F815-4 | 895 | C3 | 10 | 260 |  |  | 0
F815-5 | 895 | F | 16X6 | 255 |  |  | 0
F815-6 | 895 | C3 | 10 | 260 |  |  | 0
FPB-8-15 |  |  |  | 1440 |  | 0 | 0
F816-1 | 890A | F | 16X6 | 150 |  |  | 0
F816-2 | 890A | F | 16X6 | 150 |  |  | 0
F816-3 | 890A | F | 16X6 | 150 |  |  | 0
F816-4 | 890A | F | 16X6 | 150 |  |  | 0
F816-5 | 890A | F | 16X6 | 150 |  |  | 0
F816-6 | 890A | F | 16X6 | 150 |  |  | 0
F816-7 | 890 | F | 16X6 | 235 |  |  | 0
F816-8 | 890 | F | 16X6 | 235 |  |  | 0
F816-9 | 890 | F | 16X6 | 235 |  |  | 0
FPB-8-16 |  |  |  | 1605 |  | 0 | 0

## VAVs Single
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: Single Duct VAV's
Asset | Area Served | Address | Type | Size | Design Max CFM | Actual Max CFM | Design Min CFM | Actual Min CFM | Design Heat CFM | Actual Heat CFM | Ak (max)
VAV-8-1 | 888 |  |  |  | 540
VAV-8-2 | 885 |  |  |  | 300
VAV-8-3 | 883 |  |  |  | 270
VAV-8-4 | 880 |  |  |  | 370
VAV-8-5 | 871 |  |  |  | 1050
VAV-8-6 | 872 |  |  |  | 320
VAV-8-7 | 848 |  |  |  | 280
VAV-8-8 | 846 |  |  |  | 160
VAV-8-9 | 853 |  |  |  | 405
VAV-8-10 | 860A |  |  |  | 980
VAV-8-11 | 860 |  |  |  | 980
VAV-8-12 | 866 |  |  |  | 360
VAV-8-13 | 850 |  |  |  | 320
VAV-8-14 | 801A |  |  |  | 500
VAV-8-15 | HALL |  |  |  | 440
VAV-8-16 | 811 |  |  |  | 755
VAV-8-17 | 805 |  |  |  | 320
VAV-8-18 | 830 |  |  |  | 920
VAV-8-19 | 831 |  |  |  | 360
VAV-8-19A | 832 |  |  |  | 490
VAV-8-20 | 844 |  |  |  | 300
VAV-8-21 | 845 |  |  |  | 200
VAV-8-22 | 806 |  |  |  | 250
NOTES: | VAV'S TO BE TAKEN FROM ATTIC STOCK TO MATCH NECK SIZE AND VOLTAGE/KW. NO SUBMITTALS.
Note on C7: NTAB: BILLINGSLEY ONLY

## VAV SGRD (1)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: VAV SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V81-1 | 886 | A | 8 | 120 |  |  | 0
V81-2 | 887 | A | 8 | 80 |  |  | 0
V81-3 | 888 | A | 8 | 80 |  |  | 0
V81-4 | 889 | A | 8 | 130 |  |  | 0
V81-5 | 891 | A | 8 | 130 |  |  | 0
VAV-8-1 |  |  |  | 540 |  | 0 | 0
V82-1 | 885 | A | 8 | 150 |  |  | 0
V82-2 | 885 | A | 8 | 150 |  |  | 0
VAV-8-2 |  |  |  | 300 |  | 0 | 0
V83-1 | 884 | C1 | 8 | 60 |  |  | 0
V83-2 | 883 | C1 | 8 | 150 |  |  | 0
V83-3 | 882 | C1 | 8 | 60 |  |  | 0
VAV-8-3 |  |  |  | 270 |  | 0 | 0
V84-1 | 876 | A | 8 | 80 |  |  | 0
V84-2 | 877 | A | 8 | 50 |  |  | 0
V84-3 | 878 | A | 8 | 80 |  |  | 0
V84-4 | 881 | A | 8 | 80 |  |  | 0
V84-5 | 880 | A | 8 | 80 |  |  | 0
VAV-8-4 |  |  |  | 370 |  | 0 | 0
V85-1 | 870 | F | 16X6 | 210 |  |  | 0
V85-2 | 870 | F | 16X6 | 210 |  |  | 0
V85-3 | 871 | F | 16X6 | 210 |  |  | 0
V85-4 | 871 | F | 16X6 | 210 |  |  | 0
V85-5 | 871 | F | 16X6 | 210 |  |  | 0
VAV-8-5 |  |  |  | 1050 |  | 0 | 0

## VAV SGRD (2)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: VAV SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V86-1 | 875 | A | 8 | 80 |  |  | 0
V86-2 | 874 | A | 8 | 80 |  |  | 0
V86-3 | 873 | A | 8 | 80 |  |  | 0
V86-4 | 872 | A | 8 | 80 |  |  | 0
VAV-8-6 |  |  |  | 320 |  | 0 | 0
V87-1 | 848 | A | 8 | 140 |  |  | 0
V87-2 | 848 | A | 8 | 140 |  |  | 0
VAV-8-7 |  |  |  | 280 |  | 0 | 0
V88-1 | 847 | A | 8 | 80 |  |  | 0
V88-2 | 846 | A | 8 | 80 |  |  | 0
VAV-8-8 |  |  |  | 160 |  | 0 | 0
V89-1 | 854 | C1 | 8 | 45 |  |  | 0
V89-2 | 853 | C1 | 8 | 45 |  |  | 0
V89-3 | 857 | C1 | 8 | 70 |  |  | 0
V89-4 | 852 | C1 | 8 | 45 |  |  | 0
V89-5 | 800 | C1 | 8 | 100 |  |  | 0
V89-6 | 800 | C1 | 8 | 100 |  |  | 0
VAV-8-9 |  |  |  | 405 |  | 0 | 0
V810-1 | 863 | F | 16X6 | 245 |  |  | 0
V810-2 | 863 | F | 16X6 | 245 |  |  | 0
V810-3 | 862 | F | 16X6 | 245 |  |  | 0
V810-4 | 862 | F | 16X6 | 245 |  |  | 0
VAV-8-10 |  |  |  | 980 |  | 0 | 0
NOTES:

## VAV SGRD (3)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: VAV SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V811-1 | 861 | F | 16X6 | 245 |  |  | 0
V811-2 | 861 | F | 16X6 | 245 |  |  | 0
V811-3 | 861 | F | 16X6 | 245 |  |  | 0
V811-4 | 861 | F | 16X6 | 245 |  |  | 0
VAV-8-11 |  |  |  | 980 |  | 0 | 0
V812-1 | 856 | C1 | 8 | 60 |  |  | 0
V812-2 | 855 | C1 | 8 | 60 |  |  | 0
V812-3 | 865 | A | 8 | 80 |  |  | 0
V812-4 | 866 | A | 8 | 80 |  |  | 0
V812-5 | 867 | A | 8 | 80 |  |  | 0
VAV-8-12 |  |  |  | 360 |  | 0 | 0
813-1 | 850 | C1 | 8 | 100 |  |  | 0
813-2 | 850 | C1 | 8 | 100 |  |  | 0
813-3 | 850 | C1 | 8 | 100 |  |  | 0
813-4 | 850 | C1 | 8 | 100 |  |  | 0
VAV-8-13 |  |  |  | 400 |  | 0 | 0
814-1 | 801 | C1 | 8 | 125 |  |  | 0
814-2 | 801A | C1 | 8 | 125 |  |  | 0
814-3 | 801A | C1 | 8 | 125 |  |  | 0
814-4 | 801 | C1 | 8 | 125 |  |  | 0
VAV-8-14 |  |  |  | 500 |  | 0 | 0
NOTES:

## VAV SGRD (4)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: VAV SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
815-1 | 805B | A | 8 | 50 |  |  | 0
815-2 | 805A | A | 8 | 50 |  |  | 0
815-3 | HALL | A | 8 | 130 |  |  | 0
815-4 | 808 | F | 10X10 | 100 |  |  | 0
815-5 | 802 | C1 | 8 | 65 |  |  | 0
815-6 | 802 | C1 | 8 | 45 |  |  | 0
VAV-8-15 |  |  |  | 440 |  | 0 | 0
816-1 | 809 | A | 8 | 75 |  |  | 0
816-2 | 814 | F | 16X6 | 230 |  |  | 0
816-3 | 810 | A | 8 | 75 |  |  | 0
816-4 | 811 | A | 8 | 75 |  |  | 0
816-5 | 812 | C1 | 8 | 50 |  |  | 0
816-6 | 813 | F | 16X6 | 250 |  |  | 0
VAV-8-16 |  |  |  | 755 |  | 0 | 0
V817-1 | 805 | A | 8 | 130 |  |  | 0
V817-2 | 803 | C1 | 8 | 90 |  |  | 0
V817-3 | 815 | F | 10X10 | 100 |  |  | 0
VAV-8-17 |  |  |  | 320 |  | 0 | 0
V818-1 | 830 | F | 16X6 | 230 |  |  | 0
V818-2 | 830 | F | 16X6 | 230 |  |  | 0
V818-3 | 830 | F | 16X6 | 230 |  |  | 0
V818-4 | 830 | F | 16X6 | 230 |  |  | 0
VAV-8-18 |  |  |  | 920 |  | 0 | 0
NOTES:

## VAV SGRD (5)
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: VAV SUPPLY
Asset | Area Served | Type | Size | DESIGN CFM | Prelim CFM | FINAL CFM | % to design
V819-1 | 831 | A | 8 | 180 |  |  | 0
V819-2 | 831 | A | 8 | 180 |  |  | 0
VAV-8-19 |  |  |  | 360 |  | 0 | 0
V819A-1 | 834 | A | 8 | 200 |  |  | 0
V819A-2 | 836 | A | 8 | 100 |  |  | 0
V819A-3 | 832 | A | 8 | 80 |  |  | 0
V819A-4 | 834 | A | 8 | 110 |  |  | 0
VAV-8-19A |  |  |  | 490 |  | 0 | 0
V820-1 | 844 | A | 8 | 80 |  |  | 0
V820-2 | 843 | C1 | 8 | 70 |  |  | 0
V820-3 | 842 | C1 | 8 | 70 |  |  | 0
V820-4 | 841 | A | 8 | 80 |  |  | 0
VAV-8-20 |  |  |  | 300 |  | 0 | 0
V821-1 | 845 | A | 8 | 200 |  |  | 0
VAV-8-21 |  |  |  | 200 |  | 0 | 0
V822-1 | 806 | A | 8 | 250 |  |  | 0
VAV-8-22 |  |  |  | 250 |  | 0 | 0

## EF DD
National TAB
Project: CW 2999 - Lightbeam Health 8th Floor
Address: 2999 Olympus Dallas, TX
Asset: EF-8-1 |  |  | Area:
Unit Data |  |  |  |  | Test Data
MFG | [5 empty] | Design | Actual
Model Num |  |  |  |  | CFM | 500
Serial Num |  |  |  |  | Fan RPM
Type |  | INLINE |  |  | RL Voltage
RL Amperage
Motor Data |  |  |  |  | Suction ESP
Motor MFG |  |  |  |  | Total ESP
Frame
Horsepower |  | 293W
Motor Rpm |  | 1451
Phase |  | 1
Voltage (rated) |  | 120
Amperage (rated)
Service Factor
Asset | Area Served | Type | Size | DESIGN | CFM(1) | FINAL CFM | % to design
E81-1 | 852 | E1 |  | 50 |  |  | 0
E81-2 | 802 | E1 |  | 50 |  |  | 0
E81-3 | 853 | E1 |  | 50 |  |  | 0
E81-4 | 803 | E1 |  | 100 |  |  | 0
E81-5 | 805A | E2 |  | 125 |  |  | 0
E81-6 | 805 | E2 |  | 125 |  |  | 0
|  |  |  | 500 |  | 0 | 0
-