## Checklist Template
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (2)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (3)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (4)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (5)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (6)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (7)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (8)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (9)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (10)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (11)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (12)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (13)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (14)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (15)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (16)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (17)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (18)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (19)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (20)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (21)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (22)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (23)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (24)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (25)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.

## Checklist Template (26)
National TAB
Project: MD0055ZZ, G.H. FALLON FED BUILDING (BALTIMORE, MD)
System:
Supply Air CFM Measured:
Confirm DCV is Disabled (Demand Controlled Ventilation)
Outside Air Measurement Method (Direct PT or SA-RA PT)
Outside Air CFM Measured: (Auto-mode on VAV Systems / NA for CAV and OA units)
Outside Air CFM Measured: (with fan at maximum allowable speed) (If there are 2 OA dampers the min damper is open and the econ damper is closed)
If Outside Air CFM is determined by Supply - Return air CFM, document the Measured Return Air CFM:
BAS Setpoint. Document BAS Setpoint at time of testing. Include Outside Air Damper Setpoint BAS shows.
BAS Screenshot. Request Facility Team to save screenshots of the BAS screen for each AHU (thumb drive) and GSA or O&M upload to the google drive.
Document Actual Observed Outside Air Damper Position. [Visual % Open: 0%, 25%, 75%, 100%.]
AHU Information & Verification. Include Photo Documentation
Attach Photos of AHU Nameplate.
Pre-Filter MERV Rating (or NA)
Pre-Filter Size
Final Filter MERV Rating
Final Filter Size
Belts - Visual Assessment of condition
Belts - Size and quantity
Note any modifications made to AHU set points to operate in full capacity.
Note if the AHU has full air side economizing ability & Damper Type.
Electrical connections - Visual assessment. Document motor Voltage and Amperage.
Heating Coil(s) - Visual assessment and photo documentation.
Cooling Coil(s) - Visual assessment and photo documentation.
Condensate Pan(s) - Visual assessment and photo documentation.
Any unusual operation observed? (including vibration, over-pressure, etc.)
Exhaust System Status (on/off). If this does not apply for this AHU, "N/A"
Visually inspect outdoor air intake louvers, bird screens, mist eliminators, and adjacent areas for cleanliness and integrity.
Note ALL visible debris or visible biological material observed, physical damage to louvers, screens, or mist eliminators, and if such damage impairs the item from providing the required outdoor air entry.
List any found deficiencies. Note any remarks or comments, including corrective actions. Include photo documentation of any relevant findings.