## Sheet1
NATIONAL TAB
BUILDING READINESS
Assigned Organization: National TAB
GENERAL READINESS
| SUBSTANTIAL COMPLETION DATE? | 2023-02-10
| ANTICIPATED DATE OF TURNOVER DATE? | 2023-02-13
| ANTICIPATED GRAND OPENING DATE? | 2/27/23 - would have to verify with owner
| DOES THE INSPECTOR REQUIRED A T&B REPORT TO ISSUE CoO? IF SO, WHEN ARE FINALS ANTICIPATED FOR? | Yes. 2/6/23
| IS PERMANENT POWER TURNED ON TO THE BUILDING (THE SPACE)? | No
| IS THE GAS METER SET AND GAS TURNED ON TO THE BUILDING? | No
| ARE ALL EXTERIOR DOORS AND WINDOWS INSTALLED (BUILDING IS SEALED)? | Yes except for front door
| IS HVAC DUCTWORK COMPLETE? IF NOT, WHEN WILL IT BE COMPLETED? | In process. 1/23/23
| ARE ALL DIFFUSERS INSTALLED? IF NOT, WHEN WILL IT BE COMPLETED? | No. 1/23/23
| ARE DAMPERS INSTALLED? IF NOT, WHEN WILL IT BE COMPLETED? | No. 1/23/23
| ARE RTUS INSTALLED? WIRED? IF NOT, WHEN ARE THEY ANTICIPATED TO BE INSTALLED AND WIRED? HAVE STARTUPS BEEN COMPLETED? IF NOT, WHEN ARE STARTUPS ANTICIPATED FOR? | RTU's are installed. Wiring to be completed 1/19/23. start up up be 1/20/23
| ALL LAYIN CEILING TILES ARE INSTALLED? IF NOT, WHEN ARE THEY ANTICIPATED TO ALL BE INSTALLED? | No. 1/18/23
| WHEN WILL COOKING EQUIPMENT ARRIVE AND WHEN ARE YOU ANTICIPATING STARTUPS FOR? | Arrives 1/30/23. Start ups 2/6/23
FINAL READINESS
Building
| DOES BUILDING HAVE ROOF HATCH OR A ROOF LADDER FOR ROOF ACCESS? | Yes
| IF HIGH GRD - WHAT HEIGHT STEP LADDER DO WE NEED (10, 12, ETC)? | Max height is 9'-6"
HVAC Systems
| ELECTRICIAN HAS VERIFIED POWER TO ALL FANS & PROPER ROTATION? IF NOT, WHEN IS THIS ANTICIPATED TO BE COMPLETED? | No. 1/19/23
| HAS MECHANICAL CONTRACTOR VERIFIES THAT ECONOMIZERS ARE FUNCTIONAL? IF NOT, WHEN IS THIS ANTICIPATED TO BE COMPLETED? | No. 1/20/23
| WILL CLEAN FILTERS BE INSTALLED IN THE UNITS FOR BALANCING? | Yes
Hood Systems
| IS THE GREASE DUCT/HOOD DUCTWORK INSTALLED? IF NOT, WHEN IS THE ANTICIPATED COMPLETION DATE? | Yes. Duct wrapping starting next week
| ARE HOODS INSTALLED AND WIRED? IF NOT, WHEN IS THE ANTICIPATED COMPLETIONDATE FOR THIS? HAVE STARTUPS BEEN COMPLETED, IF NOT, WHEN IS THE ANTICIPATED STARTUP DATE? | Yes. Start ups 1/20/23
| ARE EFS INSTALLED ON CURBS AND WIRED? IF NOT, WHEN IS THE ANTICIPATED COMPLETION DATE? HAVE STARTUPS BEEN COMPLETED, IF NOT, WHEN IS THE ANTICIPATED STARTUP DATE? | ?
| IS THE MUA INSTALLED AND WIRED? IF NOT, WHEN IS THE ANTICIPATED COMPLETION DATE FOR THIS? HAVE STARTUPS BEEN COMPLETED, IF NOT, WHEN IS THE ANTICIPATED STARTUP DATE? | RTU-2 acts as the make up air unit. Start up 1/20/23
| HAS THE ANSUL FINAL BEEN COMPLETED? IF NOT, WHEN IS IT SCHEDULED FOR? | No. 2/8/23
Mechanical Contractor
| WILL THE MECHANICAL CONTRACTOR BE ON SITE AS NEEDED? | Yes as scheduled
| MECHANICAL CONTRACTOR COMPANY NAME, CONTACT NAME, CONTACT PHONE NUMBER, AND CONTACT EMAIL: | Marxaire, Rick Cooper, 303-435-8710, rick@marxaire.com; please include me in all coorespondence. Westec, Chris Thompson, 303-684-9900, chris@westecconstruction.com
NOTES/COMMENTS: